## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-010 ITP Concrete for Minor Structures and Incidental Works Rev 0 | itp |  |  |  |  | DN1211-010 ITP Concrete for Minor Structures and Incidental Works Rev 0
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance/Conformance criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
label | Standard/Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 5 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA - R
checkpoint | 3.02.02 - Survey Setout
label | Acceptance/Conformance criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard/Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.02 - Service Location
label | Acceptance/Conformance criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard/Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.02.03 - Internal Permits
label | Acceptance/Conformance criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard/Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.03 - External Permits
label | Acceptance/Conformance criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard/Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | MSQA - R
checkpoint | 3.02.04 - Approved Construction Drawings
label | Acceptance/Conformance criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard/Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Mix Design
label | Acceptance/Conformance criteria - Typical structures ‐Confirm supply of 'high grade' 20MPaconcrete; 19mm max aggregate size.
label | General site concrete
label | ○ 10MPa Where specified ondrawings, use marine grade concrete
label | ○ 30MPa The Contractor shallensure that the readymix supplier can provide mix designinformation andstrength testingrecords on request.
label | Standard/Specification - Aurecon Civil Spec Section 14.6
label | Verifying Document - Mix Design Report Approval
label | Frequency - Upon Request / prior to Use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
label | MSQA - R
checkpoint | 4.01.02 - Motar
label | Acceptance/Conformance criteria - Consisting of two parts fine, sharp, well graded sand to one part dry cementMix by hand or mixer in small qunatities,use within 30 minutes
label | Standard/Specification - Aurecon Civil Spec Section 14.6.5
label | Verifying Document - In process check
label | Frequency - Prior to each pour
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 4.01.03 - Reinforcement
label | Acceptance/Conformance criteria - Reinforcement andembedded items cut, bent (cold) andaccurately placed asshown on design drawings. At least30mm cover to all reinforcing +5mm/‐0mmBar spacing as per drawings +/‐ 10mmBend locations as perdrawings +/‐5mm
label | Standard/Specification - Aurecon Civil Spec Section 14.6.7, AS/NZS 4671
label | Verifying Document - In process check
label | Frequency - Prior to each pour
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
section | SECTION 5 – CONSTRUCTION ACTIVITY – CONCRETE INSTALLATION
checkpoint | 5.01.01 - Pre Pour Inspection Concrete Placement
label | Acceptance/Conformance criteria - Notify Engineer for inspection of formwork 24 hours prior to pour forinspection
label | Verifying Document - QA Sheet
label | Frequency - Prior to each pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature - I
label | MSQA - I
checkpoint | 5.01.02 - Pour Plan
label | Acceptance/Conformance criteria - Place concrete and construction joints as per design drawings Exposed surfaces: F4 formed finish (or F5 if specified), U2 screeded finish Slabs: U3 trowel finish for internal slabs, U5 textured forexternal slabs
label | ○ Delivery dockets dated and showing the concrete supplier and design strength shall be collected and held for every pour. Record location and date of each pour
label | Standard/Specification - NZS 3124
label | Verifying Document - QA Sheet Delivery Dockets
label | Frequency - For Each Pour
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Engineer Rep Signature - R
label | MSQA - R
checkpoint | 5.01.03 - Testing
label | Acceptance/Conformance criteria - Slump test during pour to check workability of concrete or as directed by Engineer 3 cylinder tests taken for each pour. Slump target as per mix design 120 mm when measured at the point of delivery to site.
label | Standard/Specification - Aurecon Civil Spec; Section 14.7.12, NZS 3112
label | Verifying Document - QA Sheet, UCS Test Report
label | Frequency - Each pour / every 75m3 (one sample for pours less than 75m3)
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.04 - Independent Testing
label | Acceptance/Conformance criteria - The Engineer's Rep may request site samples/cores for independent testing of fresh or cured concrete to review the grading, mix design, strength and thickness.
label | Verifying Document - IANZ Lab Report
label | Frequency - Upon Request
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Engineer Rep Signature - R
label | MSQA - R
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature - R
label | MSQA - R
checkpoint | 6.01.02 - Survey Records
label | Acceptance/Conformance criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | Engineer Rep Signature - R
label | MSQA - R
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance/Conformance criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen/RFI reference
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
label | MSQA - R
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance/Conformance criteria - Update the project Defect, Snag and Punch List Register
label | Standard/Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Engineer Rep Signature - R
label | MSQA - R