## New Guardrail Install
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M23, NZTA B/2, |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. GUARDRAIL HARDWARE ACCEPTANCE
1.01 | Guardrail Hardware | Compliant with Standards | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | MASH Tested | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
1.03 | Labelling | All components labelled with AS/NZS3845 | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
2.0. CONSTRUCTION
2.01 | Service Location | Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area | M | Where every post will be installed | Visual on Site Potholing | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.02 | Drill Post Holes | Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends | M | Where every post will be installed | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | Install Posts | Install Post 875mm deep, Top of post 786mm above finished road level | M | Where every post will be installed | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | A | I | R | dd/mm/yy
2.04 | Backfill post hole | Backfill Posthole | M | Where every post will be installed | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.06 | Install Cariages Carriages | Install New Carriages at Correct Height to Achieve 787mm above road level | H | At Every Post | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | I | A | R | dd/mm/yy
2.07 | Install W-Beam Rails | Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post | M | At Every Post | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.08 | Overlap Rails | Overlap Rails during installation to there is no leading edge facing traffic | M | Every W-Beam Rail Joint | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.09 | Splice Bolt Installation | Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection | M | Every 2nd Post | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Terminal End
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M23, NZTA B/2, |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Site Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. GUARDRAIL HARDWARE ACCEPTANCE
1.01 | Terminal Hardware | Compliant with Standards | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | MASH Tested | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
1.03 | Labelling | All components labelled with AS/NZS3845 | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet | Contractor |  | A | I | R | dd/mm/yy
2.0. CONSTRUCTION
2.01 | Service Location | Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area | M | Where every post will be installed | Visual on Site Potholing | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.02 | Drill Post Holes | Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends | M | Where every post will be installed | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | Install Posts | Install Post 1100mm-1900mm deep, Top of post 786mm above finished road level | M | Where every post will be installed | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | A | I | R | dd/mm/yy
2.04 | Backfill post hole | Backfill Posthole | M | Where every post will be installed | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.06 | Terminal Ends | Install Terminal Ends to NZTA M23 Psec and Supplier Installtion Guidelines | H | At Every Post | Measure | Site Engineers Approval | Measurement Sheet | Contractor |  | I | A | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.