## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Foam Bitumen Stabilisation - Materials | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation - Materials Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Guardrail Hardware
label | Detail of Activity / Test - Compliant with Standards
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Guardrail Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Remove Splice Bolts
label | Detail of Activity / Test - Unbolt M16x32 Splice Bolts at splice joint eaither end of the W-Beam rail
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - All Splice BoltsBolts
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Remove Carriage Bolts
label | Detail of Activity / Test - Unbolt each carriage bolt on W-Beam rail.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - All Carriage Bolts
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Replace Carriage
label | Detail of Activity / Test - Remove existing Carriage form Post and replace with Ezy-Lift Carriage
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - All Carriages
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Bolt Carriage
label | Detail of Activity / Test - Reinstall Carriage Bolts and Washers Tight
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - All Carriage Bolts
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.05 - Determine Height of Guardrail above new pavement
label | Detail of Activity / Test - Top of W-Beam 787mm Above Finished Road Level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Install Cariages Carriages
label | Detail of Activity / Test - Install New Carriages at Correct Height to Achieve 787mm above road level
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Install W-Beam Rails
label | Detail of Activity / Test - Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.08 - Overlap Rails
label | Detail of Activity / Test - Overlap Rails during installation to there is no leading edge facing traffic
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every W-Beam Rail Joint
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.09 - Splice Bolt Installation
label | Detail of Activity / Test - Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every 2nd Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - New Guardrail Installation - Terminal End | itp |  |  |  |  | ITP - New Guardrail Installation - Terminal End Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Terminal Hardware
label | Detail of Activity / Test - Compliant with Standards
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Terminal Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Service Location
label | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual on Site Potholing
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Drill Post Holes
label | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Install Posts
label | Detail of Activity / Test - Install Post 1100mm-1900mm deep, Top of post 786mm above finished road level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Backfill post hole
label | Detail of Activity / Test - Backfill Posthole
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Terminal Ends
label | Detail of Activity / Test - Install Terminal Ends to NZTA M23 Psec and Supplier Installtion Guidelines
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - New Guardrail Installation | itp |  |  |  |  | ITP - New Guardrail Installation Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Guardrail Hardware
label | Detail of Activity / Test - Compliant with Standards
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Guardrail Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Service Location
label | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual on Site Potholing
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Drill Post Holes
label | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Install Posts
label | Detail of Activity / Test - Install Post 875mm deep, Top of post 786mm above finished road level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Backfill post hole
label | Detail of Activity / Test - Backfill Posthole
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Install Cariages Carriages
label | Detail of Activity / Test - Install New Carriages at Correct Height to Achieve 787mm above road level
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Install W-Beam Rails
label | Detail of Activity / Test - Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.08 - Overlap Rails
label | Detail of Activity / Test - Overlap Rails during installation to there is no leading edge facing traffic
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every W-Beam Rail Joint
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.09 - Splice Bolt Installation
label | Detail of Activity / Test - Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every 2nd Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - P11 OGPA Pre Construction | itp |  |  |  |  | ITP - P11 OGPA Pre Construction Rev 0
section | 1.0. Pre-Commencement Activities
checkpoint | 1.1 - Approved JMF for Asphalt Surfacing
label | Detail of Activity / Test - JMF reference in here
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - JMF Validated in accordance with NZTA P11:2023
label | Record documents (QCP - Quality Control Portal) - Mix Design Report
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - JMF expiry date and validation details in here
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Site Conditions
label | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - Weather conditions and Site is suitable for paving
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Roughness
label | Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm Specified Ride requirements can be met
label | Acceptance Criteria - Site is suitable for paving: The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP.
label | Record documents (QCP - Quality Control Portal) - NASSRA Report
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Traffic Loops
label | Detail of Activity / Test - Communication with affected parties
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
label | Inspection / Test method - Visual
label | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
label | Record documents (QCP - Quality Control Portal) - Communication
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - only required where existing traffic loops are present
label | Designer -
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Paving Plan
label | Detail of Activity / Test - Paving Plan to be completed
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - NZTA M27: 2020 Clause 9.5.1
label | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages
label | Record documents (QCP - Quality Control Portal) - String Sheet
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - P11 OGPA Construction | itp |  |  |  |  | ITP - P11 OGPA Construction Rev 0
section | 2.0. MANUFACTURE OF ASPHALT
checkpoint | 2.1 - Temperatures
label | Detail of Activity / Test - Mixing of aggregates and bitumen
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
label | Inspection / Test method - Plant temperature probes
label | Acceptance Criteria - PG64 V/E (Flexiplus Bind) binder mixing range:
label | ○ 145 to 165 deg.C
label | ○ NZTA M27: 2020 states max. 185 deg.C
label | Record documents (QCP - Quality Control Portal) - Plant site diary
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.2 - Production Asphalt
label | Detail of Activity / Test - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
label | Inspection / Test method - NZS 4407, Test 3.8.1
label | Acceptance Criteria - NZTA P11: 2023, Refer to Table 6.3
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.3 - Production Asphalt
label | Detail of Activity / Test - Binder Content
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
label | Acceptance Criteria - NZTA P11: 2023
label | ○ Individual Test Result: ± 0.5
label | ○ Mean of Three Test Results: ± 0.3
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
section | 3.0. PLACING AND FINISHING
checkpoint | 3.1 - Milling
label | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - Site is suitable for paving
label | Record documents (QCP - Quality Control Portal) - String Sheet
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Tack Coat, OR
label | Detail of Activity / Test - Application of Tack Coat
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
label | Inspection / Test method - Dip bitumen emulsion tank before and after
label | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.3 - Membrane Seal
label | Detail of Activity / Test - Application of Membrane Seal
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
label | Inspection / Test method - Sealing Records
label | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
label | Record documents (QCP - Quality Control Portal) - Sealing Records
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.4 - Temperature
label | Detail of Activity / Test - Pavement Surface
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
label | Inspection / Test method - Infrared gauge
label | Acceptance Criteria - ≥ 10 °C or as otherwise agreed with NZTA
label | Record documents (QCP - Quality Control Portal) - Site diary
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - Must get NZTA approval if < 10°C
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.5 - Temperature
label | Detail of Activity / Test - Asphalt Delivery temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
label | Inspection / Test method - Temperature Probe
label | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
label | ○ Min. ≥ 120 deg.C in the Paver
label | ○ <120°C to be Rejected
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.6 - Temperature
label | Detail of Activity / Test - Compaction Temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
label | Inspection / Test method - Temperature Probe/Infrared gauge
label | Acceptance Criteria - ≥ 115°C at commencement of compaction. < 80°C - Stop Rolling
label | Record documents (QCP - Quality Control Portal) - Site diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.7 - Mat
label | Detail of Activity / Test - Load Locate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Each load
label | Inspection / Test method - M/27
label | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
label | – Truck ID/Rego/Driver
label | – Depart Plant Time
label | – Arrive Site Time
label | – AC Temp on Arrival
label | – Tonnage
label | – Run Width
label | – Estimated Run Length
label | – Calculated Area
label | – Calculated Average Depth
label | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.8 - Mat
label | Detail of Activity / Test - Thickness Monitoring
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
label | Inspection / Test method - Dipping
label | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.9 - Mat
label | Detail of Activity / Test - Shape
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
label | Inspection / Test method - 3m Straight edge
label | Acceptance Criteria - NZTA P11: 2023 - section 14.2.
label | ○ Not more than 5mm under a 3m Straight Edge parallel or perpendicular to centre line.
label | Record documents (QCP - Quality Control Portal) - Straight Edge Record
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.10 - Paving Quality
label | Detail of Activity / Test - Texture
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
label | Inspection / Test method - Sand Circle or HSD
label | Acceptance Criteria - NZTA T/10: 2013
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.11 - Paving Quality
label | Detail of Activity / Test - Alignment
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
label | Inspection / Test method - As Built Survey
label | Acceptance Criteria - ±50 mm from drawings
label | Record documents (QCP - Quality Control Portal) - Survey As builts
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.12 - Post Paving Completion Checks
label | Detail of Activity / Test - Site clear and cleanup
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.13 - Post Paving Completion Checks
label | Detail of Activity / Test - Pavement Marking
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Roadmarking is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.14 - Post Paving Completion Checks
label | Detail of Activity / Test - Cold Joint Bandaging
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Cold joint bandaging is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.15 - Post Paving Completion Checks
label | Detail of Activity / Test - Service Covers Checked
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Check that service covers are cleared and level with the pavement
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.16 - Post Paving Completion Checks
label | Detail of Activity / Test - Traffic Loops Reinstated
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Check that affected traffic loops have been reinstated
label | Record documents (QCP - Quality Control Portal) - Communication
label | Responsibility - Paving Contractor
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - P11 OGPA Post Construction | itp |  |  |  |  | ITP - P11 OGPA Post Construction Rev 0
section | 4.0. As Built Records
checkpoint | 4.1 - Assessment of all test results for conformity
label | Detail of Activity / Test - Review against ITP Requirements
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
label | Inspection / Test method - Review
label | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
label | Record documents (QCP - Quality Control Portal) - NCR
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - RAMM pavement and surface records
label | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
label | Inspection / Test method - Prepare Data
label | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
checkpoint | 4.3 - Paving Quality
label | Detail of Activity / Test - Ride Quality
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane
label | Inspection / Test method - NAASRA
label | Acceptance Criteria - Max 100m Rolling Average 60 Counts/km
label | ○ Max 20m NASSRA 70 Counts/km
label | ○ Refer TNZ TM 7003 v1 (2006)
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
label | Responsibility - Paving Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature