## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Terminal End | itp |  |  |  |  | ITP - Terminal End Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Terminal Hardware
label | Detail of Activity / Test - Compliant with Standards
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Terminal Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Service Location
label | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual on Site Potholing
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Drill Post Holes
label | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Install Posts
label | Detail of Activity / Test - Install Post 1100mm-1900mm deep, Top of post 786mm above finished road level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Backfill post hole
label | Detail of Activity / Test - Backfill Posthole
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Terminal Ends
label | Detail of Activity / Test - Install Terminal Ends to NZTA M23 Psec and Supplier Installtion Guidelines
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - New Guardrail Installation | itp |  |  |  |  | ITP - New Guardrail Installation Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Guardrail Hardware
label | Detail of Activity / Test - Compliant with Standards
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Guardrail Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Service Location
label | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual on Site Potholing
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Drill Post Holes
label | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Install Posts
label | Detail of Activity / Test - Install Post 875mm deep, Top of post 786mm above finished road level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Backfill post hole
label | Detail of Activity / Test - Backfill Posthole
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Install Cariages Carriages
label | Detail of Activity / Test - Install New Carriages at Correct Height to Achieve 787mm above road level
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measurement Sheet
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Install W-Beam Rails
label | Detail of Activity / Test - Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.08 - Overlap Rails
label | Detail of Activity / Test - Overlap Rails during installation to there is no leading edge facing traffic
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every W-Beam Rail Joint
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.09 - Splice Bolt Installation
label | Detail of Activity / Test - Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every 2nd Post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature