## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-014
[11 empty] | Revision : 1 | 2024-08-29
Client: |  | City of Melbourne |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Swanston Triangle |  | Subsurface Drainage |  | Name: Oli Brooks |  | Name: |  |  | Name:
Job No: |  |  |  | Specifications: VicRoads Specification Section 701, 705 and Drawings
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Victoria/Swanston Triangle |  | Date : 23/01/2024 |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Document review | This ITP signed off | HP* | Site Engineer Site Foreman | N/A |  | N/A
1.3 | Material Classification |  | Each Lot | Subsurface drainage pipes: (behind bluestone wall) 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2. Subsurface drainage pipes: (in soft landscaping area) 300mm wide megaflo Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (clean washed coarse sand for megaflo, 20mm screenings for behind bluestone wall) Geotextiles: Shall comply with Cl 702.06. Flushout risers: constructed to the detail of SD 1631 | 702.04 702.05 702.06 | Verify | This ITP signed off Delivery dockets, product spec sheets etc. | WP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Weekly, per operator | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Site Engineer Site Foreman | N/A
2.2 | Excavation of Trench |  | Each Lot | Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. | 702.08 | Visual Inspection | This ITP signed off | HP* | Site Engineer | N/A
2.3 | Placement of bedding |  | Each Lot | Bedding of granular filter material, sand or screenings placed across bottom of trench and screeded or graded to level | 702.09 (c ) | Visual Inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.4 | Placing pipes and geofabric (if required) |  | Each Lot | Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping. | 702.09 | Visual Inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.5 | Placement of backfill |  | Each Lot | Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing | 702.09 (g) | Visual inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.6 | Flushout risers |  | Each Lot | Installed in accordance with drawings and Cl 702.10 | 702.1 | Verify | ITP Signed Photos | HP* | Site Engineer | N/A |  | N/A
3 | Testing & Completion
3.3 | As-built |  | At completion of job | Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts. | Project tech specs 14.4.3.a | Document submission | ITP Signed As-built plan | HP | Client Site Engineer
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.