## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | FHC-ITP-005
[11 empty] | Revision : 1 | Date : 29/08/2023
Client: |  | City of Melbourne |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Swanston Triangle |  | Tree Pits |  | Name: Oli Brooks |  | Name: |  |  | Name:
Job No: |  |  |  | Specifications: City of Melbourne Design Standards 304.01 & 706.03, Drawing 1P 50320, City of Melbourne Streetscape Blue Green Infrastructure Design Standards Detail 4: Raingarden Soil Profile & Detail 16: Covered Raingarden Inlet Grate
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Victoria/Swanston Triangle |  | Date : 29/08/2023 |  | Date : |  |  | Date:
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Client Surveyor Foreman | Client | Fulton Hogan | Fulton Hogan Subcontractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  |  |  | Drawings and drawing registers | Document review | This ITP signed off | HP* | Project Engineer | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Document review | This ITP signed off | HP* | Site Engineer Site Foreman | N/A
1.3 | Precast Materials acceptance |  | Each Delivery | Precast kerb inlet blocks and pit grates and frames shall comply with Design Standard 304.4, and City of Melbourne drawings 1P 50305 and 1P 50320. All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610. | VicRoads Spec. Cl. 610 City of Melbourne Standard Drawings | Visual Inspection Verify | This ITP signed Manufacturer certificate or accreditation | IP | Site Engineer | N/A |  | N/A
1.4 | Material Classification |  | Prior to start | Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092. Drainage Backfill: 5mm screenings Transition Layer: Sand/Coarse Sand Filtration Layer: As confirmed by the client (TBC) Drainage pipe: 100mm AGI pipe (no sock) Flushout pipe: 100mm PVC solid pipe with screw cap | 701.09(d) 701.091 701.092 Project Drawing CI-00080 | Visual Inspection | This ITP signed off Delivery dockets, product spec sheets etc. | WP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Weekly, per operator | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Site Engineer Site Foreman | N/A
2.2 | Set out pits |  | Prior to start | The position of all pits are to be confirmed with the superintendent. The inverts of all outlets are to be checked to ensure there is sufficient flow to the downstream system and that there are no service clashes. | Drawings | Visual Inspection | ITP Signed | HP | Client Site Engineer
2.3 | Excavation |  | Each Pit | Excavation is to be to sufficient depth to allow for backfill layers to be placed at the required thicknesses. | Drawings | Visual Inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.4 | Placing pipes and geofabric (if required) |  | Each Pit | Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping. | 702.09 | Visual Inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.5 | Placing drainage, transition and filtration layers |  | Each Pit | Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. | 702.09 (g) | Visual inspection | ITP Signed Photos | IP | Site Engineer | N/A
2.6 | Placing structural soil (if required) |  | Each pit | Structural soil placed and compacted in layers. Volume as per IFCs. | Drawings | Visual Inspection Survey Volume | ITP Signed | IP | Site Engineer | N/A
2.7 | Flushout risers |  | Each Lot | Installed in accordance with drawings and Cl 702.10 | 702.1 | Verify | ITP Signed Photos | HP* | Site Engineer | N/A
2.8 | Place and set side entry backing block, grate and frame |  | Each Pit | Entry blocks, grates and frames must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings. | City of Melbourne drawings 1P 50305 and 1P 50320. | Visual Inspection | ITP Signed Photos | IP | Site Enginer | N/A
2.9 | Place tree guard and grate for bioretention tree pit |  | Each Pit | Guards and grates must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings. | City of Melbourne design standard 706.03 | Visual Inspection | ITP Signed Photos | IP | Site Enginer | N/A
3 | Testing & Completion
3.1 | As-built |  | At completion of job | Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts. | Project tech specs 14.4.3.a | Document submission | ITP Signed As-built plan | HP | Client Site Engineer
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent