## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-003 - Stormwater Drainage | itp |  |  |  |  | ITP-003 - Stormwater Drainage
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Precast Materials acceptance
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
label | ○ Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
label | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl. 610
label | ○ Cl.619
label | ○ Cl. 701.04
label | ○ Cl. 701.05(a) & (e)
label | ○ Cl. 705.04
label | ○ AS4058
label | ○ AS4680
label | ○ AS5100
label | ○ City of Melbourne Standard Drawings
label | INSPECTION/TEST METHOD: Visual Inspection, Verify
label | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.7 Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.8 Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Weekly, per operator
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 2.2 Set out drainage
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.151, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Excavation (pits)
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
label | REFERENCE DOCUMENTS: 705.05b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: 701.20, 701.20a
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.7 Place pipes & precast pits
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.9 Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.10 Sealing - for joining culvert sections and pipe penetrations in pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | REFERENCE DOCUMENTS: 610.32, 701.17c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.11 Survey of laid pipe or pit
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Survey Conformance Point
label | RECORD OF CONFORMITY: ITP Signed, As-built
label | SCP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.12 Haunching & compaction of bedding material
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
label | ○ Loose layer thickness <=150mm
label | ○ Compacted to refusal using hand held mechanical equipment.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.16, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | WP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
checkpoint | 2.13 Place & compact backfill material over pipes
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.19, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.14 Place & compact backfill material around pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
label | ○ Compacted to refusal using hand held mechanical equipment.
label | REFERENCE DOCUMENTS: 705.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.15 Install step irons
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: For pits > 1m deep.
label | REFERENCE DOCUMENTS: 705.12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
label | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.17 Place pit covers
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
label | REFERENCE DOCUMENTS: 705.17, CoM Standard Pit Lid Drawing
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
section | Testing & Completion
checkpoint | 3.1 CCTV inspection
label | FREQUENCY: Each new line
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: 701.3
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: CCTV Report
label | HP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Flushing of pipes
label | FREQUENCY: Each line
label | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
label | REFERENCE DOCUMENTS: 701.28
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 As-built
label | FREQUENCY: At completion of job
label | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
label | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
label | INSPECTION/TEST METHOD: Document submission
label | RECORD OF CONFORMITY: ITP Signed, As-built plan
label | HP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-004 - Subsurface Drainage | itp |  |  |  |  | ITP-004 - Subsurface Drainage
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: (behind bluestone wall) 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | ○ Subsurface drainage pipes: (in soft landscaping area) 300mm wide megaflo
label | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (clean washed coarse sand for megaflo, 20mm screenings for behind bluestone wall)
label | ○ Geotextiles: Shall comply with Cl 702.06.
label | ○ Flushout risers: constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
label | WP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Weekly, per operator
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 2.2 Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
label | REFERENCE DOCUMENTS: 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material, sand or screenings placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: 702.09 (c )
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
label | REFERENCE DOCUMENTS: 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Flushout risers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Testing & Completion
checkpoint | 3.3 As-built
label | FREQUENCY: At completion of job
label | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
label | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
label | INSPECTION/TEST METHOD: Document submission
label | RECORD OF CONFORMITY: ITP Signed, As-built plan
label | HP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-005 - Tree Pits | itp |  |  |  |  | ITP-005 - Tree Pits
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY:
label | ACCEPTANCE CRITERIA:
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Precast Materials acceptance
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast kerb inlet blocks and pit grates and frames shall comply with Design Standard 304.4, and City of Melbourne drawings 1P 50305 and 1P 50320.
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 610, City of Melbourne Standard Drawings
label | INSPECTION/TEST METHOD: Visual Inspection, Verify
label | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
label | ○ Drainage Backfill: 5mm screenings
label | ○ Transition Layer: Sand/Coarse Sand
label | ○ Filtration Layer: As confirmed by the client (TBC)
label | ○ Drainage pipe: 100mm AGI pipe (no sock)
label | ○ Flushout pipe: 100mm PVC solid pipe with screw cap
label | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092, Project Drawing CI-00080
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
label | WP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Weekly, per operator
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman
textbox | Date Completed:
checkpoint | 2.2 Set out pits
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: The position of all pits are to be confirmed with the superintendent.
label | ○ The inverts of all outlets are to be checked to ensure there is sufficient flow to the downstream system and that there are no service clashes.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Client Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Excavation
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Excavation is to be to sufficient depth to allow for backfill layers to be placed at the required thicknesses.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Placing pipes and geofabric (if required)
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
label | REFERENCE DOCUMENTS: 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Placing drainage, transition and filtration layers
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
label | REFERENCE DOCUMENTS: 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Placing structural soil (if required)
label | FREQUENCY: Each pit
label | ACCEPTANCE CRITERIA: Structural soil placed and compacted in layers. Volume as per IFCs.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection Survey Volume
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.7 Flushout risers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.8 Place and set side entry backing block, grate and frame
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Entry blocks, grates and frames must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
label | REFERENCE DOCUMENTS: City of Melbourne drawings 1P 50305 and 1P 50320.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.9 Place tree guard and grate for bioretention tree pit
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Guards and grates must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
label | REFERENCE DOCUMENTS: City of Melbourne design standard 706.03
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Photos
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
section | Testing & Completion
checkpoint | 3.1 As-built
label | FREQUENCY: At completion of job
label | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
label | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
label | INSPECTION/TEST METHOD: Document submission
label | RECORD OF CONFORMITY: ITP Signed, As-built plan
label | HP
label | RESPONSIBILITY: Client, Site Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-006 - Bluestone Kerb Installation | itp |  |  |  |  | ITP-006 - Bluestone Kerb Installation
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | ○ Bluestone shall be salvaged and re-used in new kerb alignment
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
label | ○ Alignment of new kerb shall be marked out using string line
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Saw cut (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: •Saw cuts shall be made to the following depth for existing asphalt pavements:
label | – Footpath: Minimum 75mm
label | – Roadway: Minimum 125mm
label | ○ Excavate to allow for design heights
label | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Concrete Placement and Setting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
label | ○ Gaps of >10-30mm< shall be provided and filled with mortar
label | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Mix
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
label | ○ 16% cement
label | ○ 16% stonedust
label | ○ 67% blended wash sand
label | ○ 1% lime ready mix grout
label | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972, CoM SD 1P 50406
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-007 - Bluestone Footpath | itp |  |  |  |  | ITP-007 - Bluestone Footpath
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
label | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
label | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
label | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
label | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Bed
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
label | ○ All pavers shall be coated in mortar slurry on rear face before laying
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Cutting of Pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Placement of bluestone pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
label | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
label | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
label | ○ Where required, ply shall be laid over area of works
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.8 Grouting
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 4.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
label | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: