## Table 1
Overarching ITP items
Product Stage or Material to be Tested or Inspected | Type |  |  | How Often? | Records Required | Responsibility | Initial on completion
| T = Test | Reference or | Method/Test
| I= Inspection | Specification | Required
H= Hold point
1.0 Overarching items
ITP submitted and approved | H | NZTA M10: 2020, NZTA M27: 2020, head contract | Confirm ITP approved | prior to start of season | Copy of ITP and acceptance from Waka Kotahi | Project engineer/Renewals manager
QMP submitted and approved | H | NZTA M10: 2020, NZTA M27: 2020, head contract | Confirm QMP approved | prior to start of season | Copy of QMP and acceptance from Waka Kotahi | Project engineer/Renewals manager
QA pack submitted and approved | H | NZTA M10: 2020, NZTA M27: 2020, head contract | Confirm QA pack approved | prior to start of season | Copy of QA pack and acceptance from Waka Kotahi | Project engineer/Renewals manager
Final approved program received | H |  | Confirm final program | prior to start of season | Copy of final approved program; TAC, SAC and SCRIM | Renewals manager
Ensure accuracy of tracker with final program | I |  | Crosscheck tracker with program | prior to start of season |  | Renewals manager
Pre commencement meeting with asphalt delivery team | H | QMP | in person meeting | prior to start season | signed attendance register | Paving manager/Project engineer
JSEA submitted and communicated to team | H | QMP | JSEA approved | prior to start season, updates when required or site specific additions; To be signed on by every person working on the site | Copy of JSEA signed by AC delivery team | Paving manager/Project engineer/Supervisor
Approved JMF for Strengthening Repairs Mix | H | Design Report | Confirm validity JMF and conformance with Design report | Each mix | Copy of Approved JMF | Plant manager/Project engineer
Production testing for strenghthening repair mix | T | NZTA M10: 2020, NZTA M27: 2020 | Binder grading testing Volumetric testing | 1 test per 200T of Mix produced 1 test per 600T of mix produced | copy of IANZ accredited lab test report | Plant manager/Project engineer
Approved JMF for Wearing Course Mix | H | Design Report | Confirm validity JMF and conformance with Design report | Each mix | Copy of Approved JMF | Plant manager/Project engineer
Production testing for wearing course mixes | T | NZTA M10: 2020, NZTA M27: 2020 | Binder grading testing Volumetric testing | 1 test per 200T of Mix produced 1 test per 600T of mix produced | Copy of IANZ accredited Lab test report | Plant manager/Project engineer
Confirm or establish , NDM offset and rolling patterns | I/T |  | Lay down trial or establish a rolling pattern on site | each mix | Lay down trial report or plateau testing | Paving manager/Project engineer/Site engineer
Post construction drive over | I |  | Visual inspection | end of season |  | Renewals manager/Paving manager/ Project engineer
2.0 Out Of Season Paving
Out of Season Paving | H | Winter Surfacing Site Note | Waka Kotahi Approval | Per Applicable Site | Copy of Waka Kotahi Approval | Renewals manager/Paving manager
Dispatching Temperature compliance | T | NZTA M10: 2020 Notes - Table 3.3 | As per Table N4.1: NZTA M/10: 2014 | Per Load | Asphalt dockets | Asphalt Plant Manager/ operator
Site specific ITP items
Product Stage or Material to be Tested or Inspected | Type |  |  | How Often? | Records Required | Responsibility | Initial on completion
| T = Test | Reference or | Method/Test
| I= Inspection | Specification | Required
H= Hold point
1.0 Pre-Work
Approved Design Report | H | Site design Report | Confirm document uploaded | Each site prior to establishment | Copy of Approved Design Report | Renewals manager/Project Engineer
Pre seal inspection completed: - Confirm RP's and markouts align with design report - Establish methodology and amount of shifts - Confirm any environmental protection required - Confirm any service cover adjustment requirements - Identify potential milling dumpsites and plant parking area's - Identify TM requirements | H | Preseal inspection checksheet | Confirm document uploaded | Each site prior to establishment | Copy of pre seal inspection | Site engineer/Supervisor
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Copy of stakeholder notification / Photographs of VMS Boards | Network manager/Renewals manager/Project engineer
Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used | H | QMP | Brief all team members on day’s work plan | Each shift | Job brief, updated forward works program and screenshot of weather forecast | Site engineer/supervisor
Confirm Traffic management requirements met | H | CoPTTM/NZGTTM | Confirm Approved TMP in place | Each site | TMP | Project Engineer/Site engineer
2.0 Site set up
Ambient Conditions Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above | H | NZTA M10: 2020 9.5.2 | Temperature Gun Check Acceptable / Unacceptable | Each site | Ground temp record sheet in QA pack | QA/Supervisor
Job start, identify risks and controls, communicated to team | H | HSMP | Record all risks and controls on Hazard ID following Team discussion | Each site | Daily pre start briefing Form D02.05 | Site Supervisor/Foreman
Establish traffic management to plan | H | TMP | Site audit post set up | Each site | on site record | STMS/Site engineer
Identification of Services Service Plans on-site Shallow Services marked | H | JSEA/Permit to dig | Confirm document on-site / Visual check | Each site | Permit to dig/ service plans | Site Supervisor/Site engineer
Photograph environmental protection measures installed | I | ESMP | Record temporary measures | Each site | Photograph | Site Supervisor / Site engineer
3.0 Milling (If Required )
Milling undertaken to correct depth up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report | I | site design Report; NZTA M10: 2020 10.1 | Dip checks | Per site | Stringline sheet from QA pack | Site Supervisor / Site QA/site engineer
Proofrolling to be done on milled surface Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost. | T/I | Site design report | Proofrolling with PTR or loaded truck | Per site | Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager | Site supervisor/Site engineer
4.0 Membrane (If Required )
Application as per Design Requirements (Chip size / binder application rate) | I | Design Report | Spray Sheet's | Per site | Spraysheets | Site Supervisor / Site Engineer
5.0 Strengthening Repairs (If Required )
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC20 PMB 130°C AC20 Hi-Mod 140°C AC20 60/70 125°C | T | NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Temperature Gun Check Acceptable / Unacceptable | Per load | Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Site Supervisor/QA
Structural Asphalt Layer Thickness Each Layer >80mm with a max discrepency of +10mm nominal thickness | T | NZTA M10 2020 10.1 & Table 3.1 | Dip checks and spreadrates | each truckload | Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Site Supervisor / Site QA /Site engineer
Compaction and Air Voids | T | QMP and NDM SOP | NDM for Quality Control | Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | NDM sheet in QA pack | Site Supervisor / Site QA / Site Engineer
Proven layer thickness and compaction | T | NZTA M10: 2020 9.9 | 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and <45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Site Supervisor / Site QA/ Site engineer
7.0 Wearing Course
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC PMB 130°C AC 60/70 125°C SMA PMB 125°C SMA 60/70 120°C | T | NZTA M10: 2020Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Temperature Gun Check Acceptable / Unacceptable | Per load | Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Site Supervisor/ QA/Site engineer
Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report | T | NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1 | Dip checks and spreadrates | each truckload | Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Site Supervisor / Site QA /Site engineer
Compaction and Air Voids | T | QMP and NDM SOP | NDM for Quality Control | Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | NDM sheet in QA pack | Site Supervisor / Site QA / Site Engineer
Proven layer thickness and compaction | T | NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9 | 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and <45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report. A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Site Supervisor / Site QA/ Site engineer
8.0 Post-Construction
Supervisor to provide an update regarding site completion per shift |  | QMP | email | Per site | Email | Site Supervisor/site engineer
Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing | H | MOTSAM | Visual check | Per site | Job Sheet record & photograph | Site Engineer
Post seal inspection completed: - Driveability of site acceptable - Quality of paved surface - Linemarking correctly reinstated, including cat's eyes? - All TTM signs removed - Site; stockpile and parking area left in tidy condition - Required service cover adjustments completed; covers to be flush to +10mm with surface - Environmental protection removed | I | Post seal inspection checksheet | Confirm document uploaded | Each site within 1 week of completion | Copy of post seal inspection | Site engineer/Supervisor
As-Built records – structural patches | H | Site design report | Record as-built patch dimensions & RPs | Per site | Final site diagram from QA pack | Site engineer/QA
Collect RAMM data | H | Comply with Waka Kotahi format | Correct data supplied | Per site | Job Sheet record + As-Builts + photographs | Renewals manager/Project Engineer