## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Overarching ITP items | itp |  |  |  |  | Overarching ITP items
section | 1.0 Overarching items
checkpoint | ITP submitted and approved
label | Type - H
label | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
label | Method/Test Required - Confirm ITP approved
label | How Often? - prior to start of season
label | Records Required - Copy of ITP and acceptance from Waka Kotahi
label | Responsibility - Project engineer/Renewals manager
holdpoint | HOLD POINT
checkpoint | QMP submitted and approved
label | Type - H
label | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
label | Method/Test Required - Confirm QMP approved
label | How Often? - prior to start of season
label | Records Required - Copy of QMP and acceptance from Waka Kotahi
label | Responsibility - Project engineer/Renewals manager
holdpoint | HOLD POINT
checkpoint | QA pack submitted and approved
label | Type - H
label | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
label | Method/Test Required - Confirm QA pack approved
label | How Often? - prior to start of season
label | Records Required - Copy of QA pack and acceptance from Waka Kotahi
label | Responsibility - Project engineer/Renewals manager
holdpoint | HOLD POINT
checkpoint | Final approved program received
label | Type - H
label | Reference or Specification -
label | Method/Test Required - Confirm final program
label | How Often? - prior to start of season
label | Records Required - Copy of final approved program; TAC, SAC and SCRIM
label | Responsibility - Renewals manager
holdpoint | HOLD POINT
checkpoint | Ensure accuracy of tracker with final program
label | Type - I
label | Reference or Specification -
label | Method/Test Required - Crosscheck tracker with program
label | How Often? - prior to start of season
label | Records Required -
label | Responsibility - Renewals manager
checkpoint | Pre commencement meeting with asphalt delivery team
label | Type - H
label | Reference or Specification - QMP
label | Method/Test Required - in person meeting
label | How Often? - prior to start season
label | Records Required - signed attendance register
label | Responsibility - Paving manager/Project engineer
holdpoint | HOLD POINT
checkpoint | JSEA submitted and communicated to team
label | Type - H
label | Reference or Specification - QMP
label | Method/Test Required - JSEA approved
label | How Often? - prior to start season, updates when required or site specific additions; To be signed on by every person working on the site
label | Records Required - Copy of JSEA signed by AC delivery team
label | Responsibility - Paving manager/Project engineer/Supervisor
holdpoint | HOLD POINT
checkpoint | Approved JMF for Strengthening Repairs Mix
label | Type - H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm validity JMF and conformance with Design report
label | How Often? - Each mix
label | Records Required - Copy of Approved JMF
label | Responsibility - Plant manager/Project engineer
holdpoint | HOLD POINT
checkpoint | Production testing for strenghthening repair mix
label | Type - T
label | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020
label | Method/Test Required - Binder grading testing Volumetric testing
label | How Often? - 1 test per 200T of Mix produced 1 test per 600T of mix produced
label | Records Required - copy of IANZ accredited lab test report
label | Responsibility - Plant manager/Project engineer
checkpoint | Approved JMF for Wearing Course Mix
label | Type - H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm validity JMF and conformance with Design report
label | How Often? - Each mix
label | Records Required - Copy of Approved JMF
label | Responsibility - Plant manager/Project engineer
holdpoint | HOLD POINT
checkpoint | Production testing for wearing course mixes
label | Type - T
label | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020
label | Method/Test Required - Binder grading testing Volumetric testing
label | How Often? - 1 test per 200T of Mix produced 1 test per 600T of mix produced
label | Records Required - Copy of IANZ accredited Lab test report
label | Responsibility - Plant manager/Project engineer
checkpoint | Confirm or establish , NDM offset and rolling patterns
label | Type - I/T
label | Reference or Specification -
label | Method/Test Required - Lay down trial or establish a rolling pattern on site
label | How Often? - each mix
label | Records Required - Lay down trial report or plateau testing
label | Responsibility - Paving manager/Project engineer/Site engineer
checkpoint | Post construction drive over
label | Type - I
label | Reference or Specification -
label | Method/Test Required - Visual inspection
label | How Often? - end of season
label | Records Required -
label | Responsibility - Renewals manager/Paving manager/ Project engineer
section | 2.0 Out Of Season Paving
checkpoint | Out of Season Paving
label | Type - H
label | Reference or Specification - Winter Surfacing Site Note
label | Method/Test Required - Waka Kotahi Approval
label | How Often? - Per Applicable Site
label | Records Required - Copy of Waka Kotahi Approval
label | Responsibility - Renewals manager/Paving manager
holdpoint | HOLD POINT
checkpoint | Dispatching Temperature compliance
label | Type - T
label | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
label | How Often? - Per Load
label | Records Required - Asphalt dockets
label | Responsibility - Asphalt Plant Manager/ operator
checklist | Site specific ITP items | itp |  |  |  |  | Site specific ITP items
section | 1.0 Pre-Work
checkpoint | Approved Design Report
label | Type - H
label | Reference or Specification - Site design Report
label | Method/Test Required - Confirm document uploaded
label | How Often? - Each site prior to establishment
label | Records Required - Copy of Approved Design Report
label | Responsibility - Renewals manager/Project Engineer
holdpoint | HOLD POINT
checkpoint | Pre seal inspection completed:
label | – Confirm RP's and markouts align with design report
label | – Establish methodology and amount of shifts
label | – Confirm any environmental protection required
label | – Confirm any service cover adjustment requirements
label | – Identify potential milling dumpsites and plant parking area's
label | – Identify TM requirements
label | Type - H
label | Reference or Specification - Preseal inspection checksheet
label | Method/Test Required - Confirm document uploaded
label | How Often? - Each site prior to establishment
label | Records Required - Copy of pre seal inspection
label | Responsibility - Site engineer/Supervisor
holdpoint | HOLD POINT
checkpoint | Stakeholder Management Requirements met
label | Type - H
label | Reference or Specification - CSCMP
label | Method/Test Required - Confirm requirements followed
label | How Often? - Each site
label | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | Responsibility - Network manager/Renewals manager/Project engineer
holdpoint | HOLD POINT
checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used
label | Type - H
label | Reference or Specification - QMP
label | Method/Test Required - Brief all team members on day’s work plan
label | How Often? - Each shift
label | Records Required - Job brief, updated forward works program and screenshot of weather forecast
label | Responsibility - Site engineer/supervisor
holdpoint | HOLD POINT
checkpoint | Confirm Traffic management requirements met
label | Type - H
label | Reference or Specification - CoPTTM/NZGTTM
label | Method/Test Required - Confirm Approved TMP in place
label | How Often? - Each site
label | Records Required - TMP
label | Responsibility - Project Engineer/Site engineer
holdpoint | HOLD POINT
section | 2.0 Site set up
checkpoint | Ambient Conditions: Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above
label | Type - H
label | Reference or Specification - NZTA M10: 2020 9.5.2
button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
label | How Often? - Each site
label | Records Required - Ground temp record sheet in QA pack
label | Responsibility - QA/Supervisor
holdpoint | HOLD POINT
checkpoint | Job start, identify risks and controls, communicated to team
label | Type - H
label | Reference or Specification - HSMP
label | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | How Often? - Each site
label | Records Required - Daily pre start briefing Form D02.05
label | Responsibility - Site Supervisor/Foreman
holdpoint | HOLD POINT
checkpoint | Establish traffic management to plan
label | Type - H
label | Reference or Specification - TMP
label | Method/Test Required - Site audit post set up
label | How Often? - Each site
label | Records Required - on site record
label | Responsibility - STMS/Site engineer
holdpoint | HOLD POINT
checkpoint | Identification of Services: Service Plans on-site, Shallow Services marked
label | Type - H
label | Reference or Specification - JSEA/Permit to dig
label | Method/Test Required - Confirm document on-site / Visual check
label | How Often? - Each site
label | Records Required - Permit to dig/ service plans
label | Responsibility - Site Supervisor/Site engineer
holdpoint | HOLD POINT
checkpoint | Photograph environmental protection measures installed
label | Type - I
label | Reference or Specification - ESMP
label | Method/Test Required - Record temporary measures
label | How Often? - Each site
label | Records Required - Photograph
label | Responsibility - Site Supervisor / Site engineer
section | 3.0 Milling (If Required)
checkpoint | Milling undertaken to correct depth: up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report
label | Type - I
label | Reference or Specification - site design Report; NZTA M10: 2020 10.1
label | Method/Test Required - Dip checks
label | How Often? - Per site
label | Records Required - Stringline sheet from QA pack
label | Responsibility - Site Supervisor / Site QA/site engineer
checkpoint | Proofrolling to be done on milled surface: Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost.
label | Type - T/I
label | Reference or Specification - Site design report
label | Method/Test Required - Proofrolling with PTR or loaded truck
label | How Often? - Per site
label | Records Required - Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site
label | ○ Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager
label | Responsibility - Site supervisor/Site engineer
section | 4.0 Membrane (If Required)
checkpoint | Application as per Design Requirements (Chip size / binder application rate)
label | Type - I
label | Reference or Specification - Design Report
label | Method/Test Required - Spray Sheet's
label | How Often? - Per site
label | Records Required - Spraysheets
label | Responsibility - Site Supervisor / Site Engineer
section | 5.0 Strengthening Repairs (If Required)
checkpoint | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver.
label | Manager to be notified if temperature falls below:
label | ○ AC20 PMB 130°C
label | ○ AC20 Hi-Mod 140°C
label | ○ AC20 60/70 125°C
label | Type - T
label | Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
label | How Often? - Per load
label | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
label | Responsibility - Site Supervisor/QA
checkpoint | Structural Asphalt Layer Thickness: Each Layer >80mm with a max discrepency of +10mm nominal thickness
label | Type - T
label | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
label | Method/Test Required - Dip checks and spreadrates
label | How Often? - each truckload
label | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
label | Responsibility - Site Supervisor / Site QA /Site engineer
checkpoint | Compaction and Air Voids
label | Type - T
label | Reference or Specification - QMP and NDM SOP
label | Method/Test Required - NDM for Quality Control
label | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
label | Records Required - NDM sheet in QA pack
label | Responsibility - Site Supervisor / Site QA / Site Engineer
checkpoint | Proven layer thickness and compaction
label | Type - T
label | Reference or Specification - NZTA M10: 2020 9.9
label | Method/Test Required - 150mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=45mm lift thickness
label | ○ 100mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=35mm and <45mm lift thickness
label | ○ NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
label | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report
label | ○ A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
label | Responsibility - Site Supervisor / Site QA/ Site engineer
section | 7.0 Wearing Course
checkpoint | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver.
label | Manager to be notified if temperature falls below:
label | ○ AC PMB 130°C
label | ○ AC 60/70 125°C
label | ○ SMA PMB 125°C SMA 60/70 120°C
label | Type - T
label | Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
label | How Often? - Per load
label | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
label | Responsibility - Site Supervisor/ QA/Site engineer
checkpoint | Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness. If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report.
label | Type - T
label | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4
label | ○ NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
label | Method/Test Required - Dip checks and spreadrates
label | How Often? - each truckload
label | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
label | Responsibility - Site Supervisor / Site QA /Site engineer
checkpoint | Compaction and Air Voids
label | Type - T
label | Reference or Specification - QMP and NDM SOP
label | Method/Test Required - NDM for Quality Control
label | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
label | Records Required - NDM sheet in QA pack
label | Responsibility - Site Supervisor / Site QA / Site Engineer
checkpoint | Proven layer thickness and compaction
label | Type - T
label | Reference or Specification - NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9
label | Method/Test Required - 150mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=45mm lift thickness
label | ○ 100mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=35mm and <45mm lift thickness
label | ○ NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
label | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report.
label | ○ A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
label | Responsibility - Site Supervisor / Site QA/ Site engineer
section | 8.0 Post-Construction
checkpoint | Supervisor to provide an update regarding site completion per shift
label | Reference or Specification - QMP
label | Method/Test Required - email
label | How Often? - Per site
label | Records Required - Email
label | Responsibility - Site Supervisor/site engineer
checkpoint | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing
label | Type - H
label | Reference or Specification - MOTSAM
label | Method/Test Required - Visual check
label | How Often? - Per site
label | Records Required - Job Sheet record & photograph
label | Responsibility - Site Engineer
holdpoint | HOLD POINT
checkpoint | Post seal inspection completed:
label | – Driveability of site acceptable
label | – Quality of paved surface
label | – Linemarking correctly reinstated, including cat's eyes?
label | – All TTM signs removed
label | – Site; stockpile and parking area left in tidy condition
label | – Required service cover adjustments completed; covers to be flush to +10mm with surface
label | – environmental protection removed
label | Type - I
label | Reference or Specification - Post seal inspection checksheet
label | Method/Test Required - Confirm document uploaded
label | How Often? - Each site within 1 week of completion
label | Records Required - Copy of post seal inspection
label | Responsibility - Site engineer/Supervisor
checkpoint | As-Built records – structural patches
label | Type - H
label | Reference or Specification - Site design report
label | Method/Test Required - Record as-built patch dimensions & RPs
label | How Often? - Per site
label | Records Required - Final site diagram from QA pack
label | Responsibility - Site engineer/QA
holdpoint | HOLD POINT
checkpoint | Collect RAMM data
label | Type - H
label | Reference or Specification - Comply with Waka Kotahi format
label | Method/Test Required - Correct data supplied
label | How Often? - Per site
label | Records Required - Job Sheet record + As-Builts + photographs
label | Responsibility - Renewals manager/Project Engineer
holdpoint | HOLD POINT