## Table 1
Product Stage or Material to be Tested or Inspected | Type |  |  | How Often? | Records Required | Responsibility | Initial on completion
| T = Test | Reference or | Method/Test
| I= Inspection | Specification | required
H= Hold point
1.0 Pre-Works (Off Site)
Binder Penetration Grade | T | NZTA M1 | Property Test, NZTA M01 | 1 test certificate per bulk shipment | Test Report | Bitumen Supplier / Project Manager
Production Property - Cleaness Value | I | NZTA P/17, M06 | Sample Test - Cleaness Value, NZTA P/17, M06 | Each Stockpile | Test Report | Project Manager / Renewals Manager
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Test Report | Project Manager / Renewals Manager
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Copy of stakeholder notification / Photographs of VMS Boards | Project Manager / Renewals Manager
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Copy of stakeholder notification / Photographs of VMS Boards | Project Manager / Renewals Manager
Confirm if any environmental protection is required | I | ESMP | Record decision | Each site | Pre-seal Inspection Form | Project Manager
Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work | H | QMP | Brief all team members on day’s work plan | Each site | Pre-seal Inspection Form | Project Manager
2.0 Pre-Construction (On Site)
Job start, identify risks and controls, communicated to team | H | HSMP | Record all risks and controls on Hazard ID following Team discussion | Each site | Hazard ID form | Site Foreperson
Establish traffic management to plan | H | TMP | Site audit post set up | Each site | TTM Diary | STMS
Confirm site is on approved programme | H | Approved Programme | Record as-built site dimensions | Each Site | Pre-seal Inspection Form | Site Foreperson
Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details | H | Approved Programme | Record as-built site dimensions | Each Site | Pre-seal Inspection Form | Site Foreperson / Site QA
Stockpiled sealing chip is clean and suitable for sealing | H | QMP | Acceptable/Unacceptable | Each Stockpile | Pre-seal Inspection Form & Photograph | Site Foreperson / Site QA
Stockpiled sealing chip is the same grade(s) as specified in the chipseal design | H | QMP | Acceptable/Unacceptable | Each Stockpile | Pre-seal Inspection Form | Site Foreperson / Site QA
Record & photograph environmental protection measures installed | I | ESMP | Record temporary measures | Each site | Pre-seal Inspection Form & Photograph | Site Foreperson / Site QA
Binder application rate | T | Seal Design / Spraying Insructions | Confirm seal design requirements from programme | Per site | Spray Sheet | Site Foreperson / Site QA
Pre-Sealing surface condition | I | QMP | Acceptable/Unacceptable | Per Site | Pre-seal Inspection Form & Photograph | Site Foreperson / Site QA
3.0 Construction
Start spraying Temp >10°C | T | NZTA P/17 | Start >10°C | Per site | Spray Sheet | Site Foreperson / Site QA
Binder application variation | T | NZTA P/17 | +/- 4% (spray rate) +/- 50l (tank dip) | Per site | Spray Sheet | Site Foreperson / Site QA
Sealing chip application | I | NZTA P/17 | Full and even coverage of sprayed area | Per site | Post-seal Inspection Form | Site Foreperson / Site QA
PTR Rolling pattern | I | NZTA P/17 | Initial rolling completed along with traffic- rolling under controlled TTM | Per Site | Post-seal Inspection Form | Site Foreperson
Traffickating | I | Chapter 11 - Chipsealing in NZ | Initial rolling completed along with traffic- rolling under controlled TTM | Per Site | Post-seal Inspection Form | Site Foreperson / STMS
Traffickating | I |  | Positive Traffic Control is to remain in place for at least 6 hours after the last chip run is complete, the positive TC is to move the traffic across the full width of the road to ensure full chip imbedment | Per Site | Post-seal Inspection Form | Site Foreperson / STMS
Tagging for line marking | I | Chapter 11 - Chipsealing in NZ | Pre-seal Visual check | Per site | Post-seal Inspection Form | Site Foreperson
Post-Sealing Surfacing Condition | I | QMP | Visual check | Per site | Post-seal Inspection Form & Photograph | Site Foreperson
4.0 Post-Construction
Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing | H | MOTSAM | Visual check | Per site | Photograph | Project Manager
Spray Sheet/s Checked & Supplied for Claiming | H | QMP | Spray sheet data verified against design/programme | Per site | Spray Sheet/s | Project Manager
Collect & Upload RAMM data | H | Comply with Waka Kotahi format | Correct data supplied | Per site | Spary Sheet/s & Photographs | Renewals Manager
5.0 Out Of Season Sealing
Out of Season Sealing | H | Winter Surfacing Site Note | Waka Kotahi Approval | Per Applicable Site | Copy of Waka Kotahi Approval on- site | Project Manager / Renewals Manager