## Sheet1
Approved Design Report | H | Site design Report | Confirm document uploaded | Each site prior to establishment | Copy of Approved Design Report | Renewals manager/Project Engineer | Approved Design Report | Type - H | Reference or Specification - Site design Report | Method/Test Required - Confirm document uploaded | How Often? - Each site prior to establishment | Records Required - Copy of Approved Design Report | Responsibility - Renewals manager/Project Engineer | Approved Design Report
Pre seal inspection completed: - Confirm RP's and markouts align with design report - Establish methodology and amount of shifts - Confirm any environmental protection required - Confirm any service cover adjustment requirements - Identify potential milling dumpsites and plant parking area's - Identify TM requirements | H | Preseal inspection checksheet | Confirm document uploaded | Each site prior to establishment | Copy of pre seal inspection | Site engineer/Supervisor | Pre seal inspection completed: - Confirm RP's and markouts align with design report - Establish methodology and amount of shifts - Confirm any environmental protection required - Confirm any service cover adjustment requirements - Identify potential milling dumpsites and plant parking area's - Identify TM requirements | Type - H | Reference or Specification - Preseal inspection checksheet | Method/Test Required - Confirm document uploaded | How Often? - Each site prior to establishment | Records Required - Copy of pre seal inspection | Responsibility - Site engineer/Supervisor | Type - H
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Copy of stakeholder notification / Photographs of VMS Boards | Network manager/Renewals manager/Project engineer | Stakeholder Management Requirements met | Type - H | Reference or Specification - CSCMP | Method/Test Required - Confirm requirements followed | How Often? - Each site | Records Required - Copy of stakeholder notification / Photographs of VMS Boards | Responsibility - Network manager/Renewals manager/Project engineer | Reference or Specification - Site design Report
Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used | H | QMP | Brief all team members on day’s work plan | Each shift | Job brief, updated forward works program and screenshot of weather forecast | Site engineer/supervisor | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used | Type - H | Reference or Specification - QMP | Method/Test Required - Brief all team members on day’s work plan | How Often? - Each shift | Records Required - Job brief, updated forward works program and screenshot of weather forecast | Responsibility - Site engineer/supervisor | Method/Test Required - Confirm document uploaded
Confirm Traffic management requirements met | H | CoPTTM/NZGTTM | Confirm Approved TMP in place | Each site | TMP | Project Engineer/Site engineer | Confirm Traffic management requirements met | Type - H | Reference or Specification - CoPTTM/NZGTTM | Method/Test Required - Confirm Approved TMP in place | How Often? - Each site | Records Required - TMP | Responsibility - Project Engineer/Site engineer | How Often? - Each site prior to establishment
Ambient Conditions Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above | H | NZTA M10: 2020 9.5.2 | Temperature Gun Check Acceptable / Unacceptable | Each site | Ground temp record sheet in QA pack | QA/Supervisor | Ambient Conditions Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above | Type - H | Reference or Specification - NZTA M10: 2020 9.5.2 | Method/Test Required - Temperature Gun Check Acceptable / Unacceptable | How Often? - Each site | Records Required - Ground temp record sheet in QA pack | Responsibility - QA/Supervisor | Records Required - Copy of Approved Design Report
Job start, identify risks and controls, communicated to team | H | HSMP | Record all risks and controls on Hazard ID following Team discussion | Each site | Daily pre start briefing Form D02.05 | Site Supervisor/Foreman | Job start, identify risks and controls, communicated to team | Type - H | Reference or Specification - HSMP | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion | How Often? - Each site | Records Required - Daily pre start briefing Form D02.05 | Responsibility - Site Supervisor/Foreman | Responsibility - Renewals manager/Project Engineer
Establish traffic management to plan | H | TMP | Site audit post set up | Each site | on site record | STMS/Site engineer | Establish traffic management to plan | Type - H | Reference or Specification - TMP | Method/Test Required - Site audit post set up | How Often? - Each site | Records Required - on site record | Responsibility - STMS/Site engineer | Pre seal inspection completed: - Confirm RP's and markouts align with design report - Establish methodology and amount of shifts - Confirm any environmental protection required - Confirm any service cover adjustment requirements - Identify potential milling dumpsites and plant parking area's - Identify TM requirements
Identification of Services Service Plans on-site Shallow Services marked | H | JSEA/Permit to dig | Confirm document on-site / Visual check | Each site | Permit to dig/ service plans | Site Supervisor/Site engineer | Identification of Services Service Plans on-site Shallow Services marked | Type - H | Reference or Specification - JSEA/Permit to dig | Method/Test Required - Confirm document on-site / Visual check | How Often? - Each site | Records Required - Permit to dig/ service plans | Responsibility - Site Supervisor/Site engineer | Type - H
Photograph environmental protection measures installed | I | ESMP | Record temporary measures | Each site | Photograph | Site Supervisor / Site engineer | Photograph environmental protection measures installed | Type - I | Reference or Specification - ESMP | Method/Test Required - Record temporary measures | How Often? - Each site | Records Required - Photograph | Responsibility - Site Supervisor / Site engineer | Reference or Specification - Preseal inspection checksheet
Milling undertaken to correct depth up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report | I | site design Report; NZTA M10: 2020 10.1 | Dip checks | Per site | Stringline sheet from QA pack | Site Supervisor / Site QA/site engineer | Milling undertaken to correct depth up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report | Type - I | Reference or Specification - site design Report; NZTA M10: 2020 10.1 | Method/Test Required - Dip checks | How Often? - Per site | Records Required - Stringline sheet from QA pack | Responsibility - Site Supervisor / Site QA/site engineer | Method/Test Required - Confirm document uploaded
Proofrolling to be done on milled surface Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost. | T/I | Site design report | Proofrolling with PTR or loaded truck | Per site | Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager | Site supervisor/Site engineer | Proofrolling to be done on milled surface Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost. | Type - T/I | Reference or Specification - Site design report | Method/Test Required - Proofrolling with PTR or loaded truck | How Often? - Per site | Records Required - Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager | Responsibility - Site supervisor/Site engineer | How Often? - Each site prior to establishment
Application as per Design Requirements (Chip size / binder application rate) | I | Design Report | Spray Sheet's | Per site | Spraysheets | Site Supervisor / Site Engineer | Application as per Design Requirements (Chip size / binder application rate) | Type - I | Reference or Specification - Design Report | Method/Test Required - Spray Sheet's | How Often? - Per site | Records Required - Spraysheets | Responsibility - Site Supervisor / Site Engineer | Records Required - Copy of pre seal inspection
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC20 PMB 130°C AC20 Hi-Mod 140°C AC20 60/70 125°C | T | NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Temperature Gun Check Acceptable / Unacceptable | Per load | Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Site Supervisor/QA | Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC20 PMB 130°C AC20 Hi-Mod 140°C AC20 60/70 125°C | Type - T | Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Method/Test Required - Temperature Gun Check Acceptable / Unacceptable | How Often? - Per load | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Responsibility - Site Supervisor/QA | Responsibility - Site engineer/Supervisor
Structural Asphalt Layer Thickness Each Layer >80mm with a max discrepency of +10mm nominal thickness | T | NZTA M10 2020 10.1 CHAR(AMP) Table 3.1 | Dip checks and spreadrates | each truckload | Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Site Supervisor / Site QA /Site engineer | Structural Asphalt Layer Thickness Each Layer >80mm with a max discrepency of +10mm nominal thickness | Type - T | Reference or Specification - NZTA M10 2020 10.1 CHAR(AMP) Table 3.1 | Method/Test Required - Dip checks and spreadrates | How Often? - each truckload | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Responsibility - Site Supervisor / Site QA /Site engineer | Stakeholder Management Requirements met
Compaction and Air Voids | T | QMP and NDM SOP | NDM for Quality Control | Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | NDM sheet in QA pack | Site Supervisor / Site QA / Site Engineer | Compaction and Air Voids | Type - T | Reference or Specification - QMP and NDM SOP | Method/Test Required - NDM for Quality Control | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | Records Required - NDM sheet in QA pack | Responsibility - Site Supervisor / Site QA / Site Engineer | Type - H
Proven layer thickness and compaction | T | NZTA M10: 2020 9.9 | 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Site Supervisor / Site QA/ Site engineer | Proven layer thickness and compaction | Type - T | Reference or Specification - NZTA M10: 2020 9.9 | Method/Test Required - 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Responsibility - Site Supervisor / Site QA/ Site engineer | Reference or Specification - CSCMP
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC PMB 130°C AC 60/70 125°C SMA PMB 125°C SMA 60/70 120°C | T | NZTA M10: 2020Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Temperature Gun Check Acceptable / Unacceptable | Per load | Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Site Supervisor/ QA/Site engineer | Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC PMB 130°C AC 60/70 125°C SMA PMB 125°C SMA 60/70 120°C | Type - T | Reference or Specification - NZTA M10: 2020Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Method/Test Required - Temperature Gun Check Acceptable / Unacceptable | How Often? - Per load | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp | Responsibility - Site Supervisor/ QA/Site engineer | Method/Test Required - Confirm requirements followed
Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report | T | NZTA M10:2020 10.1 CHAR(AMP) NZTA M10:2020 Notes Table 3.3 CHAR(AMP) 3.4 NZTA M27:2020 10.2 CHAR(AMP) NZTA M27:2020 Notes Table 3.1 | Dip checks and spreadrates | each truckload | Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Site Supervisor / Site QA /Site engineer | Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report | Type - T | Reference or Specification - NZTA M10:2020 10.1 CHAR(AMP) NZTA M10:2020 Notes Table 3.3 CHAR(AMP) 3.4 NZTA M27:2020 10.2 CHAR(AMP) NZTA M27:2020 Notes Table 3.1 | Method/Test Required - Dip checks and spreadrates | How Often? - each truckload | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks | Responsibility - Site Supervisor / Site QA /Site engineer | How Often? - Each site
Compaction and Air Voids | T | QMP and NDM SOP | NDM for Quality Control | Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | NDM sheet in QA pack | Site Supervisor / Site QA / Site Engineer | Compaction and Air Voids | Type - T | Reference or Specification - QMP and NDM SOP | Method/Test Required - NDM for Quality Control | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints | Records Required - NDM sheet in QA pack | Responsibility - Site Supervisor / Site QA / Site Engineer | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
Proven layer thickness and compaction | T | NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9 | 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report. A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Site Supervisor / Site QA/ Site engineer | Proven layer thickness and compaction | Type - T | Reference or Specification - NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9 | Method/Test Required - 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report. A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF | Responsibility - Site Supervisor / Site QA/ Site engineer | Responsibility - Network manager/Renewals manager/Project engineer
Supervisor to provide an update regarding site completion per shift |  | QMP | email | Per site | Email | Site Supervisor/site engineer | Supervisor to provide an update regarding site completion per shift | Type - | Reference or Specification - QMP | Method/Test Required - email | How Often? - Per site | Records Required - Email | Responsibility - Site Supervisor/site engineer | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used
Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing | H | MOTSAM | Visual check | Per site | Job Sheet record CHAR(AMP) photograph | Site Engineer | Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing | Type - H | Reference or Specification - MOTSAM | Method/Test Required - Visual check | How Often? - Per site | Records Required - Job Sheet record CHAR(AMP) photograph | Responsibility - Site Engineer | Type - H
Post seal inspection completed: - Driveability of site acceptable - Quality of paved surface - Linemarking correctly reinstated, including cat's eyes? - All TTM signs removed - Site; stockpile and parking area left in tidy condition - Required service cover adjustments completed; covers to be flush to +10mm with surface - Environmental protection removed | I | Post seal inspection checksheet | Confirm document uploaded | Each site within 1 week of completion | Copy of post seal inspection | Site engineer/Supervisor | Post seal inspection completed: - Driveability of site acceptable - Quality of paved surface - Linemarking correctly reinstated, including cat's eyes? - All TTM signs removed - Site; stockpile and parking area left in tidy condition - Required service cover adjustments completed; covers to be flush to +10mm with surface - Environmental protection removed | Type - I | Reference or Specification - Post seal inspection checksheet | Method/Test Required - Confirm document uploaded | How Often? - Each site within 1 week of completion | Records Required - Copy of post seal inspection | Responsibility - Site engineer/Supervisor | Reference or Specification - QMP
As-Built records – structural patches | H | Site design report | Record as-built patch dimensions CHAR(AMP) RPs | Per site | Final site diagram from QA pack | Site engineer/QA | As-Built records – structural patches | Type - H | Reference or Specification - Site design report | Method/Test Required - Record as-built patch dimensions CHAR(AMP) RPs | How Often? - Per site | Records Required - Final site diagram from QA pack | Responsibility - Site engineer/QA | Method/Test Required - Brief all team members on day’s work plan
Collect RAMM data | H | Comply with Waka Kotahi format | Correct data supplied | Per site | Job Sheet record + As-Builts + photographs | Renewals manager/Project Engineer | Collect RAMM data | Type - H | Reference or Specification - Comply with Waka Kotahi format | Method/Test Required - Correct data supplied | How Often? - Per site | Records Required - Job Sheet record + As-Builts + photographs | Responsibility - Renewals manager/Project Engineer | How Often? - Each shift
Records Required - Job brief, updated forward works program and screenshot of weather forecast
Responsibility - Site engineer/supervisor
Confirm Traffic management requirements met
Type - H
Reference or Specification - CoPTTM/NZGTTM
Method/Test Required - Confirm Approved TMP in place
How Often? - Each site
Records Required - TMP
Responsibility - Project Engineer/Site engineer
Ambient Conditions Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above
Type - H
Reference or Specification - NZTA M10: 2020 9.5.2
Method/Test Required - Temperature Gun Check Acceptable / Unacceptable
How Often? - Each site
Records Required - Ground temp record sheet in QA pack
Responsibility - QA/Supervisor
Job start, identify risks and controls, communicated to team
Type - H
Reference or Specification - HSMP
Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
How Often? - Each site
Records Required - Daily pre start briefing Form D02.05
Responsibility - Site Supervisor/Foreman
Establish traffic management to plan
Type - H
Reference or Specification - TMP
Method/Test Required - Site audit post set up
How Often? - Each site
Records Required - on site record
Responsibility - STMS/Site engineer
Identification of Services Service Plans on-site Shallow Services marked
Type - H
Reference or Specification - JSEA/Permit to dig
Method/Test Required - Confirm document on-site / Visual check
How Often? - Each site
Records Required - Permit to dig/ service plans
Responsibility - Site Supervisor/Site engineer
Photograph environmental protection measures installed
Type - I
Reference or Specification - ESMP
Method/Test Required - Record temporary measures
How Often? - Each site
Records Required - Photograph
Responsibility - Site Supervisor / Site engineer
Milling undertaken to correct depth up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report
Type - I
Reference or Specification - site design Report; NZTA M10: 2020 10.1
Method/Test Required - Dip checks
How Often? - Per site
Records Required - Stringline sheet from QA pack
Responsibility - Site Supervisor / Site QA/site engineer
Proofrolling to be done on milled surface Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost.
Type - T/I
Reference or Specification - Site design report
Method/Test Required - Proofrolling with PTR or loaded truck
How Often? - Per site
Records Required - Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager
Responsibility - Site supervisor/Site engineer
Application as per Design Requirements (Chip size / binder application rate)
Type - I
Reference or Specification - Design Report
Method/Test Required - Spray Sheet's
How Often? - Per site
Records Required - Spraysheets
Responsibility - Site Supervisor / Site Engineer
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC20 PMB 130°C AC20 Hi-Mod 140°C AC20 60/70 125°C
Type - T
Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
Method/Test Required - Temperature Gun Check Acceptable / Unacceptable
How Often? - Per load
Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
Responsibility - Site Supervisor/QA
Structural Asphalt Layer Thickness Each Layer >80mm with a max discrepency of +10mm nominal thickness
Type - T
Reference or Specification - NZTA M10 2020 10.1 CHAR(AMP) Table 3.1
Method/Test Required - Dip checks and spreadrates
How Often? - each truckload
Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
Responsibility - Site Supervisor / Site QA /Site engineer
Compaction and Air Voids
Type - T
Reference or Specification - QMP and NDM SOP
Method/Test Required - NDM for Quality Control
How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
Records Required - NDM sheet in QA pack
Responsibility - Site Supervisor / Site QA / Site Engineer
Proven layer thickness and compaction
Type - T
Reference or Specification - NZTA M10: 2020 9.9
Method/Test Required - 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.)
How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.)
Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
Responsibility - Site Supervisor / Site QA/ Site engineer
Delivery and compaction temperature ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC PMB 130°C AC 60/70 125°C SMA PMB 125°C SMA 60/70 120°C
Type - T
Reference or Specification - NZTA M10: 2020Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
Method/Test Required - Temperature Gun Check Acceptable / Unacceptable
How Often? - Per load
Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
Responsibility - Site Supervisor/ QA/Site engineer
Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
Type - T
Reference or Specification - NZTA M10:2020 10.1 CHAR(AMP) NZTA M10:2020 Notes Table 3.3 CHAR(AMP) 3.4 NZTA M27:2020 10.2 CHAR(AMP) NZTA M27:2020 Notes Table 3.1
Method/Test Required - Dip checks and spreadrates
How Often? - each truckload
Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
Responsibility - Site Supervisor / Site QA /Site engineer
Compaction and Air Voids
Type - T
Reference or Specification - QMP and NDM SOP
Method/Test Required - NDM for Quality Control
How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
Records Required - NDM sheet in QA pack
Responsibility - Site Supervisor / Site QA / Site Engineer
Proven layer thickness and compaction
Type - T
Reference or Specification - NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9
Method/Test Required - 150mm Diameter Cores where: 1. >30tonnes 2. >=45mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and CHAR(LESS)45mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.)
How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.)
Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report. A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
Responsibility - Site Supervisor / Site QA/ Site engineer
Supervisor to provide an update regarding site completion per shift
Type -
Reference or Specification - QMP
Method/Test Required - email
How Often? - Per site
Records Required - Email
Responsibility - Site Supervisor/site engineer
Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing
Type - H
Reference or Specification - MOTSAM
Method/Test Required - Visual check
How Often? - Per site
Records Required - Job Sheet record CHAR(AMP) photograph
Responsibility - Site Engineer
Post seal inspection completed: - Driveability of site acceptable - Quality of paved surface - Linemarking correctly reinstated, including cat's eyes? - All TTM signs removed - Site; stockpile and parking area left in tidy condition - Required service cover adjustments completed; covers to be flush to +10mm with surface - Environmental protection removed
Type - I
Reference or Specification - Post seal inspection checksheet
Method/Test Required - Confirm document uploaded
How Often? - Each site within 1 week of completion
Records Required - Copy of post seal inspection
Responsibility - Site engineer/Supervisor
As-Built records – structural patches
Type - H
Reference or Specification - Site design report
Method/Test Required - Record as-built patch dimensions CHAR(AMP) RPs
How Often? - Per site
Records Required - Final site diagram from QA pack
Responsibility - Site engineer/QA
Collect RAMM data
Type - H
Reference or Specification - Comply with Waka Kotahi format
Method/Test Required - Correct data supplied
How Often? - Per site
Records Required - Job Sheet record + As-Builts + photographs
Responsibility - Renewals manager/Project Engineer