## Sheet1
Area to be cleared Depth of grubbing Removal of topsoil | - Refer to construction drawings - Approved method statement | Survey equipment Tools to measure depth | Entire site | Contractor | Setting out plan Survey plan | Area to be cleared Depth of grubbing Removal of topsoil | STANDARD/REQUIREMENT - - Refer to construction drawings - Approved method statement | TOOLS/EQUIPMENT - Survey equipment Tools to measure depth | STAGE/FREQUENCY - Entire site | RESPONSIBILITY - Contractor | EVIDENCE - Setting out plan Survey plan | Area to be cleared Depth of grubbing Removal of topsoil
Dimensional tolerance (depth) | Width CHAR(LESS) 300mm than the dimensions shown on the drawings | Tools to measure depth | When required | Contractor/ Project Manager | Survey plan | Dimensional tolerance (depth) | STANDARD/REQUIREMENT - Width CHAR(LESS) 300mm than the dimensions shown on the drawings | TOOLS/EQUIPMENT - Tools to measure depth | STAGE/FREQUENCY - When required | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Survey plan | STANDARD/REQUIREMENT - - Refer to construction drawings - Approved method statement
Unsuitable material (If any) | JKR/SPJ/2013-S2: Clause 2.2.1 (d) or JKR 20800-0183-14 Section B Cl. 5.2.3 | Trial pit | When required | Contractor/ Project Manager | Material laboratory test | Unsuitable material (If any) | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (d) or JKR 20800-0183-14 Section B Cl. 5.2.3 | TOOLS/EQUIPMENT - Trial pit | STAGE/FREQUENCY - When required | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | TOOLS/EQUIPMENT - Survey equipment Tools to measure depth
Grading of replacement materials | JKR/SPJ/2013-S2: Table 2.1 or JKR 20800-0183-14 Section B Cl. 5.7, Table B1 | Particle Size Distribution (Gradation analysis) | When required | Contractor/ Project Manager | Material laboratory test | Grading of replacement materials | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Table 2.1 or JKR 20800-0183-14 Section B Cl. 5.7, Table B1 | TOOLS/EQUIPMENT - Particle Size Distribution (Gradation analysis) | STAGE/FREQUENCY - When required | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | STAGE/FREQUENCY - Entire site
Excavation of hard materials/ rock | JKR/SPJ/2013-S2: Clause 2.2.1 (f) and (g) or JKR 20800-0183-14 Section B Cl. 5.2.5, | Trial excavation | When required | Contractor/ Project Manager | Trial excavation record | Excavation of hard materials/ rock | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (f) and (g) or JKR 20800-0183-14 Section B Cl. 5.2.5, | TOOLS/EQUIPMENT - Trial excavation | STAGE/FREQUENCY - When required | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Trial excavation record | RESPONSIBILITY - Contractor
Rock blasting | JKR/SPJ/2013-S2: Clause 2.2.3.8 or JKR 20800-0183-14 Section B Cl. 5.1.2 | Trial blasting | When required | Contractor/ Project Manager | Trial blasting record | Rock blasting | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.3.8 or JKR 20800-0183-14 Section B Cl. 5.1.2 | TOOLS/EQUIPMENT - Trial blasting | STAGE/FREQUENCY - When required | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Trial blasting record | EVIDENCE - Setting out plan Survey plan
Suitability of materials (1) | JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | Atterberg limit test | One test/ 1500 m3 of the material to be used | Contractor/ Project Manager | Material laboratory test | Suitability of materials (1) | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | TOOLS/EQUIPMENT - Atterberg limit test | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | Dimensional tolerance (depth)
Suitability of materials (2) | JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | Gradation analysis | One test/ 1500 m3 of the material to be used | Contractor/ Project Manager | Material laboratory test | Suitability of materials (2) | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | TOOLS/EQUIPMENT - Gradation analysis | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | STANDARD/REQUIREMENT - Width CHAR(LESS) 300mm than the dimensions shown on the drawings
Suitability of materials (3) | JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | Compaction test (MS 1056) | One test/ 1500 m3 of the material to be used | Contractor/ Project Manager | Material laboratory test | Suitability of materials (3) | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | TOOLS/EQUIPMENT - Compaction test (MS 1056) | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | TOOLS/EQUIPMENT - Tools to measure depth
Suitability of materials (4) | JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | Soaked CBR test | One test/ 1500 m3 of the material to be used | Contractor/ Project Manager | Material laboratory test | Suitability of materials (4) | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 | TOOLS/EQUIPMENT - Soaked CBR test | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | STAGE/FREQUENCY - When required
Suitability of materials (5) | Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 CHAR(AMP) ICAO A. Manual Part | Plate Bearing Test |  | Contractor/ Project Manager | Material laboratory test | Suitability of materials (5) | STANDARD/REQUIREMENT - Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 CHAR(AMP) ICAO A. Manual Part | TOOLS/EQUIPMENT - Plate Bearing Test | STAGE/FREQUENCY - | RESPONSIBILITY - Contractor/ Project Manager | EVIDENCE - Material laboratory test | RESPONSIBILITY - Contractor/ Project Manager
Area to be cut and trim | Refer to construction drawing | Survey equipment Measuring tape | Before slope cutting | Surveyor / Contractor | Setting out plan Surveyor peg point | Area to be cut and trim | STANDARD/REQUIREMENT - Refer to construction drawing | TOOLS/EQUIPMENT - Survey equipment Measuring tape | STAGE/FREQUENCY - Before slope cutting | RESPONSIBILITY - Surveyor / Contractor | EVIDENCE - Setting out plan Surveyor peg point | EVIDENCE - Survey plan
Safety Precaution | JKR specification for occupational safety CHAR(AMP) Health in engineering construction | Visual checking | Before slope cutting | Contractor |  | Safety Precaution | STANDARD/REQUIREMENT - JKR specification for occupational safety CHAR(AMP) Health in engineering construction | TOOLS/EQUIPMENT - Visual checking | STAGE/FREQUENCY - Before slope cutting | RESPONSIBILITY - Contractor | EVIDENCE - | Unsuitable material (If any)
Excavation - Dimension - Level - Line - Profile | Refer to construction drawing | Survey equipment Measuring devices | Once slope cutting completed | Contrator / Surveyor Consultant | Request for Inspection Form | Excavation - Dimension - Level - Line - Profile | STANDARD/REQUIREMENT - Refer to construction drawing | TOOLS/EQUIPMENT - Survey equipment Measuring devices | STAGE/FREQUENCY - Once slope cutting completed | RESPONSIBILITY - Contrator / Surveyor Consultant | EVIDENCE - Request for Inspection Form | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (d) or JKR 20800-0183-14 Section B Cl. 5.2.3
Compaction | Refer to construction drawing Visual inspection | Excavator | Once after work completed | Contractor / Consultant | Request for Inspection Form Compaction record | Compaction | STANDARD/REQUIREMENT - Refer to construction drawing Visual inspection | TOOLS/EQUIPMENT - Excavator | STAGE/FREQUENCY - Once after work completed | RESPONSIBILITY - Contractor / Consultant | EVIDENCE - Request for Inspection Form Compaction record | TOOLS/EQUIPMENT - Trial pit
Drainage route Drain excavation and Slope alignment | Refer to construction drawing Refer to construction drawing | survey equipment Measuring tape | Before start work | Surveyor / Contractor | Setting our plan | Drainage route Drain excavation and Slope alignment | STANDARD/REQUIREMENT - Refer to construction drawing Refer to construction drawing | TOOLS/EQUIPMENT - survey equipment Measuring tape | STAGE/FREQUENCY - Before start work | RESPONSIBILITY - Surveyor / Contractor | EVIDENCE - Setting our plan | STAGE/FREQUENCY - When required
Drain invet level | Refer to construction drawing Site Layout plan | Survey equipment Level measuring devices |  |  | Request for Inspection Form | Drain invet level | STANDARD/REQUIREMENT - Refer to construction drawing Site Layout plan | TOOLS/EQUIPMENT - Survey equipment Level measuring devices | STAGE/FREQUENCY - | RESPONSIBILITY - | EVIDENCE - Request for Inspection Form | RESPONSIBILITY - Contractor/ Project Manager
Belian pile | Refer to construction drawing | Excavator Measuring tape | once during piling work | Contractor Consultant | Pile Material inspection form Request for Inspection Form for piling work | Belian pile | STANDARD/REQUIREMENT - Refer to construction drawing | TOOLS/EQUIPMENT - Excavator Measuring tape | STAGE/FREQUENCY - once during piling work | RESPONSIBILITY - Contractor Consultant | EVIDENCE - Pile Material inspection form Request for Inspection Form for piling work | EVIDENCE - Material laboratory test
Cutting and bending of steel reinforcement | Refer to construction drawing BS4449 |  | Before fixing concreting | Contractor |  | Cutting and bending of steel reinforcement | STANDARD/REQUIREMENT - Refer to construction drawing BS4449 | TOOLS/EQUIPMENT - | STAGE/FREQUENCY - Before fixing concreting | RESPONSIBILITY - Contractor | EVIDENCE - | Grading of replacement materials
Fixing of steel reinforcement to formwork | Refer to construction drawing Comply design concrete cover Comply design drain width and depth | Measuring tape |  | Contractor / Consultant | Request for Inspection Form | Fixing of steel reinforcement to formwork | STANDARD/REQUIREMENT - Refer to construction drawing Comply design concrete cover Comply design drain width and depth | TOOLS/EQUIPMENT - Measuring tape | STAGE/FREQUENCY - | RESPONSIBILITY - Contractor / Consultant | EVIDENCE - Request for Inspection Form | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Table 2.1 or JKR 20800-0183-14 Section B Cl. 5.7, Table B1
Preparation of site Compaction | Refer to construction drawing MS1056 SO approval | Compaction and CBR test equipment | once upon work done |  | Request for inspection form | Preparation of site Compaction | STANDARD/REQUIREMENT - Refer to construction drawing MS1056 SO approval | TOOLS/EQUIPMENT - Compaction and CBR test equipment | STAGE/FREQUENCY - once upon work done | RESPONSIBILITY - | EVIDENCE - Request for inspection form | TOOLS/EQUIPMENT - Particle Size Distribution (Gradation analysis)
Placement of Gabions Material | BS1052:1980 JKR/SPJ/1988 sub-Section 3.6.2.1 |  |  | Contractor / Consultant | Material inspection form | Placement of Gabions Material | STANDARD/REQUIREMENT - BS1052:1980 JKR/SPJ/1988 sub-Section 3.6.2.1 | TOOLS/EQUIPMENT - | STAGE/FREQUENCY - | RESPONSIBILITY - Contractor / Consultant | EVIDENCE - Material inspection form | STAGE/FREQUENCY - When required
Installation of Gabion Stone | refer to construction drawing refer to construction drawing |  |  | Contractor / Consultant Consultant | Request for inspection form | Installation of Gabion Stone | STANDARD/REQUIREMENT - refer to construction drawing refer to construction drawing | TOOLS/EQUIPMENT - | STAGE/FREQUENCY - | RESPONSIBILITY - Contractor / Consultant Consultant | EVIDENCE - Request for inspection form | RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Excavation of hard materials/ rock
STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (f) and (g) or JKR 20800-0183-14 Section B Cl. 5.2.5,
TOOLS/EQUIPMENT - Trial excavation
STAGE/FREQUENCY - When required
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Trial excavation record
Rock blasting
STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.3.8 or JKR 20800-0183-14 Section B Cl. 5.1.2
TOOLS/EQUIPMENT - Trial blasting
STAGE/FREQUENCY - When required
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Trial blasting record
Suitability of materials (1)
STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
TOOLS/EQUIPMENT - Atterberg limit test
STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Suitability of materials (2)
STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
TOOLS/EQUIPMENT - Gradation analysis
STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Suitability of materials (3)
STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
TOOLS/EQUIPMENT - Compaction test (MS 1056)
STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Suitability of materials (4)
STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
TOOLS/EQUIPMENT - Soaked CBR test
STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Suitability of materials (5)
STANDARD/REQUIREMENT - Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 CHAR(AMP) ICAO A. Manual Part
TOOLS/EQUIPMENT - Plate Bearing Test
STAGE/FREQUENCY -
RESPONSIBILITY - Contractor/ Project Manager
EVIDENCE - Material laboratory test
Area to be cut and trim
STANDARD/REQUIREMENT - Refer to construction drawing
TOOLS/EQUIPMENT - Survey equipment Measuring tape
STAGE/FREQUENCY - Before slope cutting
RESPONSIBILITY - Surveyor / Contractor
EVIDENCE - Setting out plan Surveyor peg point
Safety Precaution
STANDARD/REQUIREMENT - JKR specification for occupational safety CHAR(AMP) Health in engineering construction
TOOLS/EQUIPMENT - Visual checking
STAGE/FREQUENCY - Before slope cutting
RESPONSIBILITY - Contractor
EVIDENCE -
Excavation - Dimension - Level - Line - Profile
STANDARD/REQUIREMENT - Refer to construction drawing
TOOLS/EQUIPMENT - Survey equipment Measuring devices
STAGE/FREQUENCY - Once slope cutting completed
RESPONSIBILITY - Contrator / Surveyor Consultant
EVIDENCE - Request for Inspection Form
Compaction
STANDARD/REQUIREMENT - Refer to construction drawing Visual inspection
TOOLS/EQUIPMENT - Excavator
STAGE/FREQUENCY - Once after work completed
RESPONSIBILITY - Contractor / Consultant
EVIDENCE - Request for Inspection Form Compaction record
Drainage route Drain excavation and Slope alignment
STANDARD/REQUIREMENT - Refer to construction drawing Refer to construction drawing
TOOLS/EQUIPMENT - survey equipment Measuring tape
STAGE/FREQUENCY - Before start work
RESPONSIBILITY - Surveyor / Contractor
EVIDENCE - Setting our plan
Drain invet level
STANDARD/REQUIREMENT - Refer to construction drawing Site Layout plan
TOOLS/EQUIPMENT - Survey equipment Level measuring devices
STAGE/FREQUENCY -
RESPONSIBILITY -
EVIDENCE - Request for Inspection Form
Belian pile
STANDARD/REQUIREMENT - Refer to construction drawing
TOOLS/EQUIPMENT - Excavator Measuring tape
STAGE/FREQUENCY - once during piling work
RESPONSIBILITY - Contractor Consultant
EVIDENCE - Pile Material inspection form Request for Inspection Form for piling work
Cutting and bending of steel reinforcement
STANDARD/REQUIREMENT - Refer to construction drawing BS4449
TOOLS/EQUIPMENT -
STAGE/FREQUENCY - Before fixing concreting
RESPONSIBILITY - Contractor
EVIDENCE -
Fixing of steel reinforcement to formwork
STANDARD/REQUIREMENT - Refer to construction drawing Comply design concrete cover Comply design drain width and depth
TOOLS/EQUIPMENT - Measuring tape
STAGE/FREQUENCY -
RESPONSIBILITY - Contractor / Consultant
EVIDENCE - Request for Inspection Form
Preparation of site Compaction
STANDARD/REQUIREMENT - Refer to construction drawing MS1056 SO approval
TOOLS/EQUIPMENT - Compaction and CBR test equipment
STAGE/FREQUENCY - once upon work done
RESPONSIBILITY -
EVIDENCE - Request for inspection form
Placement of Gabions Material
STANDARD/REQUIREMENT - BS1052:1980 JKR/SPJ/1988 sub-Section 3.6.2.1
TOOLS/EQUIPMENT -
STAGE/FREQUENCY -
RESPONSIBILITY - Contractor / Consultant
EVIDENCE - Material inspection form
Installation of Gabion Stone
STANDARD/REQUIREMENT - refer to construction drawing refer to construction drawing
TOOLS/EQUIPMENT -
STAGE/FREQUENCY -
RESPONSIBILITY - Contractor / Consultant Consultant
EVIDENCE - Request for inspection form