## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Earthworks | itp |  |  |  |  | Appendix A1 - Earthworks ITP
section | 1 - Site clearing
checkpoint | Area to be cleared Depth of grubbing, Removal of topsoil
label | STANDARD/REQUIREMENT - Refer to construction drawings
label | ○ Approved method statement
label | TOOLS/EQUIPMENT - Survey equipment Tools to measure depth
label | STAGE/FREQUENCY - Entire site
label | RESPONSIBILITY - Contractor
label | EVIDENCE - Setting out plan Survey plan
section | 2 - Excavation
checkpoint | Dimensional tolerance (depth)
label | STANDARD/REQUIREMENT - Width < 300mm than the dimensions shown on the drawings
label | TOOLS/EQUIPMENT - Tools to measure depth
label | STAGE/FREQUENCY - When required
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Survey plan
checkpoint | Unsuitable material (If any)
label | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (d) or JKR 20800-0183-14 Section B Cl. 5.2.3
label | TOOLS/EQUIPMENT - Trial pit
label | STAGE/FREQUENCY - When required
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Grading of replacement materials
label | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Table 2.1 or JKR 20800-0183-14 Section B Cl. 5.7, Table B1
label | TOOLS/EQUIPMENT - Particle Size Distribution (Gradation analysis)
label | STAGE/FREQUENCY - When required
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Excavation of hard materials/ rock
label | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.1 (f) and (g) or JKR 20800-0183-14 Section B Cl. 5.2.5,
label | TOOLS/EQUIPMENT - Trial excavation
label | STAGE/FREQUENCY - When required
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Trial excavation record
checkpoint | Rock blasting
label | STANDARD/REQUIREMENT - JKR/SPJ/2013-S2: Clause 2.2.3.8 or JKR 20800-0183-14 Section B Cl. 5.1.2
label | TOOLS/EQUIPMENT - Trial blasting
label | STAGE/FREQUENCY - When required
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Trial blasting record
section | 3 - Fill materials
checkpoint | Suitability of materials (1)
label | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
label | TOOLS/EQUIPMENT - Atterberg limit test
label | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Suitability of materials (2)
label | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
label | TOOLS/EQUIPMENT - Gradation analysis
label | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Suitability of materials (3)
label | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
label | TOOLS/EQUIPMENT - Compaction test (MS 1056)
label | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Suitability of materials (4)
label | STANDARD/REQUIREMENT - JKR/SPJ/2013 - Cl. 2.2.4.1 and 2.2.4.2 or JKR 20800-0183-14 Section B Cl. 5.2.4 or Federal Aviation Administration (FAA) AC 150/5320-6E CI 205
label | TOOLS/EQUIPMENT - Soaked CBR test
label | STAGE/FREQUENCY - One test/ 1500 m3 of the material to be used
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
checkpoint | Suitability of materials (5)
label | STANDARD/REQUIREMENT - Federal Aviation Administration (FAA) AC 150/5320-6E CI 205 & ICAO A. Manual Part
label | TOOLS/EQUIPMENT - Plate Bearing Test
label | RESPONSIBILITY - Contractor/ Project Manager
label | EVIDENCE - Material laboratory test
section | 4 - Slope Cutting
checkpoint | Area to be cut and trim
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - Survey equipment, Measuring tape
label | STAGE/FREQUENCY - Before slope cutting
label | RESPONSIBILITY - Surveyor / Contractor
label | EVIDENCE - Setting out plan, Surveyor peg point
checkpoint | Safety Precaution
label | STANDARD/REQUIREMENT - JKR specification for occupational safety & Health in engineering construction
label | TOOLS/EQUIPMENT - Visual checking
label | STAGE/FREQUENCY - Before slope cutting
label | RESPONSIBILITY - Contractor
checkpoint | Excavation
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - Survey equipment
label | STAGE/FREQUENCY - Once slope cutting completed
label | RESPONSIBILITY - Contrator / Surveyor
label | EVIDENCE - Request for Inspection Form
label | REMARKS - Ensure nobody or property at the downstream of slope cutting
checkpoint | Dimension / Level / Line / Profile
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - Measuring devices
label | STAGE/FREQUENCY - Once slope cutting completed
label | RESPONSIBILITY - Consultant
label | EVIDENCE - Request for Inspection Form
checkpoint | Compaction
label | STANDARD/REQUIREMENT - Refer to construction drawing, Visual inspection
label | TOOLS/EQUIPMENT - Excavator
label | STAGE/FREQUENCY - Once after work completed
label | RESPONSIBILITY - Contractor / Consultant
label | EVIDENCE - Request for Inspection Form Compaction record
section | 5 - Drainage
checkpoint | Drainage route
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - survey equipment Measuring tape
label | STAGE/FREQUENCY - Before start work
label | RESPONSIBILITY - Surveyor / Contractor
label | EVIDENCE - Setting our plan
checkpoint | Drain excavation and Slope alignment
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - survey equipment Measuring tape
label | STAGE/FREQUENCY - Before start work
label | RESPONSIBILITY - Surveyor / Contractor
label | EVIDENCE - Setting our plan
checkpoint | Drain invet level
label | STANDARD/REQUIREMENT - Refer to construction drawing, Site Layout plan
label | TOOLS/EQUIPMENT - Survey equipment, Level measuring devices
label | EVIDENCE - Request for Inspection Form
checkpoint | Belian pile
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | TOOLS/EQUIPMENT - Excavator Measuring tape
label | STAGE/FREQUENCY - once during piling work
label | RESPONSIBILITY - Contractor Consultant
label | EVIDENCE - Pile Material inspection form Request for Inspection Form for piling work
checkpoint | Cutting and bending of steel reinforcement
label | STANDARD/REQUIREMENT - Refer to construction drawing BS4449
label | STAGE/FREQUENCY - Before fixing concreting
label | RESPONSIBILITY - Contractor
checkpoint | Fixing of steel reinforcement to formwork
label | STANDARD/REQUIREMENT - Refer to construction drawing
label | ○ Comply design concrete cover Comply design drain width and depth
label | TOOLS/EQUIPMENT - Measuring tape
label | RESPONSIBILITY - Contractor / Consultant
label | EVIDENCE - Request for Inspection Form
section | 6 - Slope Protection
checkpoint | Preparation of site Compaction
label | STANDARD/REQUIREMENT - Refer to construction drawing MS1056
label | ○ SO approval
label | TOOLS/EQUIPMENT - Compaction and CBR test equipment
label | STAGE/FREQUENCY - once upon work done
label | EVIDENCE - Request for inspection form
checkpoint | Placement of Gabions Material
label | STANDARD/REQUIREMENT - BS1052:1980
label | ○ JKR/SPJ/1988 sub-Section 3.6.2.1
label | RESPONSIBILITY - Contractor / Consultant
label | EVIDENCE - Material inspection form
checkpoint | Installation of Gabion
label | STANDARD/REQUIREMENT - refer to construction drawing
label | RESPONSIBILITY - Contractor / Consultant
label | EVIDENCE - Request for inspection form
checkpoint | Stone
label | STANDARD/REQUIREMENT - refer to construction drawing
label | RESPONSIBILITY - Consultant
label | EVIDENCE - Request for inspection form
checklist | TOP ENTRY MIXER TEST FORM | [5 empty] | TOP ENTRY MIXER TEST FORM
section | 1. Equipment Details
checkpoint | MIXER
label | Manufacturer: MIXTEC
textbox | Model
textbox | SerialL No.
textbox | Tank turnover
textbox | Superficial velocity
checkpoint | MOTOR
textbox | Manufacturer:
textbox | Serial No.
textbox | Voltage/ Ph/ V
textbox | Power |  |  | kW
textbox | Current |  |  | Amp
textbox | Speed
section | 2. Visual Inspection
checkpoint | a) Mixer Frame mounting check
checkpoint | b) Mixer shaft alignment check
checkpoint | c) Rotation check
checkpoint | d) Cable entry & termination
checkpoint | e) Emergency stop
checkpoint | f) Local Start/Stop
checkpoint | g) Operation protection
checkpoint | h) Motor installed with shed? ( if applicable)
section | 3. Cable Insulation Test
checkpoint | Power Cable
textbox | R-Y
textbox | R-B
textbox | Y-B
textbox | R-E
textbox | Y-E
textbox | B-E
section | 4. Operational Test
checkpoint | Mixer Stator Method:
textbox | Variable Speed Drive
textbox | DOL
textbox | AT
checkpoint | a) Manual operation test
checkpoint | b) Auto operation test
checkpoint | c) Remote operation test
checkpoint | d) Emergency stop functionality test
checkpoint | e) Low Water Level Start Prohibited Test
checkpoint | f) Local Start/Stop
checkpoint | g) Motor installed with Shed? (if applicable)
section | 5. Operation Data
checkpoint | Voltage (Vac)
textbox | R-Y
textbox | R-B
textbox | Y-B
checkpoint | Current (Amp)
textbox | R
textbox | Y
textbox | B
checkpoint-no-status | Regulated Speed (rpm/Hz)
textbox | rpm/Hz:
section | Final Inspection
checkpoint | Final Inspection
label | Prepared By: Contractor Representative
textbox | Contractor - Name:
date | Contractor - Date:
label | Witnessed By: Consultant Representative
textbox | Consultant - Name:
date | Consultant - Date:
label | Witnessed By: Client Representative
textbox | Client - Name:
date | Client - Date:
holdpoint | Add Signature