## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
346e49e8-47bc-4749-a343-58c3eff9d7ff | checklist | Concrete Pour Record |  | Concrete Pour Record
decc4ae7-db80-4b2e-9c80-491b697b9bd9 | section | Preliminaries
6e950b39-a789-4a0b-ba42-dc989a63186c | checkpoint | Survey (1)
a114b964-e012-58fb-8340-55a850003857 | note | ACCEPTANCE CRITERIA: Sufficient survey set out information is available.
474cdf33-f47e-52b0-84e6-29403e6bd4d3 | date | Date Completed:
82f9ca9a-9501-4382-b55b-810793d47c6c | checkpoint | Survey (2)
85db5add-8502-5029-b2ec-ae09d1faa949 | note | ACCEPTANCE CRITERIA: Correct line and level for placement of concrete
285592e8-42c0-5dc6-87a1-273e1883a1b1 | date | Date Completed:
034faf9a-6a66-4786-89d8-40d3397f1f07 | checkpoint | Material Delivery (1)
9dbb26a4-74e8-55b8-ad79-3342a3d953a8 | note | ACCEPTANCE CRITERIA: Items conform with the applicable Australian Standard/s
2a663534-a869-564b-a1d3-c75332b03fa1 | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
9c3afd1a-26b1-5adf-9da2-7dc563393a42 | date | Date Completed:
8aaff2a1-7e1f-4989-b52e-7c945da54714 | checkpoint | Material Delivery (2)
4bc8b152-1424-5b11-9cc3-4bf43c217e16 | note | ACCEPTANCE CRITERIA: Items delivered with no visible signs of damage
b99e1221-caae-5d4c-9147-5e452db78b5a | note | COMMENTS / RECORDS: Delivery Docket, Supplier’s Certificate of Compliance
968fee1d-b0d7-58c5-920f-1907084d08e1 | date | Date Completed:
d2f998cd-73eb-43c3-bf78-6dcca650d515 | section | Pre-Pour Check (to be completed by Engineer or Supervisor)
3d48c77e-4c03-4047-b2ef-854a4568a7c9 | checkpoint | Confirm Dimensions
03f8e694-66c7-5ce3-8f49-358df6ac7235 | note | ACCEPTANCE CRITERIA: Visual Check and Measure dimensions are correct for trench width or Thrust Block dimensions
a035709c-8844-5a32-89c5-81642f7fb875 | date | Date Completed:
d6a0cde7-a8d1-4f05-a053-a3e953512410 | checkpoint | Initial pour against ground (1)
ec31f62c-c010-5018-8503-ff962a5ec8de | note | ACCEPTANCE CRITERIA: Surface free of water and soft spots
0a38ec50-ace2-54d5-89b5-f632576bd5d7 | date | Date Completed:
72f7bbb4-0fb0-4cd5-a883-b9793b55368e | checkpoint | Initial pour against ground (2)
c4e99a11-9f3e-5e7a-b700-bfe3736dca78 | note | ACCEPTANCE CRITERIA: Hardstand/ ground suitable for concrete pump location
8763fea4-0af4-526c-8607-0b43ac3382fb | date | Date Completed:
df69d467-c00f-456c-b3b7-07ec65493b63 | checkpoint | Initial pour against ground (3)
4815e622-24a3-51a7-8bdc-c1d1c8812ddf | note | ACCEPTANCE CRITERIA: 50mm blinding UNO
3adbb4d9-d41e-5ebc-9864-a6529bf134a2 | date | Date Completed:
0720518c-3fce-49b2-bb20-ee47ee93791b | checkpoint | Initial pour against ground (4)
1eef74ae-9b2c-567c-840f-5c415e67da25 | note | ACCEPTANCE CRITERIA: If for Thrust Block no loose Material
7203128f-e7c3-5fe7-aaf0-c9581bcae687 | date | Date Completed:
4d7f6957-b9e3-42eb-b13a-af7159f88f8d | checkpoint | Construction joints & surfaces
9f08a4d0-929e-5db5-8f8e-1924e83978f3 | note | ACCEPTANCE CRITERIA: Clean and free of laitance, scabble where required.
a4dc1e1f-575f-5bf5-94a9-ba2609840e02 | date | Date Completed:
23ef06e0-b7bf-495c-8ca0-5ac8058e4b7e | checkpoint | Reinforcement
4248ec4c-9262-5269-96fb-3b0e7dd17fba | note | ACCEPTANCE CRITERIA: Installed as per IFC drawings
41120141-3825-5274-a47a-93fa08f18e0d | note | ○ Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified
29f194f3-f336-5401-a06b-dd5d6174ed8d | note | ○ Extra tie wire on splice bars around construction joints and wedges fixed to support splice bars in stop end formwork
08361996-3304-51d8-a416-e774593941f9 | note | COMMENTS / RECORDS:
baac8399-01fb-56bb-9ab1-9426475d0780 | note | Cover (mm):
f88a314e-48fb-5ca6-a7e8-7c1ff5016e94 | tickbox | 50mm above obvert
327bd230-15e6-513e-a677-f96e126870e2 | tickbox | 75mm ground clearance
b970f5d1-15ec-57ce-bfdd-30e2e1b8bcaa | note | Reo Count:
b73e1354-4e60-54c5-bd59-b2c3ebcf9bfe | tickbox | Reo Count
c4ce3874-e841-554a-beb3-c4237202c3d7 | date | Date Completed:
740bc3c3-cc8e-475d-a527-7d075b4af213 | checkpoint | Cast-in items, block outs and hold down bolts
7864c898-f51b-5f4a-9699-eed662aee989 | note | ACCEPTANCE CRITERIA: Type, quantity and location as per design.
b3d27ff4-4e2c-5b11-adf1-8211568b8fba | date | Date Completed:
8a872082-341e-4ed7-81a0-d0fc075e8cbd | checkpoint | Final inspection (1)
dd142f68-b156-54f2-89ed-a8a02158097e | note | ACCEPTANCE CRITERIA: Pour arrangements agreed and equipment adequate
6c821076-40ab-592a-a64b-af72e3167ff9 | date | Date Completed:
00bfd1a0-4d52-4679-89da-342b1ec84756 | checkpoint | Final inspection (2)
7b0c96fe-19fa-5239-be3d-ac8c7bff5203 | note | ACCEPTANCE CRITERIA: Surface free of water, dust, debris and stains.
512f9628-b920-50ad-adb8-4a6fc1e47372 | date | Date Completed:
c2e6ef42-4272-4bb3-a25c-bab3b75d1a68 | section | Concrete Pour (to be completed by Engineer or Supervisor)
01d832be-7b8e-415d-8e5f-7a2411b6552f | checkpoint | Correct Batch / Grade of Concrete
fba7b12e-6163-5715-9268-b3bdbf481736 | note | ACCEPTANCE CRITERIA: Visual Acceptance of the docket prior to pouring
352ac658-1e55-535c-9c17-163c1f4dd291 | date | Date Completed:
c79fec9a-7d09-49fb-96ae-39bf42c253c8 | checkpoint | Concrete quality
981abd6b-3662-51d7-be6b-99638520e738 | note | ACCEPTANCE CRITERIA: Visual assessment of quality - note details of any loads rejected
38b1a9f5-3a07-5556-b84e-7c2a144c78fe | date | Date Completed:
b3468d4a-6dc3-48a3-9ece-2f4591d422ef | checkpoint | Concrete Testing (Vertical Crest Thrust Block)
e35a273e-aa90-5bce-8168-2e217760ca82 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
f6675274-38c0-5bfe-8d55-28c89f1db898 | date | Date Completed:
e44c8bd4-231f-448e-8d29-daa2b12d1964 | checkpoint | Concrete Testing (All Other Concrete Pours)
1d5e1b6e-5a98-5b75-a165-8d228e158bb1 | note | ACCEPTANCE CRITERIA: 3 sample Cylinder taken (7day and 2 X 28 day tests)
58b7d6d1-48fe-5423-a467-d3692d14415a | date | Date Completed:
4c66d260-243b-41e2-8953-d645341b917e | checkpoint | Compaction Method
41dd52de-885f-5885-9de5-fa662439db3d | note | ACCEPTANCE CRITERIA:
895441a0-5808-5a83-840a-0b1d70a487cc | tickbox | Pencil vibrators
3c7d4070-81c6-52e5-b46f-93b7156ac22b | textbox | ____No
18408afc-737d-5d08-a20d-410df604ae23 | date | Date Completed:
a2fff851-145a-5612-8ba5-dba6a106c273 | textbox | Signed:
f2154298-e766-5972-9282-3dca100e366d | note | Engineer (initial & date)
6cc2f104-bd57-5b69-b029-19d0b56e0be3 | textbox | Engineer - Initials:
66d9882e-6202-55d8-84fe-d1564f13127e | date | Engineer - Date:
16d7dfa5-957f-5236-9457-494209a670b3 | note | Supervisor (initial & date)
b7c4edba-9f75-53af-904a-4094072b890a | textbox | Supervisor - Initials:
4691252d-5de4-59cc-a63b-2711103ff57d | date | Supervisor - Date:
68224f10-8759-4236-8874-5632ed536fd8 | section | Post Pour Check (to be completed by Engineer or Supervisor)
9d7d7ab9-b41e-4fc9-9c1c-fb5274178168 | checkpoint | Curing of exposed surfaces
810d7661-c45a-58d5-9056-e92a37b33c7e | note | ACCEPTANCE CRITERIA: Exposed surfaces cured
695f7040-2d56-5d6b-8ed5-1925048a1a9f | tickbox | Polyethylene sheeting (edges / laps sealed, 300mm min laps)
0f764953-e7a3-5488-8c6c-0b97ba962a58 | tickbox | Curing compound
94bd2c9d-f0e0-55d0-b48b-f976111dadc9 | tickbox | Water curing (continuous spraying, ponding, wet Hessian)
a7fbe6bb-16ba-5669-82cf-c858ac2bfaa0 | date | Date Completed:
5adaa3d2-86e0-4aa8-9b63-05c0841af3ba | checkpoint-no-value | Location of embedment, hold down bolts and penetrations
3f001e90-eaf7-5acd-8a54-e35cb9665764 | note | ACCEPTANCE CRITERIA: All embedded items, hold down bolts and penetration located in accordance with drawings
0c1ee87d-e0e7-5e2d-abf8-15d5615cd58a | note | Refer defects list below
5ce42010-82fd-5992-9218-27d2b36cc1cb | date | Date Completed:
a2d76aaf-179f-4c02-93d6-caeac17676b8 | checkpoint | Details of defects – cracking in slab pours and Inspection of repairs.
9b872936-2b65-59ec-b422-b6dcaecc3d9b | note | ACCEPTANCE CRITERIA: Finish concrete surfaces inspected by Supervisor. Within specification tolerances (≤ 0.2mm)
f2f8830a-7f46-5633-a117-bb42f8b492e0 | note | ○ All defects repaired
f7c0e7d7-f120-54c7-8a86-747a264c440a | tickbox | Cracks requiring repairs observed
3696c69f-4807-5d18-9987-ae3c98f774ed | tickbox | Refer to attached location plan
f8646abb-b6ff-5be6-ada7-86d282f3631f | textbox | RFI
17b5c1bb-fd76-51be-ab19-b6df65cb6bd5 | tickbox | Repairs in accordance with approved specification.
d0e1305f-deab-5434-ae78-96cd570aaa49 | note | COMMENTS / RECORDS:
896ae33c-4c17-58a4-8e9f-cbcaf97a05be | textbox | Type of surface finish:
7a510f27-dc30-51a7-8a95-605ecc952634 | date | Date Completed:
2a0f2917-4d5d-4207-ad23-08c5caa415b1 | section | Final inspection
46e83414-5521-40ad-a330-342f5ca61e0a | checkpoint | Witness Point
795ae5a8-f08d-5a00-8a40-6ca6167546b4 | note | Engineer (initial & date)
93e5323b-4739-55ed-a797-1377245aac9e | textbox | Engineer - Name:
a8006b88-b4b3-5238-835c-5f5e874fd2fc | date | Engineer - Date:
7ea072b4-ebcd-5529-b506-56cfda3153a1 | note | Supervisor (initial & date)
d61d0af2-03b4-5807-b251-0471abe253e4 | textbox | Supervisor - Name:
bec9f298-d258-5126-8453-d304a57cd661 | date | Supervisor - Date:
2dedd558-a4a8-4b40-ae58-6fcbef100903 | signoff | Signatures
ed109a49-6696-48fe-80fd-76697dccd6ba | checkpoint | Details of other defects
797c68be-ddfe-5b6b-b1d0-b3e407f4347b | button | Defects listed and NCR raised (Y/N) | Yes,No
2eeae433-ef6a-57a2-bfca-1af92cef8424 | textbox | NCR #
44490003-4a69-40c4-bd75-b550f3f07db7 | checkpoint | As Built survey complete
df0f97ac-1a28-4cac-8e86-8a8e850388a4 | checkpoint | Close out
7c59119c-22a3-56ba-8246-28b3c6af462b | note | Final inspection: All work completed accordance with applicable procedures, drawings, specifications and approved changes
70e1cc3e-2e8b-5302-8287-12d0db41692c | note | Engineer (Name, Sign & Date)
f77088a2-379c-51ee-8612-ed2eb88eb4ac | textbox | Name:
1d642801-a9d3-5046-94f6-e0eea2272e21 | date | Date:
522d8b50-41c3-423e-b541-dd53a93435bc | signoff | Sign ITP
f9f3ce1a-52b6-42e7-8ebc-5f8f5dfa08d2 | checkpoint | Final Inspection
294182eb-db36-5a4a-877f-6128166bbc91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
154d2203-e473-5f8b-94ed-928fca373454 | textbox | Print Name:
91ffa316-85cf-58cc-bd53-6295a9ec1c04 | textbox | Position:
d2eb4d9f-27a7-5568-b75a-b5e7f47d26d9 | date | Date:
1ae80cc1-2a01-4060-9790-f68c05a67a73 | checklist | ITP No. 1 - Bridge Rail Installation | itp | ITP No. 1 - Bridge Rail Installation
e1664d1c-6e0d-43b6-8a7f-2ad517a7b0ee | section | Details
53b6390d-169a-4b06-9281-6802cb722a89 | checkpoint | 1 - Receive Materials
6cfda95e-3bc1-5821-b78c-f49640d441ba | note | FREQUENCY: Inspection prior to receiving
f555b790-e421-5c68-a25e-36a7ac72c27c | note | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
92772672-a62f-50ed-85ec-dd018c8f334e | note | REFERENCE DOCUMENTS: AS5131
955f8c3e-e08e-5d6f-8ca5-679fbeb9b22b | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
04afd706-d82f-5b98-b047-100cf827370d | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
012c83c7-6ad8-54d1-8b70-af1bb900b345 | note | HP, AP
4cb2a58c-055e-5d57-96c0-b6d4a924b75f | note | RESPONSIBILITY: Project Manager, Clients Superintendent
960e9cb4-d25e-5039-89a4-f08ac34c06b0 | date | Date Completed:
3a9af799-7408-4113-8974-1fc1afd375e1 | signoff | AUTHORITY HOLDPOINT
ad063ec7-f1cc-4ba8-9bf8-5f9510c60bde | checkpoint | 2 - Material Testing
aa9f3dd9-6811-5a62-94ac-7422c45ae4d8 | note | FREQUENCY: Each Lot and as required
2e3581eb-4cac-5b4b-9b56-5e99bc85c0ef | note | ACCEPTANCE CRITERIA: All materials to comply with IFC drawings
77627463-c200-574f-99dd-211abd546d85 | note | REFERENCE DOCUMENTS: Drawings
e5750e6c-d8d1-5e74-9c56-fcb52856179e | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
694ef867-3d34-53cd-b9ea-700a0d94afba | note | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
9ba89753-ca73-59d6-9a02-6043309c0005 | note | HP AP
8d5bbb85-9082-5bda-abf0-662d4f0985dd | note | RESPONSIBILITY: Project Manager, Clients Superintendent
1c2dae39-5a16-5f10-8d1c-8a9ef426fef3 | date | Date Completed:
5db9681e-47e0-4b0d-a128-8232d599f954 | signoff | AUTHORITY HOLDPOINT
15e8cbbf-8b9a-4ec5-a1ea-54461711deb8 | checkpoint | 3 - Welding
8b7e8bb2-613e-58b5-b1f4-638ae84d50ec | note | FREQUENCY: Visual Inspection
dcdc7bb6-f3c5-5b63-923d-f68e185729de | note | ACCEPTANCE CRITERIA: All welds to comply with IFC drawings
16950f38-6e12-5338-9696-27b8780f0efb | note | REFERENCE DOCUMENTS: AS5131
a7ead46b-b170-5ef9-83c7-9766ede6a68a | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
cbd44ed9-483d-5500-8215-4a9131d8edf1 | note | RECORD OF CONFORMITY: Qualified Welder Certification Reports
927bab02-20d3-5ed9-a950-7933bcc0b997 | note | HP, AP
163c2b91-bed7-5e23-9929-01bc22530997 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
9d1a39d1-dbdf-53cc-81b7-08a8d4a838e3 | date | Date Completed:
3ad61cbc-e43a-4612-85a2-d8e49e6cc60d | signoff | AUTHORITY HOLDPOINT
29a84c9c-4f8a-4121-9c3e-8d2cd67f7ec0 | checkpoint | 4 - Dimensional Inspection
dc24788e-b079-5f2c-9bdb-6146e3f4bf71 | note | FREQUENCY: Tolerance as per design
246ee90a-aa25-5f33-bb4e-e8c54248183e | note | ACCEPTANCE CRITERIA: To comply with requirements of the IFC drawings
b877852f-a749-54da-b861-fcab96d24190 | note | REFERENCE DOCUMENTS: Drawings
c4c97c92-1d57-539d-b3e9-50b698c093d8 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
2a2d6140-ab18-5ac2-ab44-40617783b262 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
c25d6dbd-02a1-5353-b229-16bb09c2cc05 | note | IP, IP
0cac953f-1410-5dce-8087-f3f0c3110182 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
e57019dd-a209-5eea-9f55-6947fc7829fa | date | Date Completed:
4616bacb-ee86-4e64-abcb-ec9d99dc4e28 | checkpoint | 5 - Surface Treatments
65e2461d-ace4-5ab8-abbb-94e605caaaa2 | note | FREQUENCY: Inspection prior to receiving
aa3c12b6-88f8-5bb9-aaae-622d27d07f3b | note | ACCEPTANCE CRITERIA: Superintendent shall confirm the quality of rail surface before the erection of rails commence.
2d6a0987-ffb7-583c-8d87-c269a2dd31d2 | note | REFERENCE DOCUMENTS: Drawings
4fa2179e-723b-5d80-a07f-ceb887a7a896 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
3ec01b32-b156-5f9a-b536-4aab617ddfc1 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
f824b24b-f491-5c87-938a-dd2ca7b4bf5e | note | IP, IP
6ae78cc8-47ad-50e6-bea9-13e2f17f1a36 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8de18812-189f-5dd7-a6d9-88368a78bd68 | date | Date Completed:
91268f55-c149-4a7f-beee-eeb0fe31cc42 | checkpoint | 6 - Fixtures
4abbd69f-1cd2-5a74-889f-d1187db0c345 | note | FREQUENCY: Visual inspection
bb4cb3fd-74ee-50a2-8a6b-9db23dd6ffc7 | note | ACCEPTANCE CRITERIA: Superintendent shall confirm the positioning/number of bolted connections.
d4d865ad-83fe-52ba-be4e-eabe3a1528d3 | note | REFERENCE DOCUMENTS: -
7b18ae47-9f75-5e8a-8b07-6878c6d6ce88 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
74c084f5-12dc-556d-857e-ae91dadba3e8 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
9c8720bb-a0eb-545f-91b7-d86fff8aac0e | note | IP, IP
00f88805-10fc-56d4-b338-a04feac75797 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8be56d19-5ae0-5a5c-b147-26d774e55245 | date | Date Completed:
abc6fb4d-4ddb-4b9c-ab50-b1338ff3408a | checkpoint | 7 - Concrete Infills
9e8aa6c7-feec-55f4-abd8-56960fda2d73 | note | FREQUENCY: Visual inspection prior to pour
8cecc8c9-cc89-5603-8875-631368138bd9 | note | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the positioning of bolted connections before the installation of the concrete infill commence.
59df7b80-cd25-54ef-80bd-c5cab8155fa6 | note | REFERENCE DOCUMENTS: -
5d951d03-9c4d-5371-92a1-247a90d4a9c1 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
e10760e6-d3bd-5ef7-9ee3-73603d34c0b7 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
17f9468c-b2d4-5267-97e2-08b1613e8b48 | note | HP, WP
42efda9f-f465-52bd-9a6b-d22d8d22c9b2 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
e0a03363-2ba0-5de8-b1dc-066ac726eebb | date | Date Completed:
64ba0693-3cb0-4193-b998-86e7070115f2 | signoff | AUTHORITY HOLDPOINT
645ffd5a-e010-4052-994b-7288b386e12a | checkpoint | 8 - Finishings
0e486dea-25c2-569f-86a7-16142bf3e6ae | note | FREQUENCY: Visual inspection upon completion
2d06bd82-9d88-5d82-a812-63922d2d347a | note | ACCEPTANCE CRITERIA: Superintendent shall complete a visual inspection of the finished bridge rail in accordance to the design drawings.
fc4ce7dc-fc6f-5971-8ae8-ce7bb9668c78 | note | REFERENCE DOCUMENTS: -
aa36b0ec-c8e5-5ff8-bdc0-423028ee3177 | note | INSPECTION / TEST METHOD: All measures in accordance with relevant documentation
678128bb-d616-5edf-a204-4a81c0917cfc | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
750c1919-15c1-54f5-899f-479f289fc6cb | note | IP, IP
f84548a2-78f5-5295-99e1-75cab5d5fe74 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
d8289a72-018b-5063-aae0-9f7cb8b8affb | date | Date Completed:
3dfbfff0-b483-4dd5-8d0b-f41900c8e8ef | checkpoint | Final Inspection
456b3b71-098d-5cf4-93cf-1414a9f664dd | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
572b658b-8558-5a48-abe3-56a4b223366b | textbox | Print Name:
9f5fe989-38c4-5765-a746-9a269e5b326c | textbox | Position:
9095111b-3fc0-55d9-8c39-fd6a17cf2aa5 | date | Date:
2c1d99ea-7385-4669-ae2c-48b0be7a0157 | signoff | Sign ITP
58a3711a-4ce9-46f0-bab9-ae400aae9946 | checklist | ITP No. 2 - Bored Pile Installation | itp | ITP No. 2 - Bored Pile Installation
ccbdda98-f163-4cf0-83e7-1d6b48fc3bb7 | section | Details
0e904d62-dada-47c3-bf12-c5584b9cad72 | checkpoint | 1 - Survey Setout
1fbf4a83-4896-53d4-92fe-9496d3a59dc4 | note | FREQUENCY: Inspection all new Setout
b516ec90-0128-5129-8fdf-fd8717be6b2b | note | ACCEPTANCE CRITERIA: Site inspection and client witness point
735cc604-6d7a-567d-8208-2aaa07a3ba55 | note | REFERENCE DOCUMENTS: Section 204
2c52ee11-78a0-5c3a-89b4-8cd90764927e | note | INSPECTION / TEST METHOD: Inspection
a3ef43bb-85c5-5e68-b94d-1a71062618f7 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d2ad6378-ac91-56e9-8ccb-0a28d5a0704a | note | HP, WP
cd3b2509-846d-559f-8673-81669a4bbff8 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
4e6afd8d-3e30-5bb0-9497-677a0289efac | date | Date Completed:
706057d1-2216-4f04-9cfe-1f30d1f67956 | signoff | AUTHORITY HOLDPOINT
fd088394-4e6d-4e25-af9d-b8a724a5c78f | checkpoint | 2 - Clearing and stripping of topsoil
b7073e76-3ed3-53a1-bcd4-e265f6c5f3ce | note | FREQUENCY: Clearing and stripping lot 1 of site
59eb685a-ea5c-5a8c-af05-247b92028ea7 | note | ACCEPTANCE CRITERIA: Compliance with drawings
e1048678-f677-5dd1-bf04-631134e7c51c | note | REFERENCE DOCUMENTS: Section 204
ef83a318-b00a-5a27-b45e-9082a18b7a17 | note | INSPECTION / TEST METHOD: Inspection
8c29ca65-e226-5486-9c83-f01640ea02b9 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d4c35abb-5dec-5326-a898-9dbbbef5cf16 | note | IP, IP
89d7f748-b8ec-5df5-bd77-8b3da4ed3302 | note | RESPONSIBILITY:
0519b884-8929-59ad-a8c3-82572243e7d3 | date | Date Completed:
7747ac9c-3967-43cc-b9aa-6fd6bacae01d | checkpoint | 3 - Supply & install of bored piles
9ffcb84b-cd53-5164-b881-3a2ef42b52d3 | note | FREQUENCY: Each bored Pile
60fd874c-d8bd-512f-81c4-dceeec70b149 | note | ACCEPTANCE CRITERIA: Compliance with drawings through completion of pile which includes:
27ffe0e6-a137-5aec-9393-c32ce74280e0 | note | ○ Material conformance checks
35420002-d4a5-59e2-bf99-4fe84365b662 | note | ○ Line, level, cover, and angle checks
2b8e9acf-26f0-5b7d-a3a4-9954867966b1 | note | REFERENCE DOCUMENTS: Section 606
a7508b70-ac9a-5f7a-9fbc-ad3ab38ad43e | note | INSPECTION / TEST METHOD: Pre-pour inspection, Delivery dockets
da1bfe8e-56dd-5c95-b3a0-e4c50d1675cc | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
27f37392-0b4b-53c4-9037-12cb5f75b1d0 | note | HP, WP
bbbec084-7f87-5e30-af30-bd09f0be73be | note | RESPONSIBILITY: Project Manager, Clients Superintendent
1aae1dea-b990-5d96-9935-85e58b4f216c | date | Date Completed:
839b1af8-7f2c-40da-9ae9-5c9ce671b92b | signoff | AUTHORITY HOLDPOINT
c7e43732-cc5e-4461-a79a-89d741ee0d57 | checkpoint | 4 - Earthwork reinstatement
c8cb109a-9a02-5d07-ac8d-134b542a7d4d | note | FREQUENCY: Each lot where 1 lot is 1 site
d3b3a854-e53e-5542-9c55-91b9368bc070 | note | ACCEPTANCE CRITERIA: Compliance with drawings. checks for line, length and level
b638e125-ee06-5eb7-8647-1b4ca3d3d131 | note | REFERENCE DOCUMENTS: Section 201
59457830-a407-56b7-95db-c3eece8dd0be | note | INSPECTION / TEST METHOD: Inspection
33794a4e-a923-5fc5-a166-6208082deb52 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
7f68fd04-196c-54eb-bd02-898a48223a33 | note | HP, WP
2ea6fa4c-eba8-50c4-a323-185432abd354 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
9ab5602f-efa7-528a-bf1d-de5c82bf42e7 | date | Date Completed:
f21868cc-3241-4842-913b-d3e2ac72bccf | signoff | AUTHORITY HOLDPOINT
8e334325-12a8-41a6-a189-e836f1c18bd0 | checkpoint | 5 - Practical Completion submission and acceptance
746e85c2-1f9c-50ef-b831-4636b6f4d097 | note | FREQUENCY: Each lot where 1 lot is 1 site
c0f50cc8-4234-592f-8e9b-0806266015bc | note | ACCEPTANCE CRITERIA: Project completion achieved in accordance with subcontract agreement.
df8783d9-b4de-5aa1-927e-a28758ad7d6d | note | REFERENCE DOCUMENTS: N/A
7338177b-1df9-5074-a74b-6e64366acd51 | note | INSPECTION / TEST METHOD: Inspection
ce9b3b16-f1c4-52f6-ae0a-1031cbaf7010 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
29fed374-e90f-5409-8906-e58ed3631f8a | note | HP, WP
ab25c10c-6b84-5765-a545-f884728211f1 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
c8be335d-2c9e-5798-80b7-6b60070253ff | date | Date Completed:
9d1e8a5b-8183-4025-b3c1-12275a9b3590 | signoff | AUTHORITY HOLDPOINT
994a812f-2559-4adc-9d76-753b012edbae | checkpoint | Final Inspection
e48ca631-d6f8-5fb2-b710-2c8107c88ba9 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
00627329-6fd9-5a3d-baf1-00adcbe4a097 | textbox | Print Name:
5893bc27-234a-50fe-99b9-40771e471a80 | textbox | Position:
8cef173c-5c84-5013-b4d1-3a1dddf4d816 | date | Date:
887e6413-fe16-41a2-aba4-f60685ade924 | signoff | Sign ITP
b832ded7-1923-4a16-ba6f-761184a900ed | checklist | ITP No. 3 - Guardrail Installation | itp | ITP No. 3 - Guardrail Installation
824b1b18-3358-43ed-a633-8398cd0f3119 | section | Details
6fd1cf18-b472-4719-8a06-016c1917f5f8 | checkpoint | 1 - Setout
1c0adc80-f7f1-5abc-9def-1aa029c09918 | note | FREQUENCY: Prior to commencing any activity
2d16519b-1eeb-50f9-92cd-aed99b3ab00f | note | ACCEPTANCE CRITERIA: Chainage locations clearly identified for extent
74640689-ed2f-5aad-a020-7b58668c857e | note | REFERENCE DOCUMENTS: Design drawings Section 708
b2905f43-0053-5b6f-a727-4ef23e5a463a | note | INSPECTION / TEST METHOD: Inspection
85ddbf7c-73cc-58c1-83fc-7de2f2597764 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
5c763457-92e4-5e6d-ba9a-bf1ff09b34f5 | note | HP, AP
7ab1e8de-9c98-518a-92a9-c138d5c0c84e | note | RESPONSIBILITY: Project Manager, Clients Superintendent
89d47a7b-2a64-5017-b4e5-ac7c6b0dae74 | date | Date Completed:
16862089-07f9-45bd-89bf-836da7be3f6a | signoff | AUTHORITY HOLDPOINT
7d29dc54-79c1-4009-a4d2-e91b80cfda80 | checkpoint | 2 - Supply of materials
ad883418-1f28-56ae-9354-1c6c282db6f9 | note | FREQUENCY: Each delivery
16569a61-7449-5f0b-acf9-7a78b0875080 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
36f7cbad-1f6f-5016-aeac-09f6a66d82df | note | REFERENCE DOCUMENTS: Design drawings Section 708
3e66aa30-0d9c-5006-8c06-0ad815085450 | note | INSPECTION / TEST METHOD: Inspection, Certificate of materials
ef16625b-057d-5259-83ea-26e3cbd38739 | note | RECORD OF CONFORMITY: Material Certificates, D/Dockets Matched & Signed
132f73f0-3f7f-59a7-a757-6b85d7908d3d | note | HP AP
5c980973-f8ca-5aca-ba97-51b014c0e029 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
bdc22abd-fd67-5c39-afc9-da2d454c771a | date | Date Completed:
9a9e4bb4-d68d-4bc2-8624-5e74fb2d258a | signoff | AUTHORITY HOLDPOINT
701dda6b-049c-4a8e-bdbc-a5e5bee6737b | checkpoint | 3 - Installation
e11e6b6f-92e9-5761-a5e7-ce28f4c9a8e9 | note | FREQUENCY: Each lot as required
ff78ae02-dbb5-50a0-b82b-17eccfd9d8e9 | note | ACCEPTANCE CRITERIA: The offset, height and post spacing is to conform with VicRoads specifications and the detailed design
d978bb43-3e35-5db8-ad54-5b0f2f941345 | note | REFERENCE DOCUMENTS: Design drawings Section 708
d15d4928-a218-5f5a-983b-99bf84a5ab04 | note | INSPECTION / TEST METHOD: Inspection
c3062974-c1c9-598b-825a-290fd33fa436 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
797f9361-6664-5aea-be16-3df430340317 | note | HP, AP
4b90c5c3-c7f5-514a-98fe-b9b2817be8f4 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
8eeda902-70fa-5c5c-80eb-553f74a2f56e | date | Date Completed:
e62b0143-d7bc-46ee-86cf-f36cb3732b5e | signoff | AUTHORITY HOLDPOINT
9eaa4758-68af-4b56-8991-a6299ccf168e | checkpoint | 4 - End Treatments
0207bff1-43f1-5acd-887d-b7d316d8442e | note | FREQUENCY: Each lot as required
45c9732b-733c-571a-9843-f45dfb1d3ed3 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads specifications
2cc7317c-ffd5-52cb-aa94-084d6e51d052 | note | REFERENCE DOCUMENTS: Design drawings Section 708
83ba2ab4-db18-5ab2-8ec3-ca9aeba93eac | note | INSPECTION / TEST METHOD: Inspection
a0832483-9ae8-5119-8147-79b5844dcef5 | note | RECORD OF CONFORMITY: Qualified Welder Certification Reports
c32401ae-e81b-50fc-88b3-0ccd8d1a4e4e | note | IP, IP
9d50696c-3ce7-5910-a5b9-ef9e6ee50150 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
71db2813-96d3-5637-9b35-2b6c1accebe5 | date | Date Completed:
813b4352-c4e9-44c1-bb48-122dfd487fed | checkpoint | 5 - Motorcycle rub rail
de3e21ce-fa2f-57dd-b8f2-7ff271f61c7b | note | FREQUENCY: Each lot as required
b47e90da-b6be-5b92-ae2b-f13e7a62ca0c | note | ACCEPTANCE CRITERIA: Where specified, motorcycle rub rail is to be installed on the new length of guardrail
e3082cde-9ca8-586a-af29-29444d985f05 | note | REFERENCE DOCUMENTS: Design drawings Section 708
a79320c6-af1f-560e-880f-9447afb132b5 | note | INSPECTION / TEST METHOD: Inspection
4762d785-e27d-5761-973a-3377f2e4eb23 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
31663dd6-bf14-5a31-afa9-481363d8f027 | note | IP, IP
d887b7a1-f9cc-5c24-867a-1ba296a98176 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
b3e4a56e-69bb-57a3-b17a-02fc26aaf3b5 | date | Date Completed:
2b7530ad-f2c1-4cb0-b52f-b2ecac30960d | checkpoint | Final Inspection
88d6140f-d62c-581a-a4e5-112238177352 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
3b7bb401-83e3-5902-9d43-b99bd2c30c0c | textbox | Print Name:
758ee2a4-ca83-506f-947d-5227d7bfe9ae | textbox | Position:
319f045b-33e8-5ff9-8fb9-3506e8e9838f | date | Date:
2ab2f725-eed2-40f5-aff4-8fc9e09055cb | signoff | Sign ITP