## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
58a3711a-4ce9-46f0-bab9-ae400aae9946 | checklist | ITP No. 2 - Bored Pile Installation | itp | ITP No. 2 - Bored Pile Installation
ccbdda98-f163-4cf0-83e7-1d6b48fc3bb7 | section | Details
0e904d62-dada-47c3-bf12-c5584b9cad72 | checkpoint | 1 - Survey Setout
1fbf4a83-4896-53d4-92fe-9496d3a59dc4 | note | FREQUENCY: Inspection all new Setout
b516ec90-0128-5129-8fdf-fd8717be6b2b | note | ACCEPTANCE CRITERIA: Site inspection and client witness point
735cc604-6d7a-567d-8208-2aaa07a3ba55 | note | REFERENCE DOCUMENTS: Section 204
2c52ee11-78a0-5c3a-89b4-8cd90764927e | note | INSPECTION / TEST METHOD: Inspection
a3ef43bb-85c5-5e68-b94d-1a71062618f7 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d2ad6378-ac91-56e9-8ccb-0a28d5a0704a | note | HP, WP
cd3b2509-846d-559f-8673-81669a4bbff8 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
4e6afd8d-3e30-5bb0-9497-677a0289efac | date | Date Completed:
706057d1-2216-4f04-9cfe-1f30d1f67956 | signoff | AUTHORITY HOLDPOINT
fd088394-4e6d-4e25-af9d-b8a724a5c78f | checkpoint | 2 - Clearing and stripping of topsoil
b7073e76-3ed3-53a1-bcd4-e265f6c5f3ce | note | FREQUENCY: Clearing and stripping lot 1 of site
59eb685a-ea5c-5a8c-af05-247b92028ea7 | note | ACCEPTANCE CRITERIA: Compliance with drawings
e1048678-f677-5dd1-bf04-631134e7c51c | note | REFERENCE DOCUMENTS: Section 204
ef83a318-b00a-5a27-b45e-9082a18b7a17 | note | INSPECTION / TEST METHOD: Inspection
8c29ca65-e226-5486-9c83-f01640ea02b9 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
d4c35abb-5dec-5326-a898-9dbbbef5cf16 | note | IP, IP
89d7f748-b8ec-5df5-bd77-8b3da4ed3302 | note | RESPONSIBILITY:
0519b884-8929-59ad-a8c3-82572243e7d3 | date | Date Completed:
7747ac9c-3967-43cc-b9aa-6fd6bacae01d | checkpoint | 3 - Supply & install of bored piles
9ffcb84b-cd53-5164-b881-3a2ef42b52d3 | note | FREQUENCY: Each bored Pile
60fd874c-d8bd-512f-81c4-dceeec70b149 | note | ACCEPTANCE CRITERIA: Compliance with drawings through completion of pile which includes:
27ffe0e6-a137-5aec-9393-c32ce74280e0 | note | ○ Material conformance checks
35420002-d4a5-59e2-bf99-4fe84365b662 | note | ○ Line, level, cover, and angle checks
2b8e9acf-26f0-5b7d-a3a4-9954867966b1 | note | REFERENCE DOCUMENTS: Section 606
a7508b70-ac9a-5f7a-9fbc-ad3ab38ad43e | note | INSPECTION / TEST METHOD: Pre-pour inspection, Delivery dockets
da1bfe8e-56dd-5c95-b3a0-e4c50d1675cc | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
27f37392-0b4b-53c4-9037-12cb5f75b1d0 | note | HP, WP
bbbec084-7f87-5e30-af30-bd09f0be73be | note | RESPONSIBILITY: Project Manager, Clients Superintendent
1aae1dea-b990-5d96-9935-85e58b4f216c | date | Date Completed:
839b1af8-7f2c-40da-9ae9-5c9ce671b92b | signoff | AUTHORITY HOLDPOINT
c7e43732-cc5e-4461-a79a-89d741ee0d57 | checkpoint | 4 - Earthwork reinstatement
c8cb109a-9a02-5d07-ac8d-134b542a7d4d | note | FREQUENCY: Each lot where 1 lot is 1 site
d3b3a854-e53e-5542-9c55-91b9368bc070 | note | ACCEPTANCE CRITERIA: Compliance with drawings. checks for line, length and level
b638e125-ee06-5eb7-8647-1b4ca3d3d131 | note | REFERENCE DOCUMENTS: Section 201
59457830-a407-56b7-95db-c3eece8dd0be | note | INSPECTION / TEST METHOD: Inspection
33794a4e-a923-5fc5-a166-6208082deb52 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
7f68fd04-196c-54eb-bd02-898a48223a33 | note | HP, WP
2ea6fa4c-eba8-50c4-a323-185432abd354 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
9ab5602f-efa7-528a-bf1d-de5c82bf42e7 | date | Date Completed:
f21868cc-3241-4842-913b-d3e2ac72bccf | signoff | AUTHORITY HOLDPOINT
8e334325-12a8-41a6-a189-e836f1c18bd0 | checkpoint | 5 - Practical Completion submission and acceptance
746e85c2-1f9c-50ef-b831-4636b6f4d097 | note | FREQUENCY: Each lot where 1 lot is 1 site
c0f50cc8-4234-592f-8e9b-0806266015bc | note | ACCEPTANCE CRITERIA: Project completion achieved in accordance with subcontract agreement.
df8783d9-b4de-5aa1-927e-a28758ad7d6d | note | REFERENCE DOCUMENTS: N/A
7338177b-1df9-5074-a74b-6e64366acd51 | note | INSPECTION / TEST METHOD: Inspection
ce9b3b16-f1c4-52f6-ae0a-1031cbaf7010 | note | RECORD OF CONFORMITY: This Inspection & Test Plan (ITP)
29fed374-e90f-5409-8906-e58ed3631f8a | note | HP, WP
ab25c10c-6b84-5765-a545-f884728211f1 | note | RESPONSIBILITY: Project Manager, Clients Superintendent
c8be335d-2c9e-5798-80b7-6b60070253ff | date | Date Completed:
9d1e8a5b-8183-4025-b3c1-12275a9b3590 | signoff | AUTHORITY HOLDPOINT
| checkpoint | Requirement to undertake Pile Integrity Testing
994a812f-2559-4adc-9d76-753b012edbae | checkpoint | Final Inspection
e48ca631-d6f8-5fb2-b710-2c8107c88ba9 | note | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
00627329-6fd9-5a3d-baf1-00adcbe4a097 | textbox | Print Name:
5893bc27-234a-50fe-99b9-40771e471a80 | textbox | Position:
8cef173c-5c84-5013-b4d1-3a1dddf4d816 | date | Date:
887e6413-fe16-41a2-aba4-f60685ade924 | signoff | Sign ITP