## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
ee296416-c096-4994-9f69-8d9ce2b0e80b | checklist | Checkers Checklist - Abutment Base - AA |  | Checkers Checklist - Abutment Base - AA
532fbde3-27d7-49e0-87c2-e5acf3623501 | section | Checkers Checklist
adc3a5b7-8c4e-4fe6-878d-70c5c585088c | checkpoint | Site Safety / Workers Safety
e2b01c3d-03a6-440f-bf01-54167d4d2dc6 | checkpoint | Availability of updated shop drawing
f5cf9016-608f-4b92-9bb7-3cce81d29490 | checkpoint | Double Check the Ferrule placement -Type AA (550F400F1050F400F1050F400F550)
228cb289-be11-5370-bbd9-43d41dcfc7c8 | dropdown | Ferrule: | 550F400F1050,500F500F950
d9e30401-7010-4eef-9ab4-874f000bb9f6 | checkpoint | Overall Measurements of construction Element
4527f889-d1e9-445a-a128-b09f2abb0cac | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
cb20829d-8d4e-4353-9f84-292ab28c8a4f | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
9527ad8d-d9eb-432b-8819-ff653454d0a9 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
ce8c4fac-ae8b-4fcf-a586-c12691094873 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
995d8656-28d1-4797-8645-a68ea90e1659 | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mmDia ,300mm - 06 Nos as per the Dwg: S06
a1adc215-02b1-4d8e-bf42-6d9572cb7338 | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
93a6e719-a7d5-4cf2-b20e-c8c2299c9e1f | checkpoint | Concrete cover check minimum 30mm
7b52ec9c-7636-41f4-b4bf-6cce3961de14 | checkpoint | Panel length check, alignment check -4400x800mm
a18604a0-2707-44fa-957b-e0fabb9fd8a4 | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
2c2f65ad-687f-4ef6-b027-1ba45c383e4f | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
566add2c-e4f9-48dc-9026-f0bfae874bc4 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
88df2496-408c-409e-998e-4e9ea5fa6b49 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
2cfeec54-9de3-454d-8f66-c1ea1833ddd7 | checkpoint | Curing Procedure arranged
3f55e5de-0c61-45d5-8737-314f661a61ff | checkpoint | Photo Taken
36d228fd-ac9b-48c8-bf06-c81a9f77526d | checklist | Checkers Checklist - Abutment Base - BB |  | Checkers Checklist - Abutment Base - BB
d17c7e25-7abf-4cef-9975-252624a84343 | section | Checkers Checklist
3434f32e-fc09-46ff-99c7-a237f2833498 | checkpoint | Site Safety / Workers Safety
bfa12b83-34e5-4fbe-b223-90c26e2f8505 | checkpoint | Availability of updated shop drawing
264292cb-1de5-4e4b-9df0-9a455aaecdd6 | checkpoint | Double Check the Ferrule placement -Type BB (500F500F950F500F950F500F500)
e1117fd9-7020-5c1d-a7da-99858e95d18c | dropdown | Ferrule: | 550F400F1050,500F500F950
f3adecdb-5483-4112-9ddd-5fda577bb493 | checkpoint | Overall Measurements of construction Element
02ff0377-ee8d-4941-b45f-f8dd0c369e4d | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
e7c9e9ce-9dd0-4731-a35c-cc5ecabb9d02 | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
a5a47ec2-4a31-4ef6-b9ff-d9417ebbccdd | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
d4c9d14f-861d-472e-927f-184107525a4e | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
18a678ee-420d-42d5-9be9-124c731c58b4 | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mmDia ,300mm - 06 Nos as per the Dwg: S06
cf250a0b-667c-4704-b0fa-c073ac9d864a | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
565078f6-c54b-4932-a80a-aeb3b17d06c4 | checkpoint | Concrete cover check minimum 30mm
e21064d8-71d0-488e-a552-6884f265fc5c | checkpoint | Panel length check, alignment check -4400x800mm
285c8b13-403a-44f3-9284-6d9da8f811c8 | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
20441890-bfcf-4b0a-83b3-f8b317c20937 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
24dbd1a0-3ef0-44ce-81e3-82ca3885640a | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
b28957b7-3590-41fb-9940-aa90060cc24e | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
f61f71ed-6b76-4a79-bc83-abc1154e2fb3 | checkpoint | Curing Procedure arranged
d9beadbf-6449-4fb1-9931-eac88c8a8d01 | checkpoint | Photo Taken
29bab919-d990-49e0-806b-5be3fbced106 | checklist | Checkers Checklist - Type A - Bridge Plank |  | Checkers Checklist - Type A - Bridge Plank
8d412938-66ce-4c3c-af4f-91be7640bd1a | section | Checkers Checklist
1b3923a9-d721-4907-bc82-15a420761913 | checkpoint | Site Safety / Workers Safety
04b49532-7e15-4102-860f-69d2040f36ee | checkpoint | Availability of updated shop drawing
c4e8897f-23b0-4f6d-9e9e-b28fe2ab250e | checkpoint | Double Check the Ferrule placement - Type A (300F1450F400F1450F300)
3c6a0ca3-2140-5ce4-b498-bd7aa940a400 | dropdown | Ferrule: | 300F1450F,250F1450F
ab4d37ca-e78b-474f-8db7-d783ba3a0329 | checkpoint | Overall Measurements of construction Element
7ca40e73-0d96-40e0-b1ad-be8d1fbd78b9 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
1a6868cd-8e18-4fcd-ba89-e91bedac4153 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
06e3721e-10e4-42ed-91f2-a91355060edf | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter
9cddbbd8-5a66-4d0b-84a5-c1c15af4a945 | checkpoint | Concrete cover check minimum 30mm
b8ee21a1-2a50-406c-a703-26479899b4eb | checkpoint | Panel Thickness check,allignment check -150mm
dd331bd1-6638-47e7-b7a6-23ccf484c003 | checkpoint | Panel length check, alignment check -3900mm
6f3d5ea5-c644-4779-8953-e71bb56d7da0 | checkpoint | Diagonal length check, alignment check (4025 mm or close to this)
daf230e3-3562-4433-b747-937a0b51d7d1 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
e37e7e8d-85ee-4324-a795-c5f41344c777 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
f5bbd5b9-1c39-43fd-ab24-1da2a2faec78 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
f00c8dbc-51a6-4809-a156-f4c0d5762557 | checkpoint | Curing Procedure arranged
0fa0f5df-a309-4351-8d41-7b08cba6d8a8 | checkpoint | Photo Taken
db2cc176-c234-4803-8bc0-d944d06a498a | checklist | Checkers Checklist - Type B - Bridge Plank |  | Checkers Checklist - Type B - Bridge Plank
ffacaa50-2d5a-4e36-a358-ebd1d7f89f3e | section | Checkers Checklist
9dbbd83a-8469-4427-b770-a9dc0da30bbe | checkpoint | Site Safety / Workers Safety
4c9d52fc-81d9-4b95-b048-d3b4df19880e | checkpoint | Availability of updated shop drawing
18f33459-99b7-470e-9e2d-4550c1944dbf | checkpoint | Double Check the Ferrule placment -Type A (250F1450F500F1450F250)
6d8bfd12-d208-534c-bd9b-9781fba83d94 | dropdown | Ferrule: | 300F1450F,250F1450F
80ed392b-595e-457b-8344-d7c29dd3581c | checkpoint | Overall Measurements of construction Eliment
219996fd-bb91-4af9-8b41-5e50c324e5d8 | checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
e9c91527-ab9f-4edd-bde0-5962ebd46e88 | checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
930675e9-b7be-4b0e-9f69-438766a29ca5 | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter
8e7d5be7-1c0d-4599-b7f9-134e252c95a3 | checkpoint | Concrete cover check minimum 30mm
dab5a51e-b8ef-4a66-8c38-455607519145 | checkpoint | Panel Thickness check,allignment check -150mm
4615ba3c-945f-4465-9a82-9608384a5ae8 | checkpoint | Panel length check, allignment check -3900mm
df0b6db8-1960-477f-9d0c-c2c1f558bc43 | checkpoint | Diaganal length check, allignment check (4025 mm or close to this)
0e47372c-2c83-45db-b951-a8fee30e9f4b | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
c8a4c4ef-ca13-4fe8-9128-b4aaa3e3048f | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
23d4e231-2e04-4143-b6e6-74f74567cd90 | checkpoint | Reinforcement (Reo) placed, cleaned, tightned
e494aa58-cc1f-41d4-83b1-b820748efcbc | checkpoint | Curing Procedure arranged
a2e99321-27e3-46de-a1eb-fb9cef7ef201 | checkpoint | Photo Taken
d67c36eb-c2c5-416f-8347-1dff57f96723 | checklist | Checkers Checklist - Upper Wall - AA |  | Checkers Checklist - Upper Wall - AA
5251037a-7fcc-426f-916c-6f444c18a9f5 | section | Checkers Checklist
72f29ad7-efeb-4ba6-a4b6-fde6ed64cb0c | checkpoint | Site Safety / Workers Safety
92574bbb-bbf5-447d-96a3-d1a866d246e7 | checkpoint | Availability of updated shop drawing
e7f38f05-1f56-497d-a521-f54d75bcad34 | checkpoint | Double Check the Ferrule placement -Type AA Wall Height - 582mm
d8eff454-db3b-5e5a-89d9-74a35ccaaf47 | dropdown | Ferrule: | 582mm,776mm
5e93495a-9a1e-40d5-bff7-3c851d9e1a9c | checkpoint | Overall Measurements of construction Element
98a6920a-67a2-4ac8-8a3b-a49f9f0b4f7b | checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
f79f9473-36dc-43cd-81cd-0dc7ce8e2376 | checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
e8b64e28-316b-484d-a529-e4c6cee3affa | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
be7d971c-0f88-4944-b941-dab12102911f | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
0fd87adc-69ec-4dd2-a9cd-2594d4eaf0e9 | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
00b6591b-5dfb-4363-9711-32a1dd843d09 | checkpoint | Concrete cover check minimum 30mm
3ed69f7e-8155-447c-87b2-c3a7f62a9e3f | checkpoint | Panel Thickness check,allignment check -150mm
8bdef16a-0822-4396-8d14-3deb1742e25a | checkpoint | Panel length check, alignment check -4400x800mm
39329eb2-2151-449b-951a-b263cecc8e88 | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
b4af95a1-1350-42c7-a9a6-81ecb20fe50c | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
a702657d-dc96-42a0-8b63-1da66ebd8fa9 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
f1468128-956e-4864-add8-94a60d0612ff | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
6d10d383-67d2-4b40-ac27-d26756de8418 | checkpoint | Curing Procedure arranged
32540b01-f026-4c4a-a158-22b93cbf0a79 | checkpoint | Photo Taken
e737dc56-4b34-4062-befe-a0b749afdbd0 | checklist | Checkers Checklist - Upper Wall - BB |  | Checkers Checklist - Upper Wall - BB
ce3eb276-1945-47af-9f6a-09e65c096efe | section | Checkers Checklist
2249fb35-df0a-478d-958f-eb51404ad088 | checkpoint | Site Safety / Workers Safety
50c93608-bca3-4a50-ad1f-a305cee65d9d | checkpoint | Availability of updated shop drawing
32761239-de14-4a0b-b40d-c30ba0e51fc0 | checkpoint | Double Check the Ferrule placement -Type BB Wall Height - 776mm
8dd8ea35-3b82-5ac2-8ccb-36b7ec51c7ca | dropdown | Ferrule: | 582mm,776mm
e80a84c4-3f33-40de-bc5b-3d6ead6c4754 | checkpoint | Overall Measurements of construction Element
08071e94-8e1f-4013-828a-69aae24c57d1 | checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
7fde063e-671a-4516-a7b8-b7eca8f7364c | checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
f0e21a30-f1ab-4d63-a66a-c76ff3fca87c | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
333dfe4e-43b4-4b6e-a154-607d7fe5f3e8 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
9a25494d-afed-411a-9ac2-2e33508a0e14 | checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
35ba9207-c020-408a-8bd8-1b98786f308d | checkpoint | Concrete cover check minimum 30mm
ba7a61c8-1f26-4bae-8ce2-1ea58d0e0df8 | checkpoint | Panel Thickness check,allignment check -150mm
0a21eb12-7dac-47f1-990b-48378eec45c6 | checkpoint | Panel length check, alignment check -4400x800mm
b4745d6a-f9cd-4df8-b0e0-d18625f42df6 | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
f26a4254-acf3-4c96-8fba-36c4e186178c | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
fbf747ba-8d1e-41b6-b551-3bbecaea767a | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
def424ca-fe8c-4045-857b-b3e2f87865e2 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
c5285c18-f3cd-4689-b29a-305703a4005f | checkpoint | Curing Procedure arranged
d6c9f224-1248-4d08-aa8c-17a778f12bc0 | checkpoint | Photo Taken
86db69f6-b367-4aeb-ba70-4e92a02c3f6e | checklist | Installers Checklist - Abutment Base - AA |  | Installers Checklist - Abutment Base - AA
315af85d-0ab6-4572-a9ca-933ac28b3f94 | section | Job Approval Documents/Construction Documents
4966aefe-d43e-4b96-8e69-76da491ae68a | checkpoint | Complete Material "Bucket List"
5c589ec5-acb1-4cde-aa3e-819d717852e8 | checkpoint | Eye Anchor - 2.5T(170mm) - 04
6982563b-101b-42d7-9f31-2a3ccbdf2c68 | checkpoint | Ferrules - M24 x 96mm
c38de9e1-6c5c-4bae-984c-7059fd53afd1 | checkpoint | ID Plate
8e36001e-bdfc-5164-8af9-6e7efc74962b | textbox | ID:
2f3fbe05-ebee-4d2c-9338-5d139f0e3fa7 | section | Pre-Pour Check Approvals
be71dc72-46a5-43ba-a2cd-da6d41be6e29 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
8f23acae-2f59-47fe-9f3a-8d4522c65e4d | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
01d7bf13-0260-4360-af5a-541616fc14e8 | checkpoint | Temporary Fix ID Plate to Formwork
65419717-fc80-475e-8812-35d6ec6ffcfa | checkpoint | Double Check the Ferrule placement -Type AA
7708b4f6-9d38-4f8b-9414-7261011eb8e1 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
ed64e9e9-4d7d-48a4-ad75-199ab41aa2d8 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
c2e1bcc4-2cc8-5915-9f3c-810330ef68e1 | tickbox | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
d19a711c-6907-5c0d-8406-21af1a702eef | tickbox | Embedded Item - Ferrules for Dowels - Position,Size -M24 (96mm) - 07Nos
435792bf-48ef-53fc-ac79-54e3145e63a7 | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
1e03d909-d6b5-423a-96d7-026ac59e4d87 | checkpoint | Concrete cover Check - minimum 30mm
f628e492-7d08-4d68-840a-7d1b4899e8bf | section | Quality Assurance
5d8ed3ef-987b-4e82-94d9-ae882fa0f271 | checkpoint | QA - Final Check of ALL measurements
6fc9d57b-cb02-4a50-a80b-692b8cae7cd6 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
57d6a765-d5af-4859-a219-9b4d58077d56 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
1921dd69-36bf-4b26-b496-68e9284ad622 | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
f4b3af90-a537-5461-9569-bb0209a66a52 | date | Pour Date
3a67cda8-f284-44c8-87b1-6c6b5aaabad3 | checkpoint | CONCRETE TEST Procedure
5643296d-884e-4a56-870c-c90e2232380b | checkpoint | APPROVAL FROM ENGINEER
6026879e-2b92-48e4-b3b9-ef379abf88b0 | section | Other Arrangements
4550a233-77c2-4b4b-b662-3afdce3ea4bd | checkpoint | Concrete surface Finish Requirement arranged
b6d8f84f-5d02-59c0-bfd1-840d08ebf824 | dropdown | Finish: | Fine finish,Broom finish
2bec819c-a90b-4eb9-8921-40d82c122928 | checkpoint | Curing Procedure arranged
3587ac0f-7ae1-4ebe-a4f7-2f9eece3d186 | checklist | Installers Checklist - Abutment Base - BB |  | Installers Checklist - Abutment Base - BB
11e778cc-6b90-48b5-8d3f-878150a61405 | section | Job Approval Documents/Construction Documents
50d0ee8c-9452-4ce9-a5d1-071bf3f71f4c | checkpoint | Complete Material "Bucket List"
74c42fe5-91d0-43ff-a5ff-905dd735f15c | checkpoint | Eye Anchor - 2.5T(170mm) - 04
606e0c93-6ec8-44ee-9b3c-5b5e71e8451c | checkpoint | Ferrules - M24 x 96mm
bd809ada-5f6c-45d2-a379-5fb7581761d1 | checkpoint | ID Plate
42639d63-f42b-509e-81fd-b0857c8dd9aa | textbox | ID:
05f142e0-3606-43d1-81ec-6414aaf2f3e6 | section | Pre-Pour Check Approvals
93daeca1-c95d-4759-b4bc-5d1b8584cf6b | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
e0447c25-2ac5-4538-80e0-18b846dc9d3c | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
6a0fa4a0-6baf-49aa-97f2-458c4d3225b8 | checkpoint | Temporary Fix ID Plate to Formwork
3cb5a1f4-09d1-4196-ab9a-6735fbae1a07 | checkpoint | Double Check the Ferrule placement -Type BB
e5b0d9c9-f4b7-4349-8c04-b44a3614382e | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
1c818e86-2bee-4832-9ce5-4b35509850f5 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
36f2c022-f6f5-5b82-91d0-ed3492abbf44 | tickbox | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
bab51d27-5aae-57f5-90f4-2808526242a4 | tickbox | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
325b4509-54e5-568d-9c7e-fc4ce018b581 | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
72c71d7e-60db-4adf-a1ce-9307dc59f061 | checkpoint | Concrete cover Check - minimum 30mm
9c0165b7-e84f-4667-8ba6-aa4e344a2326 | section | Quality Assurance
8efe72e7-0ec8-4f2e-9cbb-0e49850f1ba8 | checkpoint | QA - Final Check of ALL measurements
87c85944-279d-470f-abfa-eb2fdf6c56fd | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
4ac57da6-329f-4760-856d-d60a217c619e | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
4c18ca71-a096-4516-bf7b-fecac987ab3f | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
ecac3bbe-09ab-5e20-8ec0-415bbe6fcc59 | date | Pour Date
698662c8-5553-477e-803a-67afc8f5d891 | checkpoint | CONCRETE TEST Procedure
c0211cef-5576-481c-ab3c-4108c97f89b3 | checkpoint | APPROVAL FROM ENGINEER
1cb50425-259e-4025-96c0-b22350bd5cbc | section | Other Arrangements
b91bdc48-8e4c-4b4d-940e-fae731913b6c | checkpoint | Concrete surface Finish Requirement arranged
097bac67-ec30-52ae-80e2-7f9bfaaa8a2b | dropdown | Finish: | Fine finish,Broom finish
ecaa9713-37ca-439d-860d-6447c6cfcf81 | checkpoint | Curing Procedure arranged
f1ff59d2-e92f-48ac-923c-fd94d4ba0190 | checklist | Installers Checklist - Type A - Bridge Plank |  | Installers Checklist - Type A - Bridge Plank
8d8785cc-d4d1-42c7-a954-2a91c6b83a70 | section | Job Approval Documents/Construction Documents
91a5e5f8-51b4-4b52-bc2f-b6c0c64d081c | checkpoint | Complete Material "Bucket List"
c1cf8222-50ac-4471-83c1-77ade719cede | checkpoint | Eye Anchor - 2.5T - 04
328fa9b6-bc3a-4fbb-9dc0-8ac74fc90831 | checkpoint | Ferrules - M20 x 96mm - 10
3f0e305b-7c59-4481-a1ad-7a1874b99440 | checkpoint | ID Plate
e006bcc4-86a9-52c6-a6a6-983a86ff11d9 | textbox | ID:
ed363339-8368-4677-a0b8-baee01f6241e | section | Pre-Pour Check Approvals
51724f83-f241-4180-9add-828e2c9c8ab9 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
94cb307b-67c9-454e-9680-dc55bb7ca4f6 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
7df0f039-e646-4257-b01e-5d27aa0bf170 | checkpoint | Temporary Fix ID Plate to Formwork
67c8ff0c-9974-470d-91f4-653b251b19d6 | checkpoint | Double Check the Ferrule placement -Type A
029a9b32-3a41-46c5-9eae-bb764aecffc7 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
1bad8993-53c4-4a89-81bb-e1230b834683 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
02822a3a-0b1d-5830-badf-c2ceba7a3ff4 | tickbox | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
77e3fb78-d4d1-5fab-b800-17ea54134edc | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
d7634a29-a894-4976-8c9d-958929373acf | checkpoint | Concrete cover Check - minimum 30mm
996bac04-0979-4f99-90ca-06c606cc987c | section | Quality Assurance
27719087-63d7-43bc-8d7a-5225f119a1cc | checkpoint | QA - Final Check of ALL measurements
edf88064-186b-4f68-a11c-7adc449d3e53 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
312ef315-934a-4629-ba85-56926c58f608 | checkpoint | QA - Concrete mixdesign ,variations%, adjustments%, mix time
d62289b3-8945-4011-9730-4be14c67736b | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
0cfff897-1738-50a1-9b5b-9a80c3063a5b | date | Pour Date
ae241a31-1e20-4f5c-bcc1-c1670ba1e22a | checkpoint | CONCRETE TEST Procedure
14e7bdb2-4f11-4621-8f77-569ad62769d1 | checkpoint | APPROVAL FROM ENGINEER
cf1e6f4a-37a3-454b-abbc-24cab69e6eff | section | Other Arrangements
626b58c1-f655-431e-ac1d-136a579f95bb | checkpoint | Concrete surface Finish Requirement arranged
13f45495-0501-5cc4-a055-17a61b4ba810 | dropdown | Finish: | Fine finish,Broom finish
05dfa57f-234f-41b7-b6f2-b9fc97fe2945 | checkpoint | Curing Procedure arranged
a2d63f74-e22e-4d41-88ca-60ec56b3ede6 | checklist | Installers Checklist - Type B - Bridge Plank |  | Installers Checklist - Type B - Bridge Plank
5bb0aa9e-5882-43c2-be29-2e60472bce09 | section | Job Approval Documents/Constrction Documents
0e752854-76ed-4872-9b02-2bd161064490 | checkpoint | Complete Material "Bucket List"
23c23d75-101d-400a-8f11-9d22c7c124b6 | checkpoint | Eye Anchor - 2.5T - 04
aa131e09-899d-4465-9b50-d124adcaafae | checkpoint | Ferrules - M20 x 96mm - 10
1602283e-b582-461c-9967-6475771fca4a | checkpoint | ID Plate
451f9195-d2f1-5269-bb3d-4d670d7eaa24 | textbox | ID:
36d1b1ed-bc09-40d9-b018-2a203752999a | section | Pre-Pour Check Approvals
ce3f9d99-476c-4498-b96b-2a6b9c333f61 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
e964ebc4-19e7-4f16-a47e-f88f6c252bdd | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
44890ecf-2310-4b4b-87db-dda8b307a7a4 | checkpoint | Temporary Fix ID Plate to Formwork
d086d510-6ab0-4ac3-b599-74d6c51d286f | checkpoint | Double Check the Ferrule placment -Type B
53707dfb-94d2-4b21-a5ad-44e77e8255d2 | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
9d6c7883-82f5-44cb-af96-630b78d04ae3 | checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check
f45e9511-df20-539f-8ee1-c1cb3d0f3e9f | tickbox | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
07eb43d8-7b08-5666-a56e-ae81cfab4a84 | tickbox | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
9f745f55-9bd2-4e69-aa26-40778313da4b | checkpoint | Concrete cover Check - minimum 30mm
125e02a6-d95d-4a12-b67d-1eb334caf6e4 | section | Quality Assuarance
4a1e8f39-b900-445b-ac9e-16f67bf076a4 | checkpoint | QA - Final Check of ALL measurerments
5a022578-8d8f-46d2-a474-d8fc0fd927a0 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
ca94d541-38a9-4e93-926e-0d6d27458347 | checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
4f138540-97c0-40cb-89d7-abadf8d19cfe | checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
259194bd-567e-50d0-8305-ff54f28fc65c | date | Pour Date
3d5e2eff-5d5d-4db8-8314-c19eb856c2db | checkpoint | CONCRETE TEST Procedure
2bb73650-58da-4039-b3d8-5c751bb4105f | checkpoint | APPROVAL FROM ENGINEER
8a00c29f-a615-42e1-abde-d9f5667aaead | section | Other Arangments
d0f9042f-1d35-43a9-92fb-361d69f2db3d | checkpoint | Concrete surface Finish Requirment arranged
781c184f-87c8-55b2-bdc2-7b836f465610 | dropdown | Finish | Fine finish,Broom finish
1c93dc66-79f6-41e3-842a-17f62842eb3c | checkpoint | Curing Procedure arranged
ec085513-9b49-4a00-a4a9-2a7f1b90d683 | checkpoint | Curing Procedure arranged
0b15510d-9855-4b66-939d-43f633841f70 | checklist | Installers Checklist - Upper Wall - AA |  | Installers Checklist - Upper Wall - AA
c4f49dbc-3daa-48f4-8c15-b655b3481faf | section | Job Approval Documents/Construction Documents
5e8efe5f-2754-4f9e-bef5-b080c1b5a854 | checkpoint | Complete Material "Bucket List"
f02ad93f-0ffd-45eb-a854-a211f52e11ae | checkpoint | Eye Anchor - 2.5T(170mm) - 04
5f3da2db-939d-4e76-85c5-04d3f26a8076 | checkpoint | ID Plate
f63ee509-03a0-5361-bc02-861630ccebbe | textbox | ID:
6f42e1c4-e828-4281-9e9b-93506cdc1ffc | section | Pre-Pour Check Approvals
0fa1c72b-ede4-4c66-b929-5fae6cf958d0 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
5d5b800b-705c-4258-8f19-84c1173f20eb | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
f2d41c8b-44f4-4602-8d28-c35462beaa17 | checkpoint | Temporary Fix ID Plate to Formwork
9ccd106b-8c9f-405c-9bd2-dec5359860e6 | checkpoint | Double Check the Ferrule placement -Type AA
cdb12b92-d982-4c60-8d94-3d5f18c5e319 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
54557cdc-f2ce-440d-a804-039c9250a83b | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
944108e2-5325-51f5-989c-4532adad4c3a | tickbox | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
9c8d0885-f5c4-5342-9202-5dc7753c8ad3 | tickbox | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
15c7556e-4880-558d-a796-e4d9447f984f | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
6e21d74c-9b94-5417-9e9b-078ed6b76382 | tickbox | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
98e726af-501a-4440-8d05-09865c9acf13 | checkpoint | Concrete cover Check - minimum 30mm
eec9fccb-e516-4968-8b86-3eade3844547 | section | Quality Assurance
38f24f43-28ad-4d54-b4ad-171f52f5bfca | checkpoint | QA - Final Check of ALL measurements
93b10b50-6967-4a0b-8cf5-af6084c18c6b | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
9cc37284-ffd8-4cc5-a96a-c1d15707107d | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
ea921279-b3bc-452a-8e0f-0b18a24b1dde | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
6cd51751-856c-5558-9de1-73bf2356a4e5 | date | Pour Date
8785f46e-6584-4231-bcce-ef98c8188f27 | checkpoint | CONCRETE TEST Procedure
52315681-b659-4695-a52d-e3dc84743f44 | checkpoint | APPROVAL FROM ENGINEER
c0a9d242-dec8-471c-83dd-a2247d414f9c | section | Other Arrangements
80685aa8-bc0c-4687-afff-7ad0e5ac1554 | checkpoint | Concrete surface Finish Requirement arranged
3fbda68c-ee47-5d85-881b-d73ee6a31347 | dropdown | Finish: | Fine finish,Broom finish
9fc65137-0bc5-4786-b456-be78990be01e | checkpoint | Curing Procedure arranged
8bfc0eaa-8981-4ce2-95af-d4bb645c6da3 | checklist | Installers Checklist - Upper Wall - BB |  | Installers Checklist - Upper Wall - BB
5c2fca25-f5d7-424e-88cd-ae1b4e9e4a8e | section | Job Approval Documents/Construction Documents
d4623f4a-9d3a-400f-a914-2374b7161abb | checkpoint | Complete Material "Bucket List"
2f784f6b-599a-49b2-a7a1-bea88fce346e | checkpoint | Eye Anchor - 2.5T(170mm) - 04
b05c4604-c294-4bdb-92f5-7abe64f66ac0 | checkpoint | ID Plate
efa7e41c-4ee4-5229-ac68-95a2b6df1ed7 | textbox | ID:
4b75bbe5-2d88-4900-8c75-c99f638d1397 | section | Pre-Pour Check Approvals
74aef21f-2721-45d9-9909-d30f221bf74e | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
007a4b02-53b6-40c5-8746-5fa2fa940284 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
e1c8644a-ffd8-4d38-a7c6-f6ee01c3276a | checkpoint | Temporary Fix ID Plate to Formwork
8f86136f-b407-40c2-852e-75d51eee048c | checkpoint | Double Check the Ferrule placement -Type BB
720c729b-26ea-4b8d-92da-9d010adcc648 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
c2bd5f03-22a7-4aa0-a53f-a0b2f1d3290e | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
36c1cff6-d292-56a1-9aa4-21976b5b0f6a | tickbox | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
ac3fa825-a729-5965-96c7-969cef2a4bcb | tickbox | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
e8ceb3f9-e40b-5ecc-8daa-51122de5777e | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
297431d2-9ec7-5d90-9f67-06c707ecc198 | tickbox | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
242f3d3b-fdda-4416-9862-d11889fc6862 | checkpoint | Concrete cover Check - minimum 30mm
329fbe88-a8c0-4775-a2a5-27c67aff2136 | section | Quality Assurance
4fe630ff-8394-4a8a-bfd2-f4f2034c26b1 | checkpoint | QA - Final Check of ALL measurements
a52114b7-4750-4db7-a308-09bd8ff24e1e | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
bed8d4a6-3c5d-4b39-84aa-2fda88f602aa | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
5ba601ba-a70f-4d61-ba68-77c9916e14ee | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
c9160d16-32ee-5a92-a8fe-38d813cb657f | date | Pour Date
faaf0275-4eea-45ef-a76a-ee405086d72d | checkpoint | CONCRETE TEST Procedure
9ebf5ba8-951e-4eae-9d7c-177b55ac2f3f | checkpoint | APPROVAL FROM ENGINEER
8e535e35-e014-4818-a81d-8b5121faa8ec | section | Other Arrangements
dd6f85f0-181e-4d58-a368-f4fd606951ef | checkpoint | Concrete surface Finish Requirement arranged
4c4f8882-2501-52f3-afac-c6b0ac7144fb | dropdown | Finish: | Fine finish,Broom finish
8f8ccedf-c6c0-4a50-922c-b35c49ca0137 | checkpoint | Curing Procedure arranged
138f8e75-b2b6-40d2-ac37-1a54a150351d | checklist | Precast Components ITP |  | Precast Components ITP
473e6fe0-57b8-448f-be97-14a9c19949a6 | section | Documentations
67b0a6a8-47dc-46c5-a71e-5d898eb63e22 | checkpoint-no-value | Special Instructions
9a38b6e8-02b7-4744-be32-1d7d4dd70457 | checkpoint-no-value | Approved Shop Drawings
5c7f65b5-d014-5623-a585-7d254b4603ba | tickbox | 3.9m Wide Deck Type A Panels
3fa6ea81-d027-578d-a98e-6dff7da7c86a | tickbox | 3.9m Wide Deck Type B Panels
3c2e2b3e-1f30-5bbc-a5f0-c2fc9456a1bb | tickbox | Abutment AA
1ab3d042-5354-529e-bc5d-6cfb1527d8e0 | tickbox | 582mm Upper Wall to suit Abutment AA
02a4d307-1ce7-57f7-971f-fc92c82d40f2 | tickbox | Abutment BB
25b03ead-b86f-5fe3-b461-9b3e70087076 | tickbox | 776mm Upper Wall to suit Abutment BB
0f383942-1d1c-46d3-b37a-45a9dd4c8bd7 | checkpoint-no-value | Other
ae0c10b3-cbfb-49a9-95f6-cfc1f87c68b2 | section | Job Approval Documents/Construction Documents
c30f16d5-9a9e-44c9-8a4d-547ad4fae14d | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
364f702a-5e22-5295-9e20-3611731b576f | note | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
be59d7c2-680a-4064-9372-4fd583a51dad | section | Pre-Pour Check Approvals
3d4a3d95-cda7-4b9c-972e-860e6427159d | checkpoint-no-value | Formwork
595308dd-602f-4592-8a0a-ea9799cd05c6 | checkpoint-no-value | Reinforcement(Reo)
e9a8fa5b-b3bd-455c-87b8-58181ccd2b02 | checkpoint-no-value | Embedded Items and their placement
0bf4a217-3fd2-4860-9f03-249c40e25db8 | checkpoint-no-value | Lift Procedure
f20a6938-cc2a-4e86-8c36-599b2a7a39de | checkpoint-no-value | Concreting (mix design
c6b79412-330b-40ac-bcf6-b413f2428675 | section | Test on Concrete (requests and approvals)
b404e1d7-ea69-4510-b9e7-d629cf757251 | checkpoint-no-value | Request From Client
89132d05-46c6-41c5-b518-078151ec8dfe | checkpoint-no-value | Test schedule and Test Results