## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
138f8e75-b2b6-40d2-ac37-1a54a150351d | checklist | Precast Components ITP |  | Precast Components ITP
473e6fe0-57b8-448f-be97-14a9c19949a6 | section | Documentations
67b0a6a8-47dc-46c5-a71e-5d898eb63e22 | checkpoint-no-value | Special Instructions
9a38b6e8-02b7-4744-be32-1d7d4dd70457 | checkpoint-no-value | Approved Shop Drawings
5c7f65b5-d014-5623-a585-7d254b4603ba | tickbox | 3.9m Wide Deck Type A Panels
3fa6ea81-d027-578d-a98e-6dff7da7c86a | tickbox | 3.9m Wide Deck Type B Panels
3c2e2b3e-1f30-5bbc-a5f0-c2fc9456a1bb | tickbox | Abutment AA
1ab3d042-5354-529e-bc5d-6cfb1527d8e0 | tickbox | 582mm Upper Wall to suit Abutment AA
02a4d307-1ce7-57f7-971f-fc92c82d40f2 | tickbox | Abutment BB
25b03ead-b86f-5fe3-b461-9b3e70087076 | tickbox | 776mm Upper Wall to suit Abutment BB
0f383942-1d1c-46d3-b37a-45a9dd4c8bd7 | checkpoint-no-value | Other
ae0c10b3-cbfb-49a9-95f6-cfc1f87c68b2 | section | Job Approval Documents/Construction Documents
c30f16d5-9a9e-44c9-8a4d-547ad4fae14d | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
364f702a-5e22-5295-9e20-3611731b576f | note | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
be59d7c2-680a-4064-9372-4fd583a51dad | section | Pre-Pour Check Approvals
3d4a3d95-cda7-4b9c-972e-860e6427159d | checkpoint-no-value | Formwork
595308dd-602f-4592-8a0a-ea9799cd05c6 | checkpoint-no-value | Reinforcement(Reo)
e9a8fa5b-b3bd-455c-87b8-58181ccd2b02 | checkpoint-no-value | Embedded Items and their placement
0bf4a217-3fd2-4860-9f03-249c40e25db8 | checkpoint-no-value | Lift Procedure
f20a6938-cc2a-4e86-8c36-599b2a7a39de | checkpoint-no-value | Concreting (mix design
c6b79412-330b-40ac-bcf6-b413f2428675 | section | Test on Concrete (requests and approvals)
b404e1d7-ea69-4510-b9e7-d629cf757251 | checkpoint-no-value | Request From Client
89132d05-46c6-41c5-b518-078151ec8dfe | checkpoint-no-value | Test schedule and Test Results
| section | Transport 01
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 02
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 03
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 04
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Other Documentations
| checkpoint | Special Instructions
| checkpoint | Other
| section | Installation
| checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
| checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
| bool | Set out
| bool | Core Holes
| bool | Install dowels
| checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
| checkpoint | Grouting and sealing
| checkpoint | Remove back propping when instructed by consulting Engineers.
| section | Final Inspection
| checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.