## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d011e28d-2c17-4443-a270-04997073db5a | checklist | Precast Components ITP |  | Precast Components ITP
783771d0-c2b2-488d-a4a3-d58224f6bd61 | section | Documentations
f43bd42b-7590-4257-9475-e23ec8daf31e | checkpoint-no-value | Special Instructions
a544f2d8-2b00-4464-91af-2e7271df1a1e | checkpoint-no-value | Approved Shop Drawings
8977bede-1b3b-5ff1-81a0-9bf0fd4515d7 | tickbox | 4.2m Wide Deck Panels (DP)
f82ae150-ff2c-5831-8c5f-f3b207b369f1 | tickbox | Abutment Base (UB)
4bc8326d-1bf0-51a3-a2bc-97fd6413c9ed | tickbox | Upper Wall (UW)
56d12bdc-585f-470c-9c37-fa342597b96f | checkpoint-no-value | Other
af310717-4588-48ed-94e5-759636a20819 | section | Job Approval Documents/Construction Documents
e9b1236c-8bf0-4e4e-8084-212b68f6af3d | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
775dfaba-fce5-47ec-8e64-91f8a3385917 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
d3ac69d7-b1f5-4a48-8c0e-6cdc00880c0f | section | Pre-Pour Check Approvals
10026e6a-9486-4e85-a7aa-623584d64b2b | checkpoint-no-value | Formwork
a121587b-542a-4e69-a608-659cbd6abf83 | checkpoint-no-value | Reinforcement(Reo)
6d5d664d-2f64-487f-9073-d0988f9162db | checkpoint-no-value | Embedded Items and their placement
acaa1a9a-9306-44b4-ba2b-563e972a6d58 | checkpoint-no-value | Lift Procedure
9a7d48d5-e4f3-47f5-aaea-9436c8487359 | checkpoint-no-value | Concreting (mix design
cbf3fee1-9f75-4f58-be91-df9b0e8308f4 | section | Test on Concrete (requests and approvals)
3d3a0a14-399b-48b6-8356-f96b52d27e78 | checkpoint-no-value | Request From Client
ab638037-015f-47c4-ae68-32c9df956f45 | checkpoint-no-value | Test schedule and Test Results
| section | Transport 01
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 02
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 03
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 04
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Other Documentations
| checkpoint | Special Instructions
| checkpoint | Other
| section | Installation
| checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
| checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
| bool | Set out
| bool | Core Holes
| bool | Install dowels
| checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
| checkpoint | Grouting and sealing
| checkpoint | Remove back propping when instructed by consulting Engineers.
| section | Final Inspection
| checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.