## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
8aaed07e-41e5-47e6-8428-cb2c4f9651b3 | checklist | Precast Components ITP |  | Precast Components ITP
649eac7a-24a1-484f-ab50-2488c5886339 | section | Documentations
0d6793bc-979e-4495-aed1-7009f5567ff2 | checkpoint | Special Instructions
700122c6-bd2e-4a57-89e3-ea6a36265a39 | checkpoint | approved Shop Drawings
5783a3ed-ca37-5ca3-99cb-f0bdb004ca99 | tickbox | 4.2m Wide Deck Panels (DP)
8606427c-7be6-50c7-8195-dcc2b888bf05 | tickbox | Abutment Base (UB)
c2a8de1a-d7b9-5087-abc9-cd426dfe22be | tickbox | Upper Wall (UW) 684mm
21e047e8-c28f-43bc-9544-a15311a0e425 | checkpoint | Other
231a8077-50bc-4970-a0e8-3b6a15000c4d | section | Job Approval Documents/Construction Documents
7ea9af7d-604a-43ef-a48e-5232e0961b9e | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
df4610a7-d3be-4a48-95e3-cba86be85095 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
b62fc6da-ee86-4c15-be3d-049a0d2e7b78 | section | Pre-Pour Check Approvals
29da24d5-2969-4863-8757-42254ce1d6c2 | checkpoint | Formwork
da9403aa-8765-4802-857e-42ce41ca92ba | checkpoint | Reinforcement(Reo)
4e39489e-e8a0-4c1d-8b32-5aad8998f74c | checkpoint | Embedded Items and their placement
6d64ad74-f629-4c94-aef3-721b7c278d42 | checkpoint | Lift Procedure
2c69c0b3-daa6-45ca-9d5f-3767830e6d02 | checkpoint | Concreting (mix design
7892ef4f-78df-4d74-ad47-14e82d68959c | section | Test on Concrete (requests and approvals)
1afdebd5-065e-428c-b8c9-d429f5b6f84c | checkpoint | Request From Client
c8b41490-f07d-4f81-98f8-c87fc6c13992 | checkpoint | Test schedule and Test Results
| section | Transport 01
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 02
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 03
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Transport 04
| checkpoint | Any Lifting, Loading, Transport Instructions from Client
| checkpoint | Transport Vehicle Approvals
| checkpoint | Ensure loads are glutted correctly and chains are over gluts.
| section | Other Documentations
| checkpoint | Special Instructions
| checkpoint | Other
| section | Installation
| checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
| checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
| bool | Set out
| bool | Core Holes
| bool | Install dowels
| checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
| checkpoint | Grouting and sealing
| checkpoint | Remove back propping when instructed by consulting Engineers.
| section | Final Inspection
| checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.