## Project Structure
Folder Structure |  |  |  | Checklists
Site QA
Building A
|  | Ground Floor | Lobby | Plastering & Hebel
|  |  | G01 | Plastering & Hebel
|  |  | G02 | Plastering & Hebel
|  |  | G03 | Plastering & Hebel
|  | Level 1 | Corridor | Plastering & Hebel
|  |  | 101 | Plastering & Hebel
|  |  | 102 | Plastering & Hebel
|  |  | 103 | Plastering & Hebel
|  |  | 104 | Plastering & Hebel
|  | Level 2 | Corridor | Plastering & Hebel
|  |  | 201 | Plastering & Hebel
|  |  | 202 | Plastering & Hebel
|  |  | 203 | Plastering & Hebel
|  |  | 204 | Plastering & Hebel
|  | Level 3 | Corridor | Plastering & Hebel
|  |  | 301 | Plastering & Hebel
|  |  | 302 | Plastering & Hebel
|  |  | 303 | Plastering & Hebel
|  |  | 304 | Plastering & Hebel
|  | Level 4 | Corridor | Plastering & Hebel
|  |  | 401 | Plastering & Hebel
|  |  | 402 | Plastering & Hebel
|  |  | 403 | Plastering & Hebel
|  |  | 404 | Plastering & Hebel
|  | Level 5 | Corridor | Plastering & Hebel
|  |  | 501 | Plastering & Hebel
|  |  | 502 | Plastering & Hebel
|  |  | 503 | Plastering & Hebel
|  | Level 6 | Corridor | Plastering & Hebel
|  |  | 601 | Plastering & Hebel
|  |  | 602 | Plastering & Hebel
|  |  | 603 | Plastering & Hebel
|  | Level 7 | Corridor | Plastering & Hebel
|  |  | 701 | Plastering & Hebel
|  |  | 702 | Plastering & Hebel
|  |  | 703 | Plastering & Hebel
|  | Level 8 | Corridor | Plastering & Hebel
|  |  | 801 | Plastering & Hebel
|  |  | 802 | Plastering & Hebel

## Checklists
Type | Name | Values
Checklist | Plastering & Internal Hebel
Section | Framing
Checkpoint | All frames/studs set out correctly
Checkpoint | All frames plumb and square
Checkpoint | Fix to structural members
Checkpoint | All window and sliding door openings are as per plan and line up with above elements.
Checkpoint | Nogging all installed correctly
Checkpoint | Door frames fixing
Checkpoint | Studco Supplier inspection (Provide report to builder)
Section | Internal Hebel wall
Checkpoint | Angle/sarking/top hats in place
Checkpoint | Hebel panel alignment
Checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
Checkpoint | Ensure hebel panels are in full and not cracked
Checkpoint | Ensure control joints have been installed in accordance with manufacturers specifications and installation guide
Checkpoint | Panels finish (patches done)
Checkpoint | Fire-rated caulking and sealing
Checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)
Section | Plasterboard for Walls
Checkpoint | Ply nogging
Checkpoint | Rough-in sign off
Checkpoint | Insulation installed as per AS/BCA
Checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
Checkpoint | Villaboard/WR to wet areas ONLY
Checkpoint | Plasterboard Lining to be installed as wall set out plan
Section | Plasterboard for Ceiling
Checkpoint | Confirm ceiling height
Checkpoint | Confirm access panel location
Checkpoint | Ceiling frame work
Checkpoint | Ceiling bulkheads where required
Checkpoint | Pelmets
Checkpoint | Ceiling insulation as per AS/BCA
Checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
Checkpoint | Ceiling plasterboard lining
Section | Setting & Sanding
Checkpoint | Angle/LB/P50 install
Checkpoint | First coat setting
Checkpoint | Second coat setting
Checkpoint | Final coat setting
Checkpoint | Sanding
Checkpoint | patching
Checkpoint | Defects
Checkpoint | Final Inspection