## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Plastering & Internal Hebel
section | Framing
checkpoint | All frames/studs set out correctly
checkpoint | All frames plumb and square
checkpoint | Fix to structural members
checkpoint | All window and sliding door openings are as per plan and line up with above elements.
checkpoint | Nogging all installed correctly
checkpoint | Door frames fixing
checkpoint | Studco Supplier inspection (Provide report to builder)
section | Internal Hebel wall
checkpoint | Angle/sarking/top hats in place
checkpoint | Hebel panel alignment
checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
checkpoint | Ensure hebel panels are in full and not cracked
checkpoint | Ensure control joints have been installed in accordance with manufacturers specifications and installation guide
checkpoint | Panels finish (patches done)
checkpoint | Fire-rated caulking and sealing
checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)
section | Plasterboard for Walls
checkpoint | Ply nogging
checkpoint | Rough-in sign off
checkpoint | Insulation installed as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Villaboard/WR to wet areas ONLY
checkpoint | Plasterboard Lining to be installed as wall set out plan
section | Plasterboard for Ceiling
checkpoint | Confirm ceiling height
checkpoint | Confirm access panel location
checkpoint | Ceiling frame work
checkpoint | Ceiling bulkheads where required
checkpoint | Pelmets
checkpoint | Ceiling insulation as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Ceiling plasterboard lining
section | Setting & Sanding
checkpoint | Angle/LB/P50 install
checkpoint | First coat setting
checkpoint | Second coat setting
checkpoint | Final coat setting
checkpoint | Sanding
checkpoint | patching
checkpoint | Defects
checkpoint | Final Inspection