## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 77f9ea35-4980-4375-a768-cf7f202c8b07 |  | checklist | Water Stacks Checklist |  |  |  |  | Yes | Water Stacks Checklist | 04ad76d6-976f-44f0-9247-192f6f8b6ef2
checkpoint-status | c42ddac3-2dc7-45de-a9ea-29fed2d4d106 |  | checkpoint | Tested To 1500Kpa
checkpoint-status | 3794ce26-27b5-4a75-8ce8-3869e03b9fd6 |  | checkpoint | Pipe Labels Attached
checkpoint-status | 9183f39e-f4ba-49bf-b7d0-4fd084fe5553 |  | checkpoint | Lagging Of Hot Pipes
checkpoint-status | 9cc93952-3906-40ec-9cc7-3998986252ea |  | checkpoint | Water To Be Kept In Pipes To Avoid Corrosion
checklist-flat | d187f536-73b4-4b6a-9ebf-75a8689f9fb5 |  | checklist | Drainage Checklist |  |  |  |  | Yes | Drainage Checklist | 0c9e41b3-3946-4ce5-8614-f1585025b89a
checkpoint-status | d9332a98-8d00-4745-bb69-4a1ac9810738 |  | checkpoint | Is Pipe Sitting On Bedding
checkpoint-status | 4574df79-a074-4fe5-b4b8-6e3080e2ac5b |  | checkpoint | Is Pipe Installed To Correct Falls On Plan
checkpoint-status | 41b49ec1-76d1-4688-8145-34ce72fc62ce |  | checkpoint | Has Pipe Been Photographed For Q + A
checkpoint-status | 787c19ee-25e3-41fe-a654-510b950abf7a |  | checkpoint | Is Pipe Free From Debree
checkpoint-status | 8a6a5d24-58e7-4d1f-a802-409453d10d67 |  | checkpoint | Has Fines Been Installed On Top Of Pipe
checklist-flat | e0cfb38f-0ceb-4fb1-a8c3-c0162ea1bbdf |  | checklist | ORG Checklist |  |  |  |  | Yes | ORG Checklist | 0d60e486-a414-4e52-8a84-18b4e77904dc
checkpoint-status | 3f8667c8-5fd1-4faf-b8c1-ea5b5346d794 |  | checkpoint | Installed in correct location
checkpoint-status | f7c79593-6932-4c7b-bff6-76a78bfdf5e2 |  | checkpoint | Riser level
checkpoint-status | c7dafece-e1ce-4dec-b491-ecd74b7e3388 |  | checkpoint | Is the ORG fixture connection done
checkpoint-status | 53fdab57-f886-45d4-97cb-f3c8eee5808e |  | checkpoint | Concrete placed under the gully base
checkpoint-status | 5cd90489-9ae1-4404-93a7-71d77cc40138 |  | checkpoint | Gully dish installed
checklist-flat | 2709214a-8129-4dcd-9f5d-cda03182cb63 |  | checklist | Stacks + Vents Checklist |  |  |  |  | Yes | Stacks + Vents Checklist | 11ae5511-95d0-4442-976a-872129389149
checkpoint-status | 9d0a8f3c-3e81-4a64-b147-e566d374414d |  | checkpoint | Inspection Junction Installed For Testing
checkpoint-status | c3d0e5fd-38c4-4d6d-82d8-3fb8b1bdd7d6 |  | checkpoint | Pipe Labels Installed
checkpoint-status | 273fd2e9-fd44-4a27-a5b7-32da54f02d80 |  | checkpoint | Mid Level Supports
checkpoint-status | 24637038-e8ba-4e51-ba4a-7e993f18ec69 |  | checkpoint | Write On Test Cap Date Of Test
checklist-flat | 8fe8b449-8979-4961-92da-de52e378931c |  | checklist | Pressure Testing Checklist |  |  |  |  | Yes | Pressure Testing Checklist | 13a4aaa3-8c5a-4c4a-82a9-61e2b6d761df
checkpoint-status | 0bcf44e5-92d4-4001-99f0-e3b2d9a1a34e |  | checkpoint | Pump Up To 1500kpa Minimum
checkpoint-status | 86fb3812-0ec9-4e73-b297-fbe4cbc70cd8 |  | checkpoint | Take Photos Of Testing
checklist-flat | 8ca9df6e-7de0-4991-971d-855ae1ab8b7c |  | checklist | Acoustic Lagging Checklist |  |  |  |  | Yes | Acoustic Lagging Checklist | 14792213-3790-4bcb-8b69-c6cfc7d306b5
checkpoint-status | 0fbc11a1-6825-4d11-b631-b935a6967913 |  | checkpoint | Relevant Pipework Lagged
checkpoint-status | a9a227df-e437-49e4-86a4-a4cb9c16761d |  | checkpoint | Lagging Tape Around Joints
checkpoint-status | 7fbcf8ab-d9ac-49a5-bf2a-ff6c83ff6509 |  | checkpoint | Blue Strapping And Buckles Every 1 Metre
checkpoint-status | d816c033-f122-417d-b617-098b1654528d |  | checkpoint | Pipe Labels After Lagging
checklist-flat | e29e63e0-3c03-4aa2-ae28-7ac81ffcdb33 |  | checklist | Downpipes + Decks Checklist |  |  |  |  | Yes | Downpipes + Decks Checklist | 1530eb08-9336-4007-b739-7a084ce92480
checkpoint-status | 2ff27f92-c8a1-461d-a533-842dba83b2f7 |  | checkpoint | Flanges Installed
checkpoint-status | 28556c65-c75b-4b03-aad6-33b2a1f37223 |  | checkpoint | Domes Installed
checkpoint-status | 87fadb6f-1bf9-4aca-96e4-583fa93eb63a |  | checkpoint | All Through Installed
checklist-flat |  |  | checklist | Express Plumbing Quality Assurance checks and Commissioning |  |  |  |  | Yes | Express Plumbing Quality Assurance checks and Commissioning | 23e1da25-ee3e-480b-94cd-3a143799e533
checkpoint-no-status |  |  | checkpoint | Express Plumbing Quality Assurance checks and Commissioning
label | 8cd63223-b1f3-4f34-9910-335b9309577d |  | note | Express Plumbing uses a online live document system of recording different stages of the construction process through out the build program. With the aid of mobile devices and computers we record with photographic evidence the construction build process, what things look like behind walls and below ground. We follow up these photos with the end product finish and have checkpoints for each fixture to have passed off at each stage so you can be assured of the quality Express Plumbing has archived during your project.
label | 82789061-d20c-448c-bc72-280d357bafaa |  | note | The system provides a accurate recording of what has happened on site and also provides a means of recording and resolving any defects. During checkpoint sign offs for each fixture a series of questions are asked in relation to the fixture, ie “are the pipes coming out of the wall straight?” or “Has the council inspection been passed?”. If the Express Plumbing site supervisor finds a defect he is able to send a job request immediately to any of his site staff and the repairing staff member is able to take a photo of his repair for the supervisor to approve.
label | 8ecd6366-fa14-4fd0-bd07-51f74df937c9 |  | note | All dates and time of data entered or altered are recorded next to each question. Our commissioning processes also forms part of this live document with specific fixture questions and photos during the commissioning being recorded i.e. temperature gauge photo of a running hot tap on a basin etc. We are also able to provide our Fire Register through the same system and record locations with the labels and assign a photo of each penetration to that location. We also break down the locations into areas and floors.
label | de6f5e10-f8f4-436f-a7e4-27ed61710029 |  | note | As built are also recorded during the project and are loaded into the system before the hole or ceiling is covered in. These can be on request turned into any format you may wish to have these sent to you (there may be additional costs).
label | f17d3ffd-0b01-489a-92fb-6de7fea2e7ec |  | note | Express Plumbing supervisor’s are authorised and given access to the specific job they may be running. Access is only given through Web page authorisation from the Express Project Management team. On site teams under the supervisor do not have full access to the system and can only log repairs to defects with in the system. All on site data entry, passing off of fixture, logging of finished works, fire register recording and As built entry may only be preformed by the authorised Express Plumbing Site Supervisor.
checkpoint-no-status |  |  | checkpoint | QA Hierarchy Flow Chart
text | f3083c51-d697-4f21-a7e7-216ef499e346 |  | textbox | Project Manager:
text | a10cba99-d8df-472c-9941-6d0e90e16089 |  | textbox | Site Supervisor:
text | f61c7730-cb04-4122-91d4-98b506629bfa |  | textbox | Site Defect Repairer:
checklist-flat | 66bb6713-8622-4950-8f34-cc40a5051213 |  | checklist | First Fix |  |  |  |  | Yes | First Fix | 25faeb2a-413e-466c-8a46-1ac0b08fd66b
checkpoint-status | b8edd2f1-486c-4df2-bd84-52a7033885b0 |  | checkpoint | Is the correct material used, as specified for the job?
checkpoint-status | 9b20a4c6-c44d-4573-8cc6-2e398cbbb3a8 |  | checkpoint | Wing back installed at correct location and height, prior to hardware installation?
label | 277b8239-a5a7-528e-89e4-c97a24371013 |  | note | According to manufacturer specs and architecture design
checkpoint-status | f986e600-5e70-4452-a180-06c1088e2882 |  | checkpoint | Pipework is secured/supported or protected if required
label | ee05f921-7d82-5123-9a97-ffc1b5e5591f |  | note | Min interval 600mm
checkpoint-status | 936564d9-f06f-4426-968f-5f8f5a97e9d0 |  | checkpoint | Is the pipe work tested according to hydrostatics pressure of 1500 kpa for a period of no less than 30 min?
label | bcbd2723-98b2-5db8-8265-c7471135c617 |  | note | Take picture for proof
checkpoint-status | 9c5604a3-9889-4999-a730-ba041595a9fc |  | checkpoint | Waste at correct height and location?
label | 5e8a54aa-eecb-50b1-8d8a-d783b1aa43e8 |  | note | According to fixture manufacturer specs and architecture design
checkpoint-status | a48073c2-a6b4-44f1-b06b-cf4dfeb44fc9 |  | checkpoint | Additional Comments
checklist-flat | 76382d06-50f8-4828-be48-c544d8732521 |  | checklist | Pressure Testing Checklist |  |  |  |  | Yes | Pressure Testing Checklist | 31070fff-4c5a-4944-b7cf-9ee4e8c18e31
checkpoint-status | e9903af3-e90d-4ef3-9c01-4cd5229ad820 |  | checkpoint | Pump Up To 1500kpa Minimum
checkpoint-status | 25f81b62-76d1-4332-902f-12245dc4a2d5 |  | checkpoint | Take Photos Of Testing
checklist-flat | a20e68e3-7eb9-4a4b-9030-61b18ae528c5 |  | checklist | Cesspit |  |  |  |  | Yes | Cesspit Checklist | 310a61b8-17ce-43da-869c-b085cd7649cd
checkpoint-status | 494bdc57-4e33-46e9-a62c-0e87c23ca4e0 |  | checkpoint | Is the sump set on correct LL
checkpoint-status | 526d8dde-c8a8-46d2-90f6-d412dd03cab6 |  | checkpoint | Installation Process
checkpoint-status | a7212117-10b5-4a9b-a978-6d427e879dfc |  | checkpoint | Council Inspection and As-Built
checklist-flat |  |  | checklist | First Fix |  |  |  |  | Yes | Add FF | 316290d5-750a-4ddd-9ef8-49ad46e4c823
checkpoint-status |  |  | checkpoint | Is the fixture in the right position?
checkpoint-status |  |  | checkpoint | Are pipes coming out the straight?
checkpoint-status |  |  | checkpoint | Are fixings nogs correct?
checkpoint-status |  |  | checkpoint | Has the pipework been tested?
checklist-flat |  | checklist-flat is not dependant but can't have own status | checklist | Pipework Test sheet |  |  |  |  | Yes | 10) Add Pipework Testsheet | 3d4a1589-7f25-45bf-ad5c-210bd51b0eb1
checkpoint-no-status |  |  | checkpoint | Flush – All pipework installs to be flushed for minimum of 2 minutes on full with maximum pressure available.
text | 0d3459c4-33fc-42a1-b3aa-77e602df24c9 | Hidden property width:100 | textbox | Duration
text | a533b7cb-15d7-4f7e-bed9-fb71fe8f2e28 | Hidden property width:100 | textbox | Free Flowing
checkpoint-no-status |  |  | checkpoint | Drop Test – Pipework to be subjected to a drop test. No less than 3 drops. Test is used to confirm pipework will withstand environmental extremes.
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
checkpoint-no-status |  |  | checkpoint | Hydro static test – Pipework to be subjected to a hydrostatic test for no less than 30mins. Record pressure drop if any. Acceptable drops are allowed if within manufacturers allowances.
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checklist-flat |  |  | checklist | Meter Commissioning Report |  |  |  |  | Yes | Meter Commissioning Report | 4820f8d3-a314-4e59-af88-69ba99f03103
checkpoint-status |  |  | checkpoint | Is water meter installed according to IFC and is water live?
text | cac4f757-710a-4f17-9f4f-e12fe4ff9121 |  | textbox | Water meter reading at handover:
text | d803dc8a-ecb6-42ce-8759-9378589b3cd1 |  | textbox | Water meter size:
text | b8c03996-55b7-41c8-84d5-60a560ab574e |  | textbox | Water meter asset number:
text | 1c20080e-fca3-41b2-84a0-341f39794071 |  | textbox | Water meter serial number:
checkpoint-status |  |  | checkpoint | Is gas meter installed according to IFC and is water live?
text | c2fa59eb-8248-4731-b179-7bda6945f375 |  | textbox | Gas meter reading at handover:
text | 62725d7b-5058-4062-bab3-2e83930b6601 |  | textbox | Gas meter size:
text | 553dc1e7-50bc-4834-86f7-69aecf8e12dd |  | textbox | Gas meter asset number:
text | ecb1be83-ab77-4686-9441-a0b928525daf |  | textbox | Gas meter serial number:
checklist-flat | ec773b50-f0a2-4290-83b2-8702ff4c8658 |  | checklist | Storm-Filter |  |  |  |  | Yes | Storm-Filter | 4e17ce65-03f9-4c3d-a8ae-eb8daf63b8b3
checkpoint-status | 5f2d3296-7672-4c09-ae4d-eace6adfce0a |  | checkpoint | Bedding Put In At Correct Height
checkpoint-status | c9cad9bc-d9e5-443b-a941-c479201efa25 |  | checkpoint | Grade Right
checkpoint-status | 2c7f9a60-b82c-48a4-b582-6fd3d082a4de |  | checkpoint | Check Pipes Is All The Way In
checkpoint-status | 617e8d68-fbe6-4438-9f93-beac018d4827 |  | checkpoint | As Laid Per Plans
checkpoint-status | 379e2acb-2b09-4952-9e07-5590253b34a7 |  | checkpoint | Filter Clear Of Debris
checkpoint-status | f63b1598-c4ba-43c5-8cc5-1c3522a9b893 |  | checkpoint | Lid Set To Finished Floor Level
checklist-flat |  |  | checklist | Miscellaneous Test Sheet |  |  |  |  | Yes | Miscellaneous Test Sheet | 4e503bc5-80db-4b48-8543-c02c7a23f144
checkpoint-status |  |  | checkpoint | Miscellaneous test sheet
checklist-flat | 6d291091-f9ec-4b0c-8617-f43be215e20f |  | checklist | Toilet Checklist |  |  |  |  | Yes | Toilet Checklist | 4ef5dd62-a151-4ebd-a1d4-d69583160a99
checkpoint-status | 258eb4a1-5b46-4aec-b022-f3f95415fcd4 |  | checkpoint | Wingback Installed To Correct Height
checkpoint-status | 5de4c74a-713b-4282-8235-6bae5867d1ce |  | checkpoint | Waste Installed Correct Distance From Wall
checklist-flat |  |  | checklist | Aquatherm Pressure Test Sheet |  |  |  |  | Yes | Aquatherm Pressure Test Sheet | 517470d5-a8ed-4240-8b60-f41bf08a2c50
checkpoint-status |  |  | checkpoint | Installation Details
button | 93fc2cce-4a6e-4a48-a85b-8e9dac04a136 |  | button | Type of Installation | Commercial,Domestic
select | 0891b48d-28be-4564-8cd2-765c1aac9253 |  | dropdown | Type of Pipe: | Aquatherm blue pipe,Aquatherm green pipe,Aquatherm grey pipe,Aquatherm lilac pipe,Aquatherm orange system,Aquatherm red pipe
text | 44d0058f-38ed-4e3c-905f-383f77f9f640 |  | textbox | Time Testing Started:
text | 25abef4f-adca-4bf1-9248-cc84663ac6f8 |  | textbox | Time Testing Finished:
text | dc5a2b5a-de0a-4f63-bc72-a889bd0a74df |  | textbox | Test Period (minutes):
text | e6ef9777-906e-424b-8329-626a7151f33d |  | textbox | Installers #:
checkpoint-status |  |  | checkpoint | Declaration: I declare that I have installed the above product in accordance with aquatherm specifications with no branding mix
text | e0cd90ab-c1df-4201-8246-569943f8645a |  | textbox | Name:
checklist-flat | b92c5eb9-a127-4446-91c4-dd57c59d9758 |  | checklist | Cesspit |  |  |  |  | Yes | Cesspit | 54866ad7-e084-4399-860f-049a478b544c
checkpoint-status | 064f0a71-1fbc-4a70-98ed-1fffc4c9a861 |  | checkpoint | Is the sump set on correct LL
checkpoint-status | 075119cb-4f01-497e-9637-f90ba4c5da3c |  | checkpoint | Installation Process
checkpoint-status | 50ff0040-a4c0-474e-901a-6707d942a903 |  | checkpoint | Council Inspection and As-Built
checklist-flat | 392ac3fc-98b4-4b2f-a762-e64abd54aa78 |  | checklist | Watermain Pipework |  |  |  |  | Yes | Watermain Pipework | 57761063-c1f2-4817-aa9f-54215e70a2bd
checkpoint-status | 5a2bd182-4aea-47d7-b969-6a6eb3e0338d |  | checkpoint | Bedding Put In At Correct Height
checkpoint-status | d5c8b97b-7079-4273-9c48-66bcc0686542 |  | checkpoint | Grade Right
checkpoint-status | 208fc6e8-948e-4cc2-9aea-6eaefe2abd4e |  | checkpoint | Check Pipes Is All The Way In
checkpoint-status | 537b0d1d-c6ea-4fbe-ba43-ec68f236cfa9 |  | checkpoint | Check Pipe Connections (No Gaps)
checkpoint-status | 0f9608bf-f6b2-4b77-823f-1ccceb2f9c8c |  | checkpoint | Compact Around Pipe
checklist-sectioned |  |  | checklist | Hose Taps Checklist |  |  |  |  | Yes | Hose taps | 58787704-2cfd-41c6-aca7-f277e74cbe21
checkpoint-group |  |  | section | Checks
checkpoint-status |  |  | checkpoint | Position Correct
checkpoint-status |  |  | checkpoint | Pipes coming out of wall straight
checkpoint-status |  |  | checkpoint | Fixings nogs in place
checkpoint-status |  |  | checkpoint | Prevention against waterhammer
checkpoint-status |  |  | checkpoint | All joints watertight and tested
checkpoint-status |  |  | checkpoint | Has fire rating been completed?
checklist-flat | d9f660c4-77fe-4a88-8b49-d4973e98fc6d |  | checklist | Gas Checklist |  |  |  |  | Yes | Gas Checklist | 643f6d4b-2bfd-4f17-95af-9fb55dadbacb
checkpoint-status | f0eb24b2-540c-4d69-b006-620a8bcd0b92 |  | checkpoint | Pipe Tested To 7Kpa
checkpoint-status | b2e2fa3f-4bd1-4cb6-aa61-b8b761083009 |  | checkpoint | Pipe Clearly Labelled Gas
checklist-flat | fcb9f883-f49e-47bf-8d83-4666c1915954 |  | checklist | Manhole Checklist |  |  |  |  | Yes | Manhole Checklist | 64472dd2-782e-4599-89b6-ec3f00734911
checkpoint-status | f50b59df-9701-4a44-9787-603411680f20 |  | checkpoint | Check Existing RL's Of Manhole
checkpoint-status | bd1c706f-f8c2-4932-8966-2ad101754537 |  | checkpoint | Check Invert And Grade
checkpoint-status | 45f7a322-6c63-49c2-9313-e7a94bfd7519 |  | checkpoint | Seal Pipe Into Manhole
checkpoint-status | 5cc0f163-0573-42ac-82a9-5de455e89171 |  | checkpoint | Install Manhole Lid At Finished Height
checkpoint-status | 85cb6734-4a2c-45ca-8555-6278866beaf9 |  | checkpoint | Benching To Be Complete
checklist-flat | 83ca7832-c4e9-4194-a21f-eea924fca6e2 |  | checklist | Photos |  |  |  |  | Yes | Photos | 6499bdc7-c556-4d09-aa3f-6c7fa4810834
checkpoint-status | 11881716-d32d-4e98-b218-5de09fe5cbab |  | checkpoint | Attach Photos
checklist-flat | b4f8b621-ed29-4887-95fe-dab12ebf65b1 |  | checklist | Underslung Pvc |  |  |  |  | Yes | Underslung Pvc | 65a3851b-fa87-460f-a817-5dcec3fd291c
checkpoint-status | a019af81-118c-49e3-ad94-349d8f26848b |  | checkpoint | Pvc installed To Correct Gradient
checkpoint-status | c829ab1a-858a-4774-a629-021e115bb6c8 |  | checkpoint | Flood Tested (Add Photos Of Test)
checkpoint-status | 383e0d98-cff8-4fe6-ac5c-e427ebb46491 |  | checkpoint | Take Photos Of Testing
checklist-flat | b4335e1f-0607-45cf-be3c-365418cac52e |  | checklist | Second Fix |  |  |  |  | Yes | Second Fix | 6b85dfa5-83f8-4c80-9850-b4302a88ba68
checkpoint-status | 54ed07bb-826a-4372-9514-a860c6050441 |  | checkpoint | Is the fixture correctly installed?
label | 4d0d5741-878b-5888-81e7-f484c73b465e |  | note | According to manufacturer specs and architecture design
checkpoint-status | ba52cf43-bf12-4ae4-9980-15caaecc972f |  | checkpoint | Is the fixture free of damage?
label | dea365ee-2f0e-5136-95b4-e9452901580c |  | note | Scratches, cracks, chipped areas or stains
checkpoint-status | 4f895cb0-1aaa-4f8a-80ed-5df2b6a424ea |  | checkpoint | Fixture to be commissioned and checked if any faults require attention
label | b80e7a3f-53bc-5fe4-8e93-248ab1b08099 |  | note | Include leaks
checkpoint-status | b19afade-3617-4e05-b8a9-9a3d89b6370b |  | checkpoint | Hot water temperature at any sanitary fixture used for disabled bathroom for personal hygiene should not exceed 45 degrees celsius
label | 1b10cd31-18cc-593f-8e10-64cfcc5da675 |  | note | Accept: kitchen sink min 60 degree celsius - proof with photo
checkpoint-status | 51894447-b9ad-4833-b005-a17dba3b3481 |  | checkpoint | The sanitary fixture siliconing done where required; to be neat and tidy
label | da6d4664-9cd0-5d4d-acb0-fc2ab207689e |  | note | Proof with photos
checklist-flat | 90d75a5f-a1d7-4e10-8491-42329ca8c650 |  | checklist | Accessible Shower Bathroom Checklist |  |  |  |  | Yes | Accessible Shower Bathroom Checklist | 7136e4b5-7eba-4bd7-b575-c215eb278395
checkpoint-status | 01a82daf-b48d-4efc-a0c2-bbb719a4c852 |  | checkpoint | Set-Out Meets Code
checkpoint-status | 9c882eb1-32c5-46e0-b96a-5ccc91677fff |  | checkpoint | Silicone To Prevent Water Hammer
checkpoint-status | 00155222-d84f-445e-9d5e-60f9cd354429 |  | checkpoint | Test To 1500Kpa
checklist-flat | 615fd5fe-a5eb-4ed4-9892-c00e61dbe7ab |  | checklist | Hose Taps Checklist |  |  |  |  | Yes | Hose Taps Checklist | 7c461f30-96fa-41b1-bb79-99eb97732132
checkpoint-status | ed4c9aab-ec00-4453-aee3-5df753c550ee |  | checkpoint | Position Correct
checkpoint-status | 2e5f8d10-da56-4ee8-b7f4-e401fdbff710 |  | checkpoint | Pipes coming out of wall straight
checkpoint-status | 555f4a5a-63de-4572-adc8-2cd5b894298b |  | checkpoint | Fixings nogs in place
checkpoint-status | abb42a04-ee23-4b99-8df7-d58df0454cc0 |  | checkpoint | Prevention against waterhammer
checkpoint-status | ceab9235-6536-4fd8-a404-f8405feedbcc |  | checkpoint | All joints watertight and tested
checkpoint-status | 94fe6243-eed5-455c-916d-ee01495c0fc0 |  | checkpoint | Has fire rating been completed?
checklist-flat | f6e8746c-f031-4a2a-94be-cf956b4991c9 |  | checklist | Kitchen Checklist |  |  |  |  | Yes | Kitchen Checklist | 8b1bc757-16a1-43c5-955b-dfaa2d6f71e5
checkpoint-status | 8ecf88da-b720-40fd-a8f5-28c427e45a02 |  | checkpoint | Hot And Cold Water Installed Correct Height
checkpoint-status | 94123ae5-fd71-4465-85d9-aaa2e18fa70d |  | checkpoint | Waste Installed Correct Height
checkpoint-status | fddf4966-d491-4acd-97ec-e1c611270c46 |  | checkpoint | Check Hot And Cold For Crossover
checkpoint-status | 5c06e479-a1cb-4e0b-a5af-5ff9cb0beb58 |  | checkpoint | Tested To 1500Kpa
checklist-flat | 98b3110d-4410-489f-ab61-d830a1f079b9 |  | checklist | Stand Alone Washing Machine |  |  |  |  | Yes | Stand Alone Washing Machine | 9679b850-1763-4213-9fd8-1a6ea1cc312c
checkpoint-status | 529a5d2f-271b-4f58-858c-83eb54122216 |  | checkpoint | Nogging For All Fixtures
checkpoint-status | f444a425-4eda-40c7-8215-87d6f06ac2c5 |  | checkpoint | Check Plan To Confirm Heights And Centres
checkpoint-status | 34dc2849-06b7-4459-883d-e2410d1bf26c |  | checkpoint | Check Water Hammer, Silicone Pipes
checkpoint-status | 03260921-e1c1-45c5-b4dd-b2ead6caac60 |  | checkpoint | Acoustic Lagging
checkpoint-status | fc60aa1a-c470-4ce3-b005-ee366f845edc |  | checkpoint | Test All Pipework To 1500Kpa
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Add Fit Off | a3555a91-9ca1-4dd2-a8c1-8f3a9f2f2751
checkpoint-status |  |  | checkpoint | Are all cover flanges installed?
checkpoint-status |  |  | checkpoint | Is fixture stable and installed correctly?
checkpoint-status |  |  | checkpoint | Is the fixture free from damage?
checkpoint-status |  |  | checkpoint | Has the fixture been tested?
checklist-flat | 1c4c1f10-b05e-4e1b-ab0a-d93b6b73c19d |  | checklist | Supertub |  |  |  |  | Yes | Supertub | a4a4aa50-cae1-4aea-92dd-9483553d8552
checkpoint-status | 83a93c10-d8d2-4652-b558-6215977e5209 |  | checkpoint | Nogging For All Fixtures
checkpoint-status | 898b37ef-01e3-4baf-80e8-edaf4e4fb0d1 |  | checkpoint | Check Plan To Confirm Heights and Centres
checkpoint-status | 92d1a866-2f8b-40a1-9b6c-56dd9214619a |  | checkpoint | Check Water Hammer, Silicone Pipes
checkpoint-status | 8319d65a-61a7-4c6f-924c-82cfe2e269fd |  | checkpoint | Acoustic Lagging
checkpoint-status | 4ba830dd-e8aa-4bda-adc6-8ff3a123dd64 |  | checkpoint | Test All Pipework To 1500Kpa
checklist-flat | f1de3b92-2732-4268-b352-60711d0602f0 |  | checklist | Photos & Commissioning |  |  |  |  | Yes | Photos & Commissioning | a51f4ed7-ed9a-4c5d-ba01-6b7cee76f6c7
checkpoint-status | 567b7bc8-48b6-42dc-9f5a-66693df9bb38 |  | checkpoint | Commissioning
checkpoint-status | eab115d4-7d99-4e94-8b1a-9057a33f2538 |  | checkpoint | Attach Photo/s
checklist-flat | 1196cc03-3368-4870-8470-27aa7f59adda |  | checklist | Hot Water Cylinder Checklist |  |  |  |  | Yes | Hot Water Cylinder Checklist | abc9bdf4-0ee8-4598-aa0c-12d7b1e851e9
checkpoint-status | 2d757c40-7b56-4a1f-934b-80713aa9f5d4 |  | checkpoint | Cold Feed With Isolator
checkpoint-status | fc30f6ed-e2c7-49d6-ab87-2e2d3f542021 |  | checkpoint | Hot And Cold Installed
checkpoint-status | 59b18340-2aee-42fb-bd98-38cdc8c5ef67 |  | checkpoint | Tundish In
checkpoint-status | 19e5209f-2d4f-454f-ad88-9c7e7b579287 |  | checkpoint | Has Nogs Been Installed For Seismics
checkpoint-status | c2ef22f8-eb48-4a98-99fb-09bf87a591aa |  | checkpoint | Correct Positioning & Heights
checklist-flat |  |  | checklist | Label # |  |  |  |  | Yes | 25) Add Fire Penetration | b030226f-9d2e-4ffe-bdab-04733558e8f9
checkpoint-no-status |  |  | checkpoint | Has smoke seal been used?
radio | 78e9fd5a-7e08-4dac-a15b-915b3a117651 |  | radio |  | No,Yes
checkpoint-no-status |  |  | checkpoint | What system has been used?
boolean | 3c7ff7de-4a92-4858-9e83-e004aa1b5423 |  | tickbox | Collar
boolean | 1e6aa794-5429-4266-9bac-7bcf08cd789d |  | tickbox | Wrap
boolean | 1db1676d-8099-4c10-8211-b286724084dc |  | tickbox | Other
text | 040c0e22-f74a-41de-8770-cbf20b423db6 |  | textbox | Please Specify:
checklist-flat | ff457fef-aa5c-4574-85fa-4632397ce4c4 |  | checklist | ORG Checklist |  |  |  |  | Yes | ORG Checklist | b35ca15f-98eb-4f01-934f-789d96a92676
checkpoint-status | cdd72e15-bedb-4394-a879-c562d61085f8 |  | checkpoint | Installed in correct location
checkpoint-status | 148fe040-a82f-4e8d-a3cb-11e36c9a88d8 |  | checkpoint | Riser level
checkpoint-status | 9dd90fbe-1286-4532-9184-00ca982b6e03 |  | checkpoint | Is the ORG fixture connection done
checkpoint-status | 1fda1adc-4e43-4e6e-a6e4-bf0906f0ccad |  | checkpoint | Concrete placed under the gully base
checkpoint-status | c669cd36-bab5-4709-bfff-e2e146bd306e |  | checkpoint | Gully dish installed
checklist-flat |  |  | checklist | FWG First Fix |  |  |  |  | Yes | FWG First Fix Checklist | b71932ec-4412-4ee5-9430-72d1879a2dbc
checkpoint-status |  |  | checkpoint | Correct Position
checkpoint-status |  |  | checkpoint | Flange Level
checkpoint-status |  |  | checkpoint | Construction Cap On
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | FWG Second Fix |  |  |  |  | Yes | FWG Second Fix Checklist | bb12b91f-97fb-4ede-9266-24e1af7e14fa
checkpoint-status |  |  | checkpoint | Has the fixture been fitted correctly
checkpoint-status |  |  | checkpoint | Has the fixture been tested (add photos)
checkpoint-status |  |  | checkpoint | Is the silicone neat and tidy
checkpoint-status |  |  | checkpoint | Is the fixture free from damage
checkpoint-status |  |  | checkpoint | Have the lines been flushed
checkpoint-status |  |  | checkpoint | Is the fixture free from leaks
checklist-flat | 300574f1-8bb9-4ff3-818b-7bf3d5ea602e |  | checklist | Balcony Checklist |  |  |  |  | Yes | Balcony Checklist | bd6aada6-d99f-44b9-bd6f-bc4f5af341c9
checkpoint-status | 3b6d5861-c5b0-46e6-a3b3-aa8eaa3d9ade |  | checkpoint | Allthrough Installed
checkpoint-status | 32c4d95a-bc5b-44ac-af4c-0bf1be833121 |  | checkpoint | Overflow Flange Installed
checkpoint-status | 09c74be4-1aa4-4b8c-9287-37ca9829173f |  | checkpoint | Downpipe Flange Installed
checklist-flat | f1462766-c583-4fab-9159-9deb557999c1 |  | checklist | First Fix Checklist |  |  |  |  | Yes | First Fix Checklist | bedd1cc8-7e7e-47af-ad60-250bb7e7531b
checkpoint-status | 52f44d75-e77d-43fc-9a58-e5857dcbefa3 |  | checkpoint | Nogging For All Fixtures
checkpoint-status | 7feb28a2-be13-4aea-be80-cdf4f4d0bd10 |  | checkpoint | Check Plan To Confirm Heights And Centres
checkpoint-status | 51fd7f78-05a8-4a09-91ef-336ccaa9ea71 |  | checkpoint | Check Water Hammer, Silicone Pipes
checkpoint-status | d4f4a2f3-051b-457d-9510-01928a84c383 |  | checkpoint | Acoustic Lagging
checkpoint-status | 1a1f9c19-0d39-48bf-8ec0-2d6ecdb00226 |  | checkpoint | Test All Pipework To 1500Kpa
checklist-flat | f1173ce9-aac2-4733-84ee-7f25ea42b9b6 |  | checklist | Laundry |  |  |  |  | Yes | Laundry | c13b7f77-e669-4af6-902a-31074bd00aad
checkpoint-status | c7541232-aac4-4e65-85f6-4d454106bb81 |  | checkpoint | Nogs for all Fixing
checkpoint-status | af50b416-b8a8-41be-8100-df536a6273ae |  | checkpoint | Check plan to confirm Heights
checkpoint-status | 7ed80ec1-cf7a-4fe5-8fe1-3b3fdb54caed |  | checkpoint | Check Water Hammering, Silicone Pipes
checklist-flat | 0a430193-7dd3-4b25-ba17-2e747da010cc |  | checklist | Stormwater Checklist |  |  |  |  | Yes | Stormwater Checklist | c2f78997-e3d1-4b87-a70c-08bf418d877d
checkpoint-status | 8791debf-f167-44a0-ae42-7f196afe642b |  | checkpoint | Relevant Pipework Lagged
checkpoint-status | 6a014b12-ec65-47e7-a0a5-c729fb13f604 |  | checkpoint | Lagging Tape Around Joints
checkpoint-status | ed162cc1-48e9-4ee7-a921-9edaf036eb4d |  | checkpoint | Blue Strapping And Buckles Every 1 Metre
checkpoint-status | f7af5f1a-6888-4282-8cdb-aef801e9c7e5 |  | checkpoint | Pipe Labels After Lagging
checkpoint-status | bb1fce6b-d96a-4116-a527-4445122b204a |  | checkpoint | Pipe Tested For Leaks
checklist-flat |  |  | checklist | Label # |  |  |  |  | Yes | Fire Penetration | ce1f7e62-a3d5-4b40-a5a5-fef7a2e2bea2
checkpoint-no-status |  |  | checkpoint | Has smoke seal been used?
radio | 78e9fd5a-7e08-4dac-a15b-915b3a117651 |  | radio |  | No,Yes
checkpoint-no-status |  |  | checkpoint | What system has been used?
boolean | 3c7ff7de-4a92-4858-9e83-e004aa1b5423 |  | tickbox | Collar
boolean | 1e6aa794-5429-4266-9bac-7bcf08cd789d |  | tickbox | Wrap
boolean | 1db1676d-8099-4c10-8211-b286724084dc |  | tickbox | Other
text | 040c0e22-f74a-41de-8770-cbf20b423db6 |  | textbox | Please Specify:
checklist-flat | 838fb53f-13b0-4a0b-aaf6-5f51850486df |  | checklist | Shower Checklist |  |  |  |  | Yes | Shower Checklist | d5cde67a-ae5b-4296-9efd-194adab8de77
checkpoint-status | 1a326874-6f35-4329-9a2a-68d528d244f0 |  | checkpoint | Mixer Sticking Out The Correct Length
checkpoint-status | 4858ceab-fd88-45d1-a778-bdeabf5bd24e |  | checkpoint | Mixer Wingback Above 1700 To Prevent Backflow
checklist-flat |  |  | checklist | Flood Test Sheet |  |  |  |  | Yes | Flood Test Sheet | d9b1cd75-42c1-4555-a3ff-8a2809f19afe
checkpoint-status |  |  | checkpoint | Flood Test Date
checkpoint-status |  |  | checkpoint | Flood Test Duration
checkpoint-status |  |  | checkpoint | No sign of water on any joints
checkpoint-status |  |  | checkpoint | No water drop during test
checklist-flat | 9fbb2e1b-68c3-414e-8796-385cfd0348f1 |  | checklist | Photos |  |  |  |  | Yes | Photos | e1879199-cdb7-4bda-a3e4-dd101842d222
checkpoint-status | 89677568-fcda-42f6-86d2-4822bd1409c1 |  | checkpoint | Attach Photos
checklist-flat | 7e860696-23f9-4af3-86e1-645adb50e944 |  | checklist | 1x Shower Tray |  |  |  |  | Yes | 1x Shower Tray | e59f33a3-f47f-403c-8499-de4685fe47ef
checkpoint-status | df97a2c3-868a-43e1-8fe6-99c706df419e |  | checkpoint | Shower Tray Installed Level
checkpoint-status | 51380154-baeb-4c79-87e3-771489a0f64d |  | checkpoint | Flood Test Shower Tray
checklist-flat | c92d7366-e1bd-44df-9fc4-b0ddc64ecdc1 |  | checklist | Drainage Checklist |  |  |  |  | Yes | Drainage Checklist | e75128f1-7f8e-4180-bf20-4d4bd87cd009
checkpoint-status | e7739428-7b9c-4bb5-8fbe-4263aaaf85ab |  | checkpoint | Is Pipe Sitting On Bedding
checkpoint-status | 971142be-f9e5-45d0-8d7b-01e56f643ef7 |  | checkpoint | Is Pipe Installed To Correct Falls On Plan
checkpoint-status | 146f829d-153b-4237-84b7-1991cba32669 |  | checkpoint | Has Pipe Been Photographed For Q + A
checkpoint-status | c51af63a-6af7-487d-a45d-50ef5432280e |  | checkpoint | Is Pipe Free From Debree
checkpoint-status | 50894004-aa13-4cee-adfc-bb7b03c2b906 |  | checkpoint | Has Fines Been Installed On Top Of Pipe
checklist-flat | 5336812c-8bdf-4e05-aacb-49f749550ef2 |  | checklist | Underslab - Water (Rename to required Area) |  |  |  |  | Yes | Underslab - Water (Rename to required Area) | f132a136-1e53-4c0c-88a9-70514c08343f
checkpoint-status | cac82a61-2fa6-42ae-bbe9-261a6d469adf |  | checkpoint | Dimension From Center Of Pipe To Reference Point
checkpoint-status | d8438ae1-f9f4-4a3b-b227-35f3211f123d |  | checkpoint | Pipe Specification
checkpoint-status | 7954ca92-abd5-4629-9f83-d0794d84c44d |  | checkpoint | Is The Installation Compliant To As/Nzs 3500:1
checkpoint-status | 47b22084-9638-4224-9a65-fad86c56787e |  | checkpoint | All Joints Are Crimp And Watertightness
checkpoint-status | 2776a49e-37e4-49e0-85cc-4be62d5648e0 |  | checkpoint | Is The Pipe Protected
boolean | bcb19dd5-85ea-5c7f-b13a-9f447e82623d |  | tickbox | Testing Method | High Pressure Air Test,Water Pressure Test
checkpoint-status | 923a07a5-485d-40a8-a955-35997627ee8a |  | checkpoint | Any Damage On Pipe
checkpoint-status | 91bb44b2-d75a-4ed2-8bb3-dafb062a24b8 |  | checkpoint | Check For Leak Or Pressure Drop
checkpoint-status | 69112d07-09ad-4b29-a4d2-6fb852f9fe87 |  | checkpoint | Is Stub Straight Or Level Both Side
checkpoint-status | 876c89d3-4394-403f-a15a-3e6920f75b7e |  | checkpoint | Council Inspection And As-Built
checkpoint-status | 74522d8f-29d5-43b0-968a-d0b16aa2fab2 |  | checkpoint | Backfill And All Pipe Covered, Even Protection Sleeves For Concrete
checklist-flat |  |  | checklist | Pipework Test sheet |  |  |  |  | Yes | Add Potable Water Pressure Test Sheet | fca156b4-0629-4cc9-8b00-4e397901f452
checkpoint-status |  |  | checkpoint | Photos attached - Pressure gauge and/or flood test
checkpoint-no-status |  |  | checkpoint | Flush – All pipework installs to be flushed for minimum of 2 minutes on full with maximum pressure available.
text | 0d3459c4-33fc-42a1-b3aa-77e602df24c9 | Hidden property width:100 | textbox | Duration
text | a533b7cb-15d7-4f7e-bed9-fb71fe8f2e28 | Hidden property width:100 | textbox | Free Flowing
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
checkpoint-no-status |  |  | checkpoint | Drop Test – Pipework to be subjected to a drop test. No less than 3 drops. Test is used to confirm pipework will withstand environmental extremes.
text | 7962a8d8-ce7f-49f1-b244-44262c4aeb6f |  | textbox | 1 st test pressure:
text | 3c6ad13d-e627-4d87-b26c-1f17d5446e9f |  | textbox | Duration:
text | 29aea5fd-4a2c-4e66-8cae-6f8471f66f5a |  | textbox | Rest time:
text | 823ecc56-7bec-4073-ad01-0a0cd9fe3cdf |  | textbox | 2 nd test pressure:
text | 59e6bf31-b8ba-4c06-ba29-f8a179d468d6 |  | textbox | Duration:
text | d958669a-35ab-46e5-a4c5-89599aaabf39 |  | textbox | Rest time:
text | 9245f833-4587-42f3-b43d-996e3928d4bb |  | textbox | 3 rd test pressure:
text | 5df57267-c866-436a-a2f5-36be1aca2914 |  | textbox | Rest time:
text | d51066fe-8ef7-4c22-a2b6-fd9155d2e425 |  | textbox | Duration:
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checkpoint-no-status |  |  | checkpoint | Hydro static test – Pipework to be subjected to a hydrostatic test for no less than 30mins. Record pressure drop if any. Acceptable drops are allowed if within manufacturers allowances.
text | 9829c9e0-a1ca-40d4-8aec-e68cfa3b6dde |  | textbox | Test pressure:
text | 82429beb-bc98-419c-bf72-1ce769acdd0f |  | textbox | Duration:
text | d6762c94-3820-4f02-8efe-50e8a3b3a320 |  | textbox | Drop:
checklist-sectioned |  |  | checklist | QA Checklist |  |  |  |  | Yes | QA Checklist | fd5618f3-fe45-4e44-83d9-b1c2433dde34
checkpoint-group |  |  | section | Roof outlet questions
checkpoint-status |  |  | checkpoint | Is overflow on correct pipe
checkpoint-status |  |  | checkpoint | Are clamp rings secure
checkpoint-status |  |  | checkpoint | Is gutter free of debris
checkpoint-status |  |  | checkpoint | Has pipework been tested ( Insert photo - mandatory for all testing)
checkpoint-status |  |  | checkpoint | Is pipework secure to outlet
checkpoint-status |  |  | checkpoint | Has acoustic lagging been completed
checkpoint-status |  |  | checkpoint | Are the pipes labelled correctly
checkpoint-group |  |  | section | Vent Questions
checkpoint-status |  |  | checkpoint | container
checkpoint-group |  |  | section | General QA
checkpoint-status |  |  | checkpoint | Pressure Test Sheets
checkpoint-status |  |  | checkpoint | Downpipes
checkpoint-status |  |  | checkpoint | Service duds
checkpoint-group |  |  | section | Drainage
checkpoint-status |  |  | checkpoint | Are all pipe falling
checkpoint-status |  |  | checkpoint | All joints secure and tested
checkpoint-status |  |  | checkpoint | Are all upstands labelled
checkpoint-status |  |  | checkpoint | Is backfill complete
checkpoint-status |  |  | checkpoint | Are all pioe protections in place
checkpoint-status |  |  | checkpoint | All upstand locations secure
checkpoint-status |  |  | checkpoint | Has works been signed off by council