## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | T+T Consultant Site Visit Report |  |  |  |  | Yes | I - C - T+T Consultant Site Visit Report | 2d2a3516-e823-4da6-8e88-04f7e3c7848b
checkpoint-group |  |  | section | Site Visit Details
checkpoint-status |  |  | checkpoint | All site visit details have been captured
text | 4f426398-6e05-5335-acd8-0559dfe0d420 |  | textbox | Date
text | b7ad38d7-3932-5cc2-9731-d766dcd3f922 |  | textbox | Time
text | bb785de2-f015-5618-a764-0f223454ac42 |  | textbox | Weather Conditions:
text | 6e879818-c4d2-584c-ba2f-e9feda61ac69 |  | textbox | Site Conditions:
text | 5e3ff8be-d72f-5a3d-a0b8-ba245dd30144 |  | textbox | Sub-contractors:
text | dbf3a3db-ba09-5e89-84ad-d6dc0975e82c |  | textbox | On-site contact with:
text | 562d5fba-b40b-586f-8b34-5adb2457e5dc |  | textbox | Plant/Equipment on site:
text | e37e1062-23d5-5560-a0a1-8c469ed4c8f7 |  | textbox | Materials on site:
checkpoint-status |  |  | checkpoint | General progress recorded
checkpoint-group |  |  | section | Health and Safety
checkpoint-status |  |  | checkpoint | Health and safety - All details inputted and any closeout completed
boolean | b8f868eb-2726-5dbc-bb3c-43655fb00bed |  | tickbox | Contractors induction/Hazard IT sighted
boolean | 91a7a74b-4992-598f-9ebe-e9b17aa933c8 |  | tickbox | T+T's JSA/Hazard ID signed
boolean | fba974f3-cfdc-5ff9-843f-5f7b53810340 |  | tickbox | Double take completed
text | 3f10e384-1db5-5a4d-9f97-b0f067b0cd18 |  | textbox | Comments:
text | bcc13e80-7b54-58fb-afae-c8baef67af38 |  | textbox | Actions:
text | d85ed0ab-07f7-5657-96da-91bb4deddc68 |  | textbox | Follow up:
checkpoint-group |  |  | section | Inspection Details/Closeout
checkpoint-status |  |  | checkpoint | All Inspection Details Inputted Below
text | e286f9b9-9244-5ac8-a18e-a353ea03eb41 |  | textbox | WORK ELEMENT BEING MONITORED:
button | 4a54ef98-157d-5237-baa0-c92fd4b962d7 |  | button | HAS CONTRACTOR PRE-INSPECTION QA CHECK BEEN VIEWED | Yes,No
text | d633003b-ab90-5c99-8d1c-f308a85440e2 |  | textbox | If "Yes" what QC/QA has been viewed
text | 18db7113-cbc8-5f13-bc67-be40e8823a34 |  | textbox | If "No" detail why no QC/QA has been viewed/referenced
checkpoint-status |  |  | checkpoint | DRAWING REFERENCE:
checkpoint-status |  |  | checkpoint | Works may proceed
label | c2edcf6b-0f66-5a10-8342-68f5e292c6e5 |  | note | "FAIL" if reinspection is required to defective elements (If Failed - Works Cannot Proceed without T+T approval)
label | 98e812a4-d2fa-5bb7-a703-f8d08e541194 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
text | 2112eb49-01ba-59d0-a8db-c4d39f78aa3a |  | textbox | Reported By:
text | 9edd2320-8aee-5bba-b14e-8913243e94aa |  | textbox | Reviewed By:
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | 2fd582e2-0c3c-46d3-af6a-c547067c4dbc
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | a566bafd-d8d5-5924-8c1b-18bebc9f8ca9 |  | textbox | Date of pour
text | 7a6d99a1-3423-5b59-9e58-84dfa3ac1e08 |  | textbox | Specified concrete strength:
text | 3cacc034-5dbf-50e4-af5e-e30943362526 |  | textbox | Concrete strength ordered:
text | efcbbbe0-f4ee-5425-aca3-bec378f10bf0 |  | textbox | Concrete quantity ordered:
text | 6f530bfc-72bd-5efc-9cf0-c10ed7217234 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | e49e18c0-1f0f-5d55-97a7-225987e945f9 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 219c4d9f-601b-5d05-a5dc-6a2bbe9ba902 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 136fe8a8-f346-5359-9200-c15f91cc1972 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 6a7010f5-8edd-5aa2-ad8e-fdf2749d52b4 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 5783fa31-8dfe-525b-8996-24ec71381f8a |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | a4c39795-223b-51a0-b54a-ff01fb46dc4e |  | button | Note remedial work needed | None, Minor, Major
text | 3b1508ed-e658-54a6-8413-967f24504f75 |  | textbox | Inspected by and date:
checklist-sectioned |  |  | checklist | Site Visit Report: |  |  |  |  | Yes | I - C - S&H Consultant Site Visit Report | 31d96830-30a4-4e01-a956-7fc9edfc7782
checkpoint-group |  |  | section | Site Visit Details
checkpoint-status |  |  | checkpoint | Site Details
text | b09f2fb2-8972-5cd7-8a42-eaa69a3327f3 |  | textbox | Area of site visited:
text | 96fa103c-67b3-5773-9f19-6cdd1259583c |  | textbox | Work element monitored / purpose of visit:
text | afdf8881-b47c-5a91-8889-8319081b441a |  | textbox | Date of site visit:
text | c2b776ec-8646-543a-bc48-f3d8994ddc76 |  | textbox | Time on site (include start and end times):
text | 8a1d14ac-bfdf-5554-9f2a-6500408ec389 |  | textbox | Weather conditions:
text | 0250dce3-cb61-568a-8dd4-1183d3e1c112 |  | textbox | Report prepared by:
text | 176df8f1-eddf-57c0-8798-f62f95acdb09 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 6cc6b6a8-4edd-5cdf-afef-0e96f471cfab |  | textbox | Building Consent Number:
text | 9359917c-617c-5852-8b8b-bc80213cbc0c |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | 51b0fe12-a859-5f07-bb3d-a2845d27af56 |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | fad115be-aafc-5640-ba17-74e52265c609 |  | tickbox | Report attached or remedials summarised below
text | 9f14e762-f961-5c86-b0ab-8833d320cfda |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Woods Consultant Remedial Item Checklist |  |  |  |  | Yes | I - C - Woods Consultant Remedial Item Checklist | 3f3f015c-8b3b-4b75-942f-82edced5c2de
checkpoint-status |  |  | checkpoint | Remedial Status (Woods to "Pass" once satisfied)
text | 7f5e05d2-8527-537a-bd79-e3c8ee3cd47e |  | textbox | Location of Remedial
text | 6fe9dda4-92a9-5e59-9b3f-fb6662f2149f |  | textbox | Remedial Description
text | 58a72199-e107-5218-af69-27383d881ece |  | textbox | Action Required
holdpoint |  |  | signoff | Request Woods Signoff on Remedial
checklist-sectioned |  |  | checklist | ST - R - Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | 5753f0ca-ed4a-460c-95d8-ff81e9bb7b72
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-status |  |  | checkpoint | Ryman Infill Installation SOP obtained and reviewed. Record version number below. Click PASS to confirm
text | fc2d3aae-dda9-5c4a-9e07-bb29f891050d |  | textbox | Version number
checkpoint-status |  |  | checkpoint | Subcontractor SWMS obtained and reviewed against Ryman SOP.
checkpoint-status |  |  | checkpoint | Variations to the SOP are proactively assessed and managed with the subcontractor accordingly. Record personnel involved below. Respond N/A if no variation to Ryman SOP is identified.
text | 67cd97b3-acb1-5291-9729-b36e6cbcc5f3 |  | textbox | Name/s of personnel
checkpoint-status |  |  | checkpoint | Upload a copy of the subcontractor SWMS document. PASS this checkpoint when uploaded.
checkpoint-status |  |  | checkpoint | Approval to proceed given.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
checklist-flat |  |  | checklist | T+T Vibration Monitoring Report |  |  |  |  | Yes | I - C - T+T Vibration Monitoring Report | 615b497b-5d33-4b3b-8738-3886a579476a
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection & report attached
checklist-flat |  |  | checklist | ITP - R - Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | 7ad5c926-bfc9-4782-b9fd-9814ed3bf2a8
checkpoint-status |  |  | checkpoint | Contractor Allocated
text | c6a29304-64c7-5741-815b-6364a93a5413 |  | textbox | Record Subcontractor Company Name
text | ffcd552e-f5b4-561e-bf64-12f89246a7a8 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checklist-flat |  |  | checklist | T+T Remedial Item Checklist |  |  |  |  | Yes | I - C - T+T Remedial Item Checklist | 8288ccd3-4f4a-4f5e-8e6e-3f30cf929688
checkpoint-status |  |  | checkpoint | Remedial Status (T+T to "Pass" once satisfied)
text | ab61d8d9-adb4-5449-a7bf-e8a522e407d0 |  | textbox | Location of Remedial
text | 871adada-11a4-58e2-97ee-46af68e47f17 |  | textbox | Remedial Description
text | 110ae150-083f-504a-9dc8-a1e2a809a892 |  | textbox | Action Required
holdpoint |  |  | signoff | Request T+T Signoff on Remedial
checklist-flat |  |  | checklist | ST - R - Monier Tiled Roof Installation |  |  |  |  | Yes | ST - R - Monier Tiled Roof Installation | 8559b731-141d-4fe2-8236-338bd46a2e26
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Monier Installation Guide Confirmed with Contractor
checkpoint-status |  |  | checkpoint | Subcontractor QA completed and passed
checkpoint-status |  |  | checkpoint | Fall Arrest Anchor Point Fixings in place
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Battens - jointing and fixing.
checkpoint-status |  |  | checkpoint | Sarking/Underlay
checkpoint-status |  |  | checkpoint | Tiles Laid and Secured
checkpoint-status |  |  | checkpoint | Hip and Ridge Tile Bedding and Pointing
checkpoint-status |  |  | checkpoint | Gable ends / Barge Boards - Finish
checkpoint-status |  |  | checkpoint | Fire Wall/Internal Separating Walls
checkpoint-status |  |  | checkpoint | Fire Consultant inspection completed and approved
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
text | 630de155-80e3-5b2d-bc63-8055bf6840e1 |  | textbox | Note remedial work needed
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Concrete - Planning and Pour (per area) |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per area) | 8cd42c09-8da3-4793-bc75-69e8517bba0b
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 13d43c4a-ecdf-5b36-9074-862bd207357a |  | textbox | Date of pour
text | 313c28ba-0be7-5d44-8949-76e7489842ac |  | textbox | Specified concrete strength:
text | 1283ab0e-12d5-5844-a20c-d1791872a01b |  | textbox | Concrete strength ordered:
text | a0347221-f196-5183-a334-a62ac4bec742 |  | textbox | Concrete quantity ordered:
text | 2a8dadf8-47e9-502e-9382-393ced1385c1 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | d6b2d4d0-aa4e-54db-893b-c9c37068ec82 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | fe8a66e0-692d-505c-b501-e7883888ce84 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 951902ab-e3bb-5e4f-a9d5-45ce256744ce |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 1e003843-2f24-5852-8654-d12ff3d612d1 |  | button | Couples present and correct | Yes, Reworked, N/A
button | c2bbb1c0-eaed-5e63-a199-964270f88655 |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 0f0d28bf-0300-569a-a4c7-8861a9ed7155 |  | button | Note remedial work needed | None, Minor, Major
text | 1a647ad7-fb64-5c18-bc39-ed1a71db1c9e |  | textbox | Inspected by and date:
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Documentation
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-sectioned |  |  | checklist | ITP - R - Apartment Facade (per elevation/grid) |  |  |  |  | Yes | ITP - R - Apartment Facade (per elevation/grid) | 91a246c0-a098-4d87-8686-d62dff432325
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 00b315b0-28e0-5504-9813-b422a80e6290 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | 5b865678-4a60-52d6-a763-e8cace78cd17 |  | button | Lintels installed | Yes, Reworked, N/A
button | 52a34110-4f1c-5692-a4d6-9f6737b6e880 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | eb70016f-9526-5851-a530-255f56c62e22 |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | b071040f-0e58-5047-af69-c7b08ab44814 |  | button | Flashing installed | Yes, Reworked, N/A
button | 05d0943c-40db-52a6-8e90-e39b5bbb6b58 |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Balcony waterproofing completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 8f57220a-63af-5789-a725-0e8a3bf07127 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | f9440bb9-12ce-5d59-9f9b-bc6ffc5eaa7f |  | button | Note remedial work needed | None, Minor, Major
text | 6ec91b26-c81e-5a67-adf3-b80b002e5526 |  | textbox | Describe cladding type:
button | 58a28e40-45c4-5eb1-9b1a-3294bc338ed2 |  | button | Brick Works completed | Yes, Reworked, N/A
button | 83b66492-d86e-5cb3-b168-a7d69e1b3254 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Panels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | 7528efd7-c049-5bbc-993f-bcad6ef82207 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 9d190b3d-29dc-5f9e-8e36-57fe852c5224 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | 2295f235-2079-55f5-9b42-c409ba1f1638 |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 11b6b2aa-4255-52eb-bb45-ee083227ecdf |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c907be16-68ee-54ba-bbbf-716725d67489 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 1504efa6-70a5-528d-bff6-a20bfaf7f65e |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Pipe Laying (Mains Water, Storm and Waste) |  |  |  |  | Yes | ITP - R - Pipe Laying (Mains Water, Storm and Waste) | 91cdf93d-3f3a-40ff-9e53-eb04dba8536a
checkpoint-group |  |  | section | Main Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 39afa771-3aff-5a09-89c7-98580c92a49b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 7238ef8c-0838-5c24-a6f9-4472cc97ba2e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 196cd4a2-c7f3-5472-88d3-420686b4ba58 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 4e4bea62-bd74-57cf-80e1-ad7de3cad2e5 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c81f12cf-a579-51c6-b2ab-8ff97085c281 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | f507952e-5f03-5017-8826-c69cb9082500 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Waste Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Air/water test completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | bd49c02e-99fc-5c59-a72d-d906f469d6ee |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ca7cb3e4-51e0-5212-9074-8f1e84652e13 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 13134261-c750-52a2-9030-b9d5acdae13b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre & Post Line (per area/grid) |  |  |  |  | Yes | ITP - R - Apartment Pre & Post Line (per area/grid/location) | 9d3dbbaf-e2b9-4658-96b9-4147b24fc049
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 2baa6765-d1af-507e-80c1-94e8511da692 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | 945534ed-28a7-54e7-b366-661adf192f07 |  | button | Lintels installed | Yes, Reworked, N/A
button | fd80b4b3-b737-5c22-90ee-6e9e9c5a2e93 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | 02810e6f-82af-591f-9829-c0bb5524cd8c |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | cd33afb3-bb57-587b-88a2-ac382ddb5e88 |  | button | Flashing installed | Yes, Reworked, N/A
button | 81ed297b-cfb5-5916-82e0-ce999c85ad1d |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | e92a174d-65f7-5a65-aadf-b99776584fce |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 0519b98e-747e-53fa-988f-36d79c6c94b4 |  | button | Note remedial work needed | None, Minor, Major
text | 0cc81a0f-a572-5a15-b4de-7b0712a44a49 |  | textbox | Describe cladding type:
button | bc7b8086-1f7d-5d9b-9d40-02e7384bfd1d |  | button | Brick Works completed | Yes, Reworked, N/A
button | 309c3a45-4b1d-555d-b16f-616aec372371 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Panels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c1d4414f-b7ae-528d-8c93-86e70fe7781b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 44515db8-0ba1-5fa8-b012-e3f78ad62670 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 0920e965-f310-5b3a-878d-006e728e8455 |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed and comply
button | 2064b828-a37d-55a5-9277-0a42a6d00c96 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | 9f9924f2-1939-53a3-af7c-7aa45e8bef82 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | e03ec794-92c0-5a2e-a7d1-bad0b88f0d21 |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 40c34c38-f8a9-5046-bb9d-bb2b479793f0 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 3af54551-0b0e-5c66-a00a-7acea2bec90b |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 6415f5cb-6fdf-5f9e-98eb-7cb111ef3cc6 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | 350659f4-71b2-5864-8a03-0f40287828e5 |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | 07088a7f-d491-55b2-b19d-360a7750355a |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | d7ae1656-bc55-585f-9d54-f8cedf10ec48 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 4892ced3-553c-5f42-af04-67ce7f86da64 |  | button | Note remedial work needed | None, Minor, Major
text | 0377cb69-9171-5b48-b3e4-2c8f6ebe079f |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | b0609ca6-2deb-5459-b0c2-74a9dbde1064 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | 266fc80c-595c-5dbc-bd3e-7abf08855a6a |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 6d3f25fd-9a90-5cba-99a1-71977869081e |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | 364ee501-85ae-56ea-a020-d4efe229f5d8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | dd367f23-a251-5fe1-8847-8dd13d584732 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast, Timber, Insitu, Blockwork Element Installation (per area/level) | 9dd18c59-13f4-4a06-b44f-3a2793baad73
checkpoint-group |  |  | section | Pre-Cast Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Installed vertically / aligment tolerances complies with specification (components below)
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Spandrels
checkpoint-status |  |  | checkpoint | Pre-cast panels
checkpoint-status |  |  | checkpoint | Columns
checkpoint-status |  |  | checkpoint | Stitch joints
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 3a40dd67-90a2-5517-839b-ac4a75ca58d7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | bf73d49a-37f5-5f72-937d-3c647ca12c0f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | aa51a282-90b5-5aa5-aec1-07b17de217e0 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Timber Framing Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Timber Framing installed
button | 4852c1dc-9fef-5af9-8e26-21c69a0e6ad5 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 202e9ddc-b14e-5d9a-8258-fe3af9328820 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ce86213a-d5c4-5ba9-ba36-086a33b1a096 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 06971275-6386-5475-961d-d9ce94f8806c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Insuti Pour Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stitch joints - meets specification
checkpoint-status |  |  | checkpoint | Beams - meets specification
checkpoint-status |  |  | checkpoint | Panels - meets specification
checkpoint-status |  |  | checkpoint | Columns - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 8208ff85-0cac-52ff-a381-8aa327576eff |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c9f88748-5e33-5f42-9872-6fba21b514ad |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 45828b6c-2aea-56e2-bd21-0af89e34a9ee |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Reinforced Blockwork Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Blockwork - meets specification
checkpoint-status |  |  | checkpoint | Reinforcing - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 1352c890-15eb-575a-bd41-20a296621262 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 40b39b8f-fbcd-5f46-8317-920b63563bcc |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 37b863c8-3288-5581-9ffb-be8bbf0bf926 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Chemical anchor testing completed. Upload report
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
text | 9c47c708-82ce-55c2-b888-2685ae084e9f |  | textbox | Record sample size
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Concrete Documentation
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 4a083c16-4523-5ddd-9bee-86006f25e0aa |  | textbox | Date of pour
text | f6c10cf6-d7e6-5143-a8c6-ab517775ccd6 |  | textbox | Specified concrete strength:
text | 983396ee-c6a0-5bd1-a912-aad2a0ce0fc4 |  | textbox | Concrete strength ordered:
text | 19f576d5-89ea-5201-a11b-889bd002c0bf |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-flat |  |  | checklist | Woods Survey Set-Out Checklist |  |  |  |  | Yes | I - C - Woods Survey Set-Out Checklist | a18595c0-c90c-4073-8ba5-e5e65451f946
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | 2a7dc799-7c91-5f78-97cc-327eafc32966 |  | textbox | Survey works completed by - (enter name)
text | ca984a9f-f4ec-54a5-bb57-6f5d1f7ddc61 |  | textbox | Additional personnel accompanying surveyor
text | 1b8f0eb9-1b6e-55af-b933-60ca3d201099 |  | textbox | Building/Area to Setout
checkpoint-status |  |  | checkpoint | Received CAD drawing of building grids or outline
boolean | 7d4983b5-ea77-56fc-8e82-22cc498b7acd |  | tickbox | Office calculations
boolean | 73fad50f-29ec-575c-ba89-502380b83882 |  | tickbox | Set out platform using offset stake
boolean | 6b88bb0f-9e12-5081-93a8-6233f8bf0dc4 |  | tickbox | Mark level of top of platform
boolean | 593ed0ac-1dd2-5b39-b80d-49c66714b791 |  | tickbox | Provide diagram of set out to contractor
checkpoint-status |  |  | checkpoint | Check level of platform is correct
boolean | 978b01d2-1898-5be6-83dc-4cd32728b4df |  | tickbox | Set out grids on profiles installed by contractor
checkpoint-status |  |  | checkpoint | Setting out certificate or Building Location Certificate before concrete pour
boolean | 2228dae0-fdd1-53be-9a91-66f75607f49a |  | tickbox | Copy of Setting out or Building Location Certificate
boolean | 2168316d-d679-5ae7-8791-42b5f353fdfd |  | tickbox | Upper floor setout (if required)
boolean | 240ff477-1fce-5966-93d0-e365f1ff7a72 |  | tickbox | Receive instruction from Rymans
boolean | 83061db0-570a-53dc-8e90-4de941c3dbc0 |  | tickbox | Set out service locations on upper floors
boolean | cd7179fa-f601-5538-8d48-bec4ad4881bf |  | tickbox | Diagram provided to contractor
checkpoint-status |  |  | checkpoint | Setout / Surveying works completed and report sent to relevant parties
checklist-sectioned |  |  | checklist | ITP - R - Services |  |  |  |  | Yes | ITP - R - Services | a578df0b-2e5e-466c-8db6-e1300a2eb98c
checkpoint-group |  |  | section | Residential Apartment/Townhouse Unit
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 56e1b5e6-6036-5b78-a527-181a8520ebf9 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | d9e6975b-a286-5ba1-b248-b48cb23daa7e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | dec2c850-1321-546c-9b61-c19ef4d9728b |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 24716e16-a440-57a5-8171-803289c11416 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | e8d53e07-ebb6-5ae3-8700-c67dd3223910 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | POST - R - Grab Rail Load Testing (per stage) |  |  |  |  | Yes | POST - R - Grab Rail Load Testing (per stage) | a60e3d1f-8548-4bc4-b07a-38fea343d06c
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | df8e0893-a09e-595e-b364-fa0503888ebc |  | textbox | Record quantity tested
text | 4fa99306-9d9c-5831-90a7-ce8eb9cce022 |  | textbox | Record sample size (%)
text | da6a685b-75a6-56b2-ada0-53ac7f54d648 |  | textbox | Record Apartment No's tested
text | 15135b72-9f4e-5cb7-9101-277578c35236 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | a982193a-38dd-4fa6-ad7a-d89612bf58dd
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 12f06f9d-851f-586f-b79f-934e897cacb0 |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | ST - R - Double T Installation |  |  |  |  | Yes | ST - R - Double T Installation | b7d480d2-3a29-437c-90c3-3fdfc3921223
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Inspected on arrival & damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Shoreload completed
checkpoint-status |  |  | checkpoint | Double T install complete and acceptable (checked location and level)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 60546f6c-4cfe-5f2c-811c-8de408253aa2 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | On Grade Slab Pre-Pour |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per townhouse block) | bfff35c9-603b-44ad-895a-add4d4bee63d
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | 85efbc53-74fa-52a0-b06a-4d6ad661b420 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 5a633978-fb98-5e51-8422-5f39bf626ea4 |  | button | Note remedial work needed | None, Minor, Major
text | 48106bbd-593e-51c0-9924-269c3c999bba |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-sectioned |  |  | checklist | Woods Consultant Site Visit Report |  |  |  |  | Yes | I - C - Woods Consultant Site Visit Report | c999a420-682d-48c7-8026-6f7c87d38e88
checkpoint-group |  |  | section | Site Details & Inspection Specifics
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | d9885644-11ad-5600-9c72-692ff238b160 |  | textbox | SVR#
text | 155066c2-e395-5735-86dd-af91b26e3e2f |  | textbox | Area of site visited
text | fc9a85a8-d30a-5492-83b5-fef2b4cf1ca6 |  | textbox | Purpose of visit
text | 5a8e908b-a6cf-5a67-bbc5-7870c9a43883 |  | textbox | Date site visit occurred
text | 485c34d9-ccab-53b0-82ba-8cacd8a53ed3 |  | textbox | Time on site (Include start & end time)
text | 5842bc30-fe54-5a6d-8488-291aa695db33 |  | textbox | Weather
text | 158f91af-950a-54d3-8aee-d4a22501a518 |  | textbox | Report prepared by - Engineer's name
text | 372d9276-3631-54e4-83e2-1270a1e1fa46 |  | textbox | Additional personnel accompanying engineer
checkpoint-status |  |  | checkpoint | Health and Safety Observations recorded/photos attached
checkpoint-status |  |  | checkpoint | Dust / Erosion and Sediment Control Observations recorded / photos attached
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | d1ffa4b1-b5e4-5b53-a677-6a4c1a5ce98c |  | textbox | Drawing & Revision Number(s)
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
label | 1ef147bb-75bb-5b0f-af12-a839676d624e |  | note | Capture relevant photos specific to this site visit report
button | fd364f62-116f-566b-b72a-5b9dfc909f64 |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 195cf81d-f8f4-50b0-96b1-711af26773b6 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | bd078291-6596-57f7-9156-3f684fc8c503 |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or re inspection required to defective elements (select Fail - Works Cannot Proceed)
select | ea506436-65c7-5625-98fd-f93f862c014d |  | dropdown | Select appropriate outcome | PASS - no remedial work, PASS - Remedial action needed to proceed, FAIL - Stop works (fail checkpoint).
label | 1634ec0c-7988-576f-a4fb-ec316edca116 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
checkpoint-status |  |  | checkpoint | Remedials raised against Main Contractor
holdpoint |  |  | signoff | Raise Remedial Request
checklist-sectioned |  |  | checklist | POST - R - Stair Well Guard and Hand Rail Testing (per stage) |  |  |  |  | Yes | POST - R - Stair Well Guard and Hand Rail Testing (per stage) | d15f947d-8ecb-4dd7-876d-65c7855b4b77
checkpoint-group |  |  | section | Guard Rail Pull and Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Bolt pull testing completed and passed. Test results received and confirmed.
text | a9c32f84-9c7d-58fa-bf98-f00809305437 |  | textbox | Record quantity tested
text | ecffe705-a20e-5d14-a610-c667a52f9586 |  | textbox | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testing completed and passed. Test results received and confirmed.
text | bf5af4b6-5363-56e6-bb96-6bdb2c0219a9 |  | textbox | Record quantity tested
text | b2e46a61-8dd2-557d-a372-6cff9ce18f0b |  | textbox | Record sample size (%)
text | a35e5c12-3ab6-557e-b0be-e25ed145389e |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Handrail Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | 070cc95a-3b40-57eb-973f-832ec068db1c |  | textbox | Record quantity tested
text | cdacd5c6-d579-563d-8c04-b2575233242c |  | textbox | Record sample size (%)
text | c7d10804-50c8-5931-879d-3c3cca6e6228 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Fitout |  |  |  |  | Yes | ITP - R - Fitout (per townhouse unit) | d1c8a907-8caa-4c21-ac2b-752f96c0667a
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | 90b59940-b9c7-5fd7-8a3e-0bced6739f38 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | 4bbc2670-6e28-53f5-ae59-8348ee82bdbb |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | f7916c64-81a3-58fd-a229-2c1272924308 |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 7e7a5a4a-7606-55e3-a327-ad6c429ff17e |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 4820c93c-e60f-5840-aa10-e4800a08310e |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | 76aad3c5-12f2-578e-a88a-27c5acc855d4 |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | 29049e71-86e9-5fa0-b76d-b772a27d7430 |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | a334a3eb-1b7f-59fc-9794-c9b9a4102b9e |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | MV Consultant Site Visit Report |  |  |  |  | Yes | I - C - MV Consultant Site Visit Report | e1f8f4f1-0cd9-4991-8878-055de13e1fa1
checkpoint-group |  |  | section | Site Inspection Details
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | f796cdf6-1cc3-5115-ba07-0ff76c522012 |  | textbox | Building Consent No.
text | b1f81a58-c4c1-508f-ab59-dd5f5ed361db |  | textbox | Date site visit occurred
text | 994ac6a0-7d23-574f-a4d4-e47bdca59313 |  | textbox | Time on site (include start and end times)
text | 83b47e99-3880-5633-9ae4-f04bbdbc9c37 |  | textbox | Report prepared by - Engineer's name
text | c4ea4f5a-79ee-5484-8b83-c0646a5c3768 |  | textbox | Additional personnel accompanying engineer
button | 4b04de9f-01a0-5e66-9c4b-f5793be2d3cc |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 7d400e33-ea35-515e-8c54-69a5c61b7ef6 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | 6085d91a-80c4-5cec-942e-7d4773633e9f |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-group |  |  | section | Inspection Specifics
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or reinspection required to defective elements (select Fail - Works Cannot Proceed)
text | 7db14ead-a8b3-5898-b7a0-2c5bb5d83e29 |  | textbox | Remedial(s) - Recorded and Closed Out
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-flat |  |  | checklist | MV Compliance Documents |  |  |  |  | Yes | I - C - MV Compliance Documents | e3f813ab-5f92-4f5a-9651-5e3962463348
checkpoint-status |  |  | checkpoint | Compliance Documents
boolean | 60dac8a3-1b67-5ba5-b9ad-257afa937dc7 |  | tickbox | LBP Memorandum
boolean | d2841a9d-e45b-5290-a4a7-5e3023301ca0 |  | tickbox | Mill Certificates
boolean | 238e917e-0f97-5308-912c-81de20c3461f |  | tickbox | Concrete Dockets
boolean | 8abcf8b5-a6ad-53de-8b31-f80a00e8cf3c |  | tickbox | Concrete Strength Test Results
checkpoint-status |  |  | checkpoint | Mitchell Vranjes PS4 Attached
checklist-flat |  |  | checklist | MV Remedial Item Checklist |  |  |  |  | Yes | I - C - MV Remedial Item Checklist | ea801be6-4450-4b35-a9d9-1ba7a14ac0e8
checkpoint-status |  |  | checkpoint | Remedial Status (MV to "Pass" once satisfied)
text | 104edfc1-4fc5-5fc9-99a4-4baf090eddac |  | textbox | Location of Remedial
text | cca059f4-64ec-598f-a24b-f0e12f3e03c7 |  | textbox | Remedial Description
text | f44ee69a-58ec-5993-a234-1057564fd340 |  | textbox | Action Required
holdpoint |  |  | signoff | Request MV Signoff on Remedial
checklist-sectioned |  |  | checklist | Townhouse Block Build |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | efee36d2-c198-4a5c-acaf-5a59d8457993
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Timber Framing installed
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | d36c2053-3b4c-5d42-b8b3-3c1dc01cc805 |  | button | Note remedial work needed | None, Minor, Major
text | 734b5056-4aa5-5c7a-9d86-33267fb303de |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | 43618b40-f0bd-505e-b7e4-2e3edc044cf6 |  | button | Note remedial work needed | None, Minor, Major
text | 025df47e-66d6-5bf5-a607-00fb36e46ad6 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | b4f81066-3f6d-5559-8b5c-e9238b4a341c |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | f1f5e14f-c94f-572b-a5c3-f91ce0be96e1 |  | button | Lintels installed | Yes, Reworked, N/A
button | 81579ca4-4558-5fcd-b3b8-6d3060817aec |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | e75d1cae-2e6b-545a-89c8-ecafc6822593 |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | acbf913e-0c18-5f03-a6de-2e5e56ff7130 |  | button | Flashing installed | Yes, Reworked, N/A
button | 508bac90-ccff-5438-a400-37f7d3549364 |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 24084087-afdc-5fbf-8ac4-3336206bb111 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | f01676a5-c1b0-5876-ab68-18c01dfae556 |  | button | Note remedial work needed | None, Minor, Major
text | 8e6a1b1c-ec67-575c-a530-8dbf369e6a51 |  | textbox | Describe cladding type:
button | 1d0569d5-651d-51f5-a201-329f54d8d695 |  | button | Brick Works completed | Yes, Reworked, N/A
button | 738768b2-37d6-52f1-a535-b6993e4cc638 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 2f09208f-5e7b-5aff-98ef-e9d9e950c4be |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 0e42350e-b3fd-5e06-b721-26bc704d08f0 |  | button | Timber frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | c40eb259-4a56-58de-9d09-3f877a517c2e |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
button | 69ba2c2c-d640-5da3-9f49-f4d9bb73f1e6 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | c51ca6be-a615-5214-adf8-8165d072c256 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 0d0b968c-7ab2-583e-b9b0-3807df5e89de |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 19224e2c-bbc0-59f6-b7fd-44243f08a279 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 5d156462-8165-5107-b2ab-07c166fed994 |  | button | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 69292ca5-fa21-5b36-b6a4-8c60af6caf65 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | daa078a6-ab97-5492-8d3d-1ceb1f5f7ddf |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | fb59201e-c353-5e2c-93fc-a7ec48328c4d |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 82976e74-c562-51a3-9f6d-2a6bd04f03be |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 856b9346-be85-55a7-b2fb-c417c357d46b |  | button | Note remedial work needed | None, Minor, Major
text | 8d0d30e2-2ebe-5db9-91d8-66d0130663e4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 7f0e7218-84ae-5457-97e0-28f4ea69b1ca |  | button | Note remedial work needed | None, Minor, Major