## Project breakdown
| B H Fixing & Stopping | PROJECT BREAKDOWN
BH Fixing & Stopping Limited - Riccarton Park
Project Build QA
Stage 3 - THB11, THB13
THB 11 (TH33, 34, 35, 36)
TH 33
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
TH 34
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
TH 35
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
TH 36
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
THB 13 (TH37, 38, 39)
TH 37
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
TH 38
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
TH 39
[5 empty] | Internal Lining Ceilings | Prepopulate | POST - S - Internal Lining - Ceilings
[5 empty] | Internal Lining Walls | Prepopulate | POST - S - Internal Lining - Walls
[5 empty] | Stopping | Prepopulate | POST - S - Stopping
Completion Documents

## Checklist
checklist | POST - S - Internal Lining - Ceilings
checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
checkpoint | Services/Penetrations, correctly formed & located (consider cutout tolerances and access hatches (location & size) where applicable)
checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint | Any bracing elements completed to design specification
checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | POST - S - Internal Lining - Walls
checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
text | Specific products used (photos Required)
checkpoint | Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint | Any bracing elements completed to design specification
checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | POST - S - Stopping
checkpoint | Consider fire stopping between layers of lining & apply compound(s) as specified
checkpoint | Openings/penetrations/corners & bulkheads, correctly formed (consider tolerances where applicable)
checkpoint | Consider square stopping, slimlines, joints checked & acceptable
checkpoint | Correct compound(s) used to align with consented specifications
checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
checkpoint | Light check completed to ensure no sheet joins stand out
checkpoint | Stopping work completed - specified level of finish achieved
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS