## BW Retaining Walls
type | name | values | prefix | postfix | usage count
checklist-flat | Retaining Wall (Sheet)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | Granules installed at cold joint? | Yes,No,N/A
button | Installation of sheet membrane as required? | Yes,No
button | Termination pressure bar installed as required? | Yes,No
checkpoint | Area completed to manufacturer's specification? (Attach photos)
text | If inspection failed, please provide reasons and recommended course of action.
button | Cement sheet installed? | Yes,No,N/A
button | Corflute installed installed? | Yes,No,N/A
button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint | Backfilled within manufacturer's specified timeframe?
label | Attach Client Signature Below
checklist-flat | Retaining Wall (Liquid)
label | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | Installation of liquid membrane as required? | Yes,No
checkpoint | Area completed to manufacturer's specification? (Attach photos)
button | Cement sheet installed? | Yes,No,N/A
button | Corflute installed installed? | Yes,No,N/A
button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint | Backfilled within manufacturer's specified timeframe?
label | Attach Client Signature Below

## PVC
type | name | values | prefix | postfix | usage count
checklist-flat | PVC Installation (Sarnafil and Cosmofin)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | Adequate fall in substrate? | Yes,No
label | If any of these checkpoints fail information and required action by builder provided in comments below
button | Adhesive installed to manufacturer's specification? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of adhesive
label | If any of these checkpoints fail information and required action by builder provided in comments below
button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below
type | name | values
checklist-flat | PVC Installation (Wolfin)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water, and adequate fall in substrate (Moisture gauge photo attached below)
label | If any of these checkpoints fail information and required action by builder provided in comments below
button | Bitunamel primer installed to manufacturer's specification? | Yes,No
button | Bitunamel primer given adequate time (4 hours) to cure – as per manufacturer's specification? | Yes,No
checkpoint | Record (Photo) batch numbers and dates of manufacture of bitunamel primer
checkpoint | Area primed and suitable for membrane application. Substrate free of contaminants - photos attached below
text | If inspection failed, please provide reasons and recommended course of action
button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below
checkpoint | Manufacturer Inspection
label | Manufacturer's Warranty Certificate attached below

## Butynol Sheet
type | name | values | prefix | postfix | usage count
checklist-flat | Butynol Installation (External)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water? (Attach moisture gauge photo)
button | Adequate fall in substrate? | Yes,No
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Installation of primer as required? | Yes,No
checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below
label | Attach Client Signature Below
checklist-flat | Butynol Installation (Internal)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
label | If substrate failed please provide information and required action by builder
text | Add Comment
button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below
label | Attach Client Signature Below

## Bentonite
type | name | values | prefix | postfix | usage count
checklist-flat | Bentonite - Underslab Membrane (Hydrostatic)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
checkpoint | Dewatered
text | Notes on dewatering for Project Manager
button | Membrane Installed? | Yes,No
select | Minimum lap required | 150mm,200mm
button | Waterstop to pile caps | Yes,No,N/A
button | Detailing of penetrations | Yes,No,N/A
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Underslab Membrane (Non-Hydrostatic)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
checkpoint | Dewatered
text | Notes on dewatering for Project Manager
button | Membrane Installed? | Yes,No
select | Minimum lap required | 150mm,200mm
button | Detailing to pile caps | Yes,No,N/A
button | Detailing of penetrations | Yes,No,N/A
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Strip/Pad Footings (Hydrostatic)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
checkpoint | Dewatered
text | Notes on dewatering for Project Manager
button | Granules to perimeter? | Yes,No
button | Membrane Installed? | Yes,No
select | Minimum lap required | 150mm,200mm
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Shotcrete Wall Membrane
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
select | Join Coverage | 50mm,75mm,100mm,50-100mm
button | Capping Beam Part Of Installation? | Yes,No
button | Capping Beam Waterstop Installed? | Yes,No
select | Waterstop Type | RX-102,Akwaswell,Both
button | Waterstop to drop join installed ? | Yes,No,N/A
button | Detailing of penetrations | Yes,No,N/A
button | Membrane Installed? | Yes,No
select | Minimum lap required | 150mm,200mm
checkpoint | Starter bars detailed
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Anchor Boxouts
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
button | Membrane, Bentoseal & waterstop installed? | Yes,No
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No,N/A
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Wall / Slab Junction
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
select | Slab Thickness | <450mm,>=450mm
select | No. of waterstops to install | 1,2
button | Waterstop installed? | Yes,No
button | Granules to junction? | Yes,No
button | Akwaswell to lowest 2 laps? | Yes,No
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - PT Slab Wall Junction Termination
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
button | Waterstop installed? | Yes,No
button | Termination bar installed? | Yes,No,N/A
button | Bentoseal installed? | Yes,No,N/A
button | Cetinject installed? | Yes,No,N/A
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Dewatering Wells
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
button | PureGold Chips Installed | Yes,No
button | Builder installed Concrete Grout | Yes,No
button | Membrane Installed? | Yes,No
button | Waterstop installed? | Yes,No
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below
checklist-flat | Bentonite - Capping Beam Waterstop
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate suitable for application
text | If inspection failed, please provide reasons and recommended course of action.
button | Waterstop installed? | Yes,No
checkpoint | Area completed - photos attached below
text | If inspection failed, please provide reasons and recommended course of action.
button | Manufacturer Inspection Requested? | Yes,No
checkpoint | Manufacturer Inspection
label | Attach Manufacturer's Signature Below
label | Attach Manufacturer's Report Below

## Liquid Membranes
type | name | values | prefix | postfix | usage count
checklist-flat | External (Exposed)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | Adequate fall in substrate? | Yes,No
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Installation of primer as required? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of primer
Select | Curing time for primer (hours) | 6,12,18,24
checkpoint | Substrate free from surface water - Moisture gauge photo attached below
button | Installation of fillets/bandage to junctions as required? | Yes,No
button | Installation of base coat within rquired maximum curing time of primer? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of base coat
button | Base coat installed to minimum film thickness? | Yes,No
button | Installation of UV-stable top coat? | Yes,No,N/A
checkpoint | Record (Photo) batch number and date of manufacture of top coat
button | Top coat installed to minimum film thickness? | Yes,No,N/A
button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
checkpoint | Area completed to manufacturer's specification - photos attached below
checklist-flat | External (Non-Exposed)
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint | Substrate free from surface - Moisture gauge photo attached below
button | Adequate fall in substrate? | Yes,No
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Installation of primer as required? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of primer
checkpoint | Substrate free from surface water - photos attached below
button | Installation of fillets/bandage to junctions as required? | Yes,No
button | Installation of base coat? | Yes,No
button | Base coat installed to minimum film thickness? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of base coat
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Attach Client Signature Below
checklist-flat | Internal
label | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
button | Adequate fall in substrate? | Yes,No
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Installation of tape or caulk to junctions. | Yes,No
button | Penetrations correctly detailed? | Yes,No
button | Waterstop correctly detailed? | Yes,No,N/A
button | Installation of liquid membrane to manufacturer's specification? | Yes,No
button | Installation of liquid membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint | Area completed to manufacturer's specification? - attach photos below
checkpoint | Record (Photo) batch number and date of manufacture of membrane
label | Attach Client Signature Below

## Torch-On
type | name | values | prefix | postfix | usage count
checklist-flat | Torch-On Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | Adequate fall in substrate? | Yes,No
button | Bitumen primer installed to manufacturer's specification? | Yes,No
button | Primer given adequate time to cure – as per manufacturers specification? | Yes,No
checkpoint | Area completed and suitable for membrane application - photos attached below
checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
button | Installation of base layer membrane (min. 50mm overlaps) ? | Yes,No
select | Type of second layer | Normal,Mineral,Antiroot
button | Installation of second layer membrane (min. 50mm overlaps) ? | Yes,No
button | Termination pressure bar installed to all upturns where required? | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below
label | Attach Client Signature Below

## Screed
type | name | values | prefix | postfix | usage count
checklist-flat | Screed
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Substrate cleaned & assessed for suitability to screed to - photos attached below
checkpoint | Sufficient setdown depth available to create adequate fall to wastes?
checkpoint | Substrate free from pooling or ponding water?
checkpoint | Minimum screed thickness of 20mm at waste available to achieve 1:100 fall?
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Screed mixed to manufacturer's specifications? | Yes,No
button | Slurry applied for bonding as per manufacturer's specification? | Yes,No
checkpoint | Screed completed and suitable for membrane application - photos attached below
label | Attach Client Signature Below

## Floor Coatings
type | name | values | prefix | postfix | usage count
checklist-flat | Floor Coatings
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate to be cleaned, mechanically grinded & assessed for surface uniformity - photos attached below
checkpoint | Substrate temperature is not less then 5*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | Adequate fall in substrate?
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Installation of epoxy primer? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of primer
checkpoint | Substrate free from surface water?
button | Construction joints marked for mirroring after application? | Yes,No,N/A
button | Installation of base coat? | Yes,No
checkpoint | Record (Photo) batch number and date of manufacture of base coat
button | Broadcast of non-slip application if required | Yes,No,N/A
button | Installation of top coat (UV stable if required)? | Yes,No,N/A
checkpoint | Record (Photo) batch number and date of manufacture of top coat
button | Chase out onstruction joints and caulk? | Yes,No,N/A
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Add Comment
label | Attach Client Signature Below

## Planters (hidden)
type | name | values | prefix | postfix | usage count
checklist-flat | Planter (Sheet Membrane)
checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
checkpoint | Sufficient fall in planter base?
button | Adequate fall in substrate? | Yes,No
checkpoint | Substrate free from pooling or ponding water?
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Sheet membrane installed to manufacturer's specification? | Yes,No
button | Termination pressure bar installed? | Yes,No
checkpoint | Signoff of compliant installation.
label | Attach Client Signature Below
label | Client Signature
checklist-flat | Planter (Liquid Membrane)
checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
checkpoint | Sufficient fall in planter base?
button | Adequate fall in substrate? | Yes,No
checkpoint | Substrate free from pooling or ponding water?
label | If any of these checkpoints fail please provide information and required action by builder
text | Add Comment
button | Liquid membrane installed to manufacturer's specification? | Yes,No
checkpoint | Signoff of compliant installation.
label | Attach Client Signature Below
label | Client Signature

## Testing and Handover
type | name | values | prefix | postfix | usage count
checklist-flat | ILD Testing
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
button | ILD Test Requested? | Yes,No
button | ILD Test Performed | Yes,No
checkpoint | ILD Test
label | ILD technician signature attached below
label | ILD report attached below
checklist-flat | Handover
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
label | Bravada and Client Representative name/(s) and signature/(s) attached below

## Control Joints
type | name | values | prefix | postfix | usage count | user addable
checklist-flat | Control Joints
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Channel cut to sufficient width
text | Enter width
checkpoint | Polyurethane caulk applied to channel

## Bespoke
checklist-flat | Bespoke Task
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
Button | Warrantable Works | Yes, No
text | Notes Relating To Works Performed
checkpoint | Area completed - photos attached below