## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Bentonite - Dewatering Wells |  |  |  |  | Yes | Bentonite - Dewatering Wells | 080d6970-cc12-4eae-940f-b65cecc18e4c
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f550a7cb-c537-508d-83fd-a9250d67481d |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 40b3a972-4d3f-5161-a428-cb559f07d578 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 1f8c2bce-ea01-5116-8f97-90e8cf2d3366 |  | button | PureGold Chips Installed | Yes,No
button | 52c3cb54-0b4d-5593-8aaa-4829413d992a |  | button | Builder installed Concrete Grout | Yes,No
button | 8ba63f99-8616-5168-8e87-d2ea0e5920ae |  | button | Membrane Installed? | Yes,No
button | c418ad98-22d7-5f78-b492-39f8ad042605 |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 29ea899d-1617-55b2-9188-3848e26d4f1c |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | c2fbc6fc-6437-50b2-be37-ccfcf80502d0 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 6119d18e-e310-5c1b-8120-371f5de53b0e |  | note | Attach Manufacturer's Signature Below
label | be1398e9-32f5-5cdf-a93f-c35b6d041028 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Control Joints |  |  |  |  | Yes | Control Joints | 0ef8ad36-3be0-4195-abe4-b8f16aa87775
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | b097ba48-a1f0-5c7d-a436-03ed5e139cb9 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Channel cut to sufficient width
text | 7bb300ef-eb1d-5e5b-8c03-e7d459f1c40e |  | textbox | Enter width
checkpoint-status |  |  | checkpoint | Polyurethane caulk applied to channel
checklist-flat |  |  | checklist | Bespoke Task |  |  |  |  | Yes | Add Bespoke Task | 4665cd55-8a54-4460-a291-781fb7b85210
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 302218cd-bf23-5bbc-ada9-1f1d6bf94b13 |  | textbox | Enter SOW description
button | 6907509d-4025-52d8-9bf9-e96af61e5be1 |  | button | Warrantable Works | Yes, No
text | f7b21c25-f195-522b-9a15-5bb5d33e673e |  | textbox | Notes Relating To Works Performed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
checklist-flat |  |  | checklist | Bentonite - Shotcrete Wall Membrane |  |  |  |  | Yes | Bentonite - Shotcrete Wall Membrane | 4a2066bb-0e7b-4197-b5a4-cba5c257a3ff
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f7fc91f0-297f-5500-9339-336e93605e30 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 2afa2109-005f-5f29-9fb4-6f66dad068b2 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | b099a719-6320-5814-b64e-5192d7530736 |  | dropdown | Join Coverage | 50mm,75mm,100mm,50-100mm
button | 394a889c-e232-5993-ac64-70f4b664c6de |  | button | Capping Beam Part Of Installation? | Yes,No
button | 78a78793-df02-5d7e-bb1f-c2927b9ea97c |  | button | Capping Beam Waterstop Installed? | Yes,No
select | 1877b711-474d-59f6-b66e-0840fc9bf61f |  | dropdown | Waterstop Type | RX-102,Akwaswell,Both
button | cc8e8a88-fa34-5f35-96a9-1aa785e28fbe |  | button | Waterstop to drop join installed ? | Yes,No,N/A
button | 2340af5a-66a7-513e-8f00-8f44a1004c81 |  | button | Detailing of penetrations | Yes,No,N/A
button | b4d4c174-0466-5472-9d13-68655f28d990 |  | button | Membrane Installed? | Yes,No
select | 697a1fa4-df04-5e79-9f8e-a66f7ad68fdd |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Starter bars detailed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | c8653555-9a31-531f-8334-389e2d5c764d |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 3677d367-a7cf-55b5-bc89-a965a008f743 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 6d4638b5-faec-5421-9ecf-a4fb1268b80e |  | note | Attach Manufacturer's Signature Below
label | 69e354fa-47d1-5c30-a061-5e0b4c458ad7 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | 6247ee56-0e26-4fac-8484-c4fb5223f01e
checkpoint-status |  |  | checkpoint | Handover details enterred correctly below
label | ec883553-f22c-5c0e-90ef-1fa202e9f0fd |  | note | Enter Scope Description (from Bravada SOW) and item numbers
text | 41e2424f-04d3-574d-96d8-d82fde63cc92 |  | textbox | SOW description
text | 9074ba64-ff50-593a-b452-a24300cf3f7b |  | textbox | Bravada Rep. Name
label | 09ee7040-1b26-5896-a2e2-f595d85717f6 |  | note | Bravada Rep. Signature attached below
text | 200ccd6a-7f76-57c5-8c51-80f2bd4d3916 |  | textbox | Bravada Rep. Name
label | f2f07dbe-41e6-51b2-8215-0136de4e0fd7 |  | note | Bravada Rep. Signature attached below
text | 6221252a-29de-5149-843e-2913c170a8c3 |  | textbox | Bravada Rep. Name
label | 42e563cf-d24d-59f9-9f27-e415694abdc3 |  | note | Bravada Rep. Signature attached below
text | 828536ab-1d64-5241-9c81-8c7bfe867526 |  | textbox | Client Rep. Name
label | 10cf9fab-be3f-525f-9347-b2443a23e131 |  | note | Client Rep. Signature attached below
checklist-flat |  |  | checklist | Bentonite - Wall / Slab Junction |  |  |  |  | Yes | Bentonite - Wall / Slab Junction | 626e20b3-b0b2-4dae-bccb-b8cf710873c7
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 9b3ff9b8-e162-5b44-bcb6-6519003204ee |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | b8e2b098-4d0a-56bd-8017-956a6af99190 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | 147f2b95-5d6f-541d-bdf6-9c99b84cadf3 |  | dropdown | Slab Thickness | <450mm,>=450mm
select | e718aa21-4516-55a6-a22c-233b41bcbaef |  | dropdown | No. of waterstops to install | 1,2
button | e53de806-c871-5938-a4de-f502745ab3c0 |  | button | Waterstop installed? | Yes,No
button | 91c59f30-d554-5609-9fef-e72c6a4a7b49 |  | button | Granules to junction? | Yes,No
button | 02c1db31-e751-5caa-8ac6-b2cbda744281 |  | button | Akwaswell to lowest 2 laps? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | ee3dc0a7-1a52-599e-96c9-163f88d1b09c |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | c7ca19a5-6fdd-5d46-83f9-3f370f7f9fea |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 76d66afc-a7c1-5e00-bec3-e02c0e58e80d |  | note | Attach Manufacturer's Signature Below
label | 6285ed49-425f-5073-8493-d562c0939997 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - PT Slab Wall Junction Termination |  |  |  |  | Yes | Bentonite - PT Slab Wall Junction Termination | 944be315-41a4-42bd-a966-21ce8cbc345e
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | ac09edfd-ad8f-52e6-a926-5d8e3f57b59d |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | e39608a5-5e4d-52f2-aadc-a783199d6d4c |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 9354b674-eaf7-5e9e-8d6d-c87669f9155d |  | button | Waterstop installed? | Yes,No
button | ee6bb947-da02-5be1-b686-0008d3f6edfc |  | button | Termination bar installed? | Yes,No,N/A
button | 8957a21d-eae0-59a7-958b-c26db1e7b23a |  | button | Bentoseal installed? | Yes,No,N/A
button | 86dead77-7918-5f76-b31f-2e2fde492edc |  | button | Cetinject installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 47738a49-6215-589f-8eb2-18ed1f93e34e |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 6290a343-11c5-5ecc-b6c0-68aed01876aa |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | a0bd74a7-070b-58de-8112-0132a3b0b653 |  | note | Attach Manufacturer's Signature Below
label | adf4cc6c-c495-5380-8fa2-04f5c1b0ab74 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | External (Non-Exposed) |  |  |  |  | Yes | External (Non-Exposed) | 9e1249d3-1adc-46b0-8b7a-7d5d04bae3a9
checkpoint-status |  |  | checkpoint | Scope of works details enterred correctly below
label | 77777422-b7ad-5af6-adf5-cf2bd8d2dfb4 |  | note | Enter Scope Description (from Bravada SOW) and item numbers
text | 4aba6806-3bd5-5c34-81a5-f4ac4f791e0d |  | textbox | SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity (Attach photos below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from surface? (Attach moisture gauge photo)
button | 8b842b47-1ff0-58bd-8793-005c34ddfad8 |  | button | Adequate fall in substrate? | Yes,No
label | f0ef711a-d04b-5327-b765-e8cd2efd1416 |  | note | If any of these checkpoints fail please provide information and required action by builder
button | 63be1b48-c32b-52f8-b35c-5038cbaafd01 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Attach photo)
button | cf862003-2d12-535c-b18f-d8a50424d9dd |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | a80096b3-e133-5487-b809-cc0e65feb9cb |  | button | Installation of base coat? | Yes,No
button | 7ef63625-134e-5dbd-b7fc-a5f948325f99 |  | button | Base coat installed to minimum film thickness? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? (Attach photos)
label | cef4a881-fa3c-58f3-aca3-505bacd73970 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Torch-On Installation |  |  |  |  | Yes | Torch-On Installation | aaacaa68-d24c-45d7-a3fd-7046fa6cb797
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity (Attach photos below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Attach moisture gauge photo below)
button | cafad15e-de0c-52c7-9aff-71772e4192a6 |  | button | Adequate fall in substrate? | Yes,No
button | 6aed077b-4399-5491-abe4-5fab6e5215e3 |  | button | Bitumen primer installed to manufacturer's specification? | Yes,No
button | 74935f45-79d3-5819-80f0-550caf3285b1 |  | button | Primer given adequate time to cure – as per manufacturers specification? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed and suitable for membrane application - attach photos below
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
button | ad242bc1-b42f-5695-beea-9ae9a259af26 |  | button | Installation of 2 layer membrane (min. 50mm overlaps) ? | Yes,No
button | 35dd0e0f-28f2-51ad-8392-cc042cbf2924 |  | button | Termination pressure bar installed to all upturns where required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - attach photos below
label | e2f926b8-ee0a-5ed8-b649-9cec84b1f259 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Capping Beam Waterstop |  |  |  |  | Yes | Bentonite - Capping Beam Waterstop | ad528b8e-cded-4e59-bd98-f806877f75cd
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 56e8d50f-866c-56d3-a41d-e4e825aa672e |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | d6156ca0-4de2-54ba-8475-c9a9f5ba66d1 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | aa5c56b6-7aa1-5ca6-8702-3ba12d430f9c |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 6f615b9f-4683-5e8e-ac2b-1566617b5bae |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 3d75ccf7-56f1-5972-8c49-542eb795ad1e |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 8601fa7e-737f-5c01-a18b-2c8e624b2b7d |  | note | Attach Manufacturer's Signature Below
label | 1e4756b9-19c3-52f1-8fbe-7e9b3ccdd080 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Strip/Pad Footings (Hydrostatic) |  |  |  |  | Yes | Bentonite - Strip/Pad Footings (Hydrostatic) | b78c8ed7-4d21-47a3-91ab-300843784dcb
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 7bf081e1-c24c-5b3e-811b-1b3149b84bdf |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | e3f7d5b0-4dac-5cbb-8513-83f641b722d7 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | c7f7fd00-da4a-5661-860c-40371a2678e6 |  | textbox | Notes on dewatering for Project Manager
button | 8a6fbb74-e51c-5745-b592-3a2ff90b37b1 |  | button | Granules to perimeter? | Yes,No
button | 1dc33f61-f40b-5d3f-b54e-4ce4833bcc82 |  | button | Membrane Installed? | Yes,No
select | 7080518c-68ee-5dee-963b-6502693cbcdd |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 3dadc162-4bcc-5266-8985-ac81402fb4e4 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | a4eaba62-09be-535a-bb8c-f2b012723123 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 1d96c95d-1caa-5e3a-b385-e22c5fb727bb |  | note | Attach Manufacturer's Signature Below
label | 5c7a243d-22e9-528a-8e83-0f22174fcc8f |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Anchor Boxouts |  |  |  |  | Yes | Bentonite - Anchor Boxouts | e31ea3ed-8651-47ce-af57-ec107747961d
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | aed01fa6-1068-522b-b9bf-ea74efe7c8c4 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | da088eb4-9d8f-5eaf-8b9d-36190166b1d2 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 5e5c1247-ddba-51d4-83f9-d5dd70dfe618 |  | button | Membrane, Bentoseal & waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 776b3581-00b5-5271-8e8c-289ce6e022f9 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | b59905f5-8d6f-5000-b19e-6e06fce9029b |  | button | Manufacturer Inspection Requested? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | a3c0caac-def3-5feb-b58b-eaf53dfd1186 |  | note | Attach Manufacturer's Signature Below
label | 8cb0c81b-8b94-5f80-82b9-80c6b8b68322 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Hydrostatic) | e7cbec52-67ec-4a0d-a7da-e028901d58a9
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f9d6c1fc-dc83-553f-af00-2c65a10c2f04 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 639360b0-a4d0-5046-8112-b572e02938ef |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | 4e85cba1-9a72-529e-a94d-97369707a94c |  | textbox | Notes on dewatering for Project Manager
button | 8456e406-cb1a-5307-95f8-1a1bbb42f946 |  | button | Membrane Installed? | Yes,No
select | 994fd457-eba7-55f2-bf21-1e96c7290a1b |  | dropdown | Minimum lap required | 150mm,200mm
button | 8f410aa8-294a-5106-af02-0b0a6b75cbf4 |  | button | Waterstop to pile caps | Yes,No,N/A
button | 1fe58982-e7a9-5d61-b37d-53fb5254f48e |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 4cfeea08-3b27-5c1a-af0a-8298554258ab |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 9f47bfbd-d481-55dd-995c-ade0293a6f18 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 3ea10065-7173-51bd-80fa-1493a3ac8f5f |  | note | Attach Manufacturer's Signature Below
label | 8f9add5c-5c5e-59df-9fce-9f5b5e266638 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Non-Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Non-Hydrostatic) | eadd3cae-ea14-4e0b-98ad-abff9cef0461
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | aeb46a97-9582-58c6-aaa6-62542d53403d |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | b8ccf16e-cd8f-54bd-a336-6eb1002cc3a9 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | 2fc5fc1e-5a30-5d45-8aaa-858f8c726279 |  | textbox | Notes on dewatering for Project Manager
button | e675aedc-4d0e-5a7a-99cc-7c0675365a59 |  | button | Membrane Installed? | Yes,No
select | e2bb0b7c-5c34-54e2-afa5-cbfb23397cdc |  | dropdown | Minimum lap required | 150mm,200mm
button | 7cde037b-3e74-554f-a190-f4d0ac23f046 |  | button | Detailing to pile caps | Yes,No,N/A
button | b27e7fb8-0c3b-54bf-ba56-ae72feb0a75c |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 4fd8238d-5f07-5b23-a07c-d0948c393718 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | b710af7b-a427-5822-b79c-b3dcff3e305f |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 7ed2217e-f078-517d-8c99-5413976623d2 |  | note | Attach Manufacturer's Signature Below
label | 162126c5-2536-5d56-ba3d-3aedd443d2cf |  | note | Attach Manufacturer's Report Below