## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | 0c9a6bb9-1755-4029-8a98-963c7b1a94bf
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | b0ac2ad1-34b3-539a-83d3-1b07e0079491 |  | textbox | SOW description entered
label | ec4afb64-97a1-5209-ae5a-b55b505d3bdd |  | note | Bravada and Client Representative name/(s) and signature/(s) attached below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Hydrostatic) | 10ddb764-c720-4da7-bcb9-58a177d9f80e
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 65a4d96e-a75a-58be-b0fe-e7b8d20c6ae4 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | bc40a30c-243e-588c-83fc-b6448efd8491 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | dd1ae2b5-1ea8-516f-b92e-8cff03552448 |  | textbox | Notes on dewatering for Project Manager
button | 876d6d80-df20-5536-bd09-7cd41474d3dc |  | button | Membrane Installed? | Yes,No
select | ed788219-c92b-5a38-97f2-7a052f31f039 |  | dropdown | Minimum lap required | 150mm,200mm
button | e286c77a-8b65-5049-b665-8234887afbc3 |  | button | Waterstop to pile caps | Yes,No,N/A
button | 0403bfa1-78db-5061-9dbf-18a81122b9d3 |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | f8e730ab-22b7-5314-bb56-e40337568494 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 4769acf0-a120-5ddf-be55-d7a0f6b75d3c |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | d05685b0-9cf3-5cba-a157-dca0b454d9b2 |  | note | Attach Manufacturer's Signature Below
label | 3ac45cdb-b3e2-5251-99c3-ebd5cb33448f |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | External Sheet (Non-Exposed) |  |  |  |  | Yes | External Sheet (Non-Exposed) | 1179943d-c347-4cf6-a6d0-4c9cbf93118c
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 83ddba4d-c7c5-5dc0-a7d8-d932ab66894c |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from surface - Moisture gauge photo attached below
button | 59f02d9f-db4f-5557-9059-e6b1d60e21d8 |  | button | Adequate fall in substrate? | Yes,No
label | 93f72bd9-5725-51f5-b51c-42930284b193 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 48dd6de8-9693-505e-a6f5-62e6808812aa |  | textbox | Add Comment
button | 045fff2e-ab28-51ae-9286-fc6d04e21209 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water - photos attached below
button | 509d2589-95c6-5c7f-bdc7-6511274b53e8 |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | e7ff3b77-e183-542c-9ecb-908c231e0583 |  | button | Installation of base coat? | Yes,No
button | cb3dec9f-a82d-54d3-a0e5-03d96fbe6946 |  | button | Base coat installed to minimum film thickness? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | e9d6f348-e5fc-5a34-9874-55378b0a58f5 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | External Liquid (Non-Exposed) |  |  |  |  | Yes | External Liquid (Non-Exposed) | 14192515-b3a5-43a4-8fca-6585ece87426
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f5542c98-b8d6-5a9b-9b60-76422565c7b3 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from surface - Moisture gauge photo attached below
button | ec2b4dbd-fa81-5483-b22e-ee07d8bad4bd |  | button | Adequate fall in substrate? | Yes,No
label | fb9d683b-81f8-5a1c-9057-ec4e3580005d |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 63a6a7f0-0066-5900-8543-3d287966e915 |  | textbox | Add Comment
button | f00cad24-8d06-54aa-a2a2-a67151ca5d6d |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water - photos attached below
button | 177e301e-e3ea-555c-8608-eb1ea76149cb |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | af8969d8-22fc-563e-ad65-ccdd444954f5 |  | button | Installation of base coat? | Yes,No
button | 54b5af9e-5515-56f4-8b66-8633c5e73617 |  | button | Base coat installed to minimum film thickness? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | 8d653645-f33b-5f91-9449-f6a4b11df220 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | HVAC Flashing |  |  |  |  | Yes | HVAC Flashing | 18641f71-ba60-4544-81bf-1aeddb020347
checkpoint-status |  |  | checkpoint | Removal of existing pressure bar termination
checkpoint-status |  |  | checkpoint | Supply / Installation of matching flashing termination
checklist-flat |  |  | checklist | Bentonite - Anchor Boxouts |  |  |  |  | Yes | Bentonite - Anchor Boxouts | 1a76ad9b-30c5-4dd0-b4e3-e3dbc5912ee8
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 3dbd6c9b-34d6-5fa4-a818-75474e8d845a |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | c77fe010-4ee4-5fdd-bc69-2ad882497269 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 316573f3-9a1d-5573-b8d9-44d82ff09f3b |  | button | Membrane, Bentoseal & waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | b160b821-d4f4-5e8b-8106-82de6901ea8d |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | c8fb7d8a-56f3-57ea-ace6-b2a123280280 |  | button | Manufacturer Inspection Requested? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 2ba4ee62-6ab1-5d71-a191-a0f4a5e056ab |  | note | Attach Manufacturer's Signature Below
label | f1e75566-26d1-5d12-a597-fe53edcde0ea |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | HVAC heaving repairs |  |  |  |  | Yes | HVAC heaving repairs | 2ff475c6-9b9e-441a-bd0d-70831c019134
checkpoint-status |  |  | checkpoint | Localised removal of WPM715
checkpoint-status |  |  | checkpoint | Allow substrate too dry to less than 10% moisture content
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat (incl. sand broadcast)
checkpoint-status |  |  | checkpoint | Supply / Installation of Ardex repair mortar (product depending on depth)
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat over cured repair mortar
checkpoint-status |  |  | checkpoint | Supply / Installation of UV stable sheet membrane
checklist-flat |  |  | checklist | Torch-On Installation |  |  |  |  | Yes | Torch-On Installation | 32f37158-fce1-4533-a77a-0785f0e04c44
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 05bc1194-3377-5bb0-8601-dfb19560649a |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | dbe03410-e58b-5d20-b9e8-813a79fad91d |  | button | Adequate fall in substrate? | Yes,No
button | a484ab29-6310-5ef8-96e9-9dceefd2cdfc |  | button | Bitumen primer installed to manufacturer's specification? | Yes,No
button | a8ce4268-7508-5a6d-9820-892f400ec643 |  | button | Primer given adequate time to cure – as per manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed and suitable for membrane application - photos attached below
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
button | d7ee1d2c-1bc5-55e1-aea6-9122504c77a3 |  | button | Installation of base layer membrane (min. 50mm overlaps) ? | Yes,No
select | 2429dced-d12f-56de-8953-ad03ad5a6841 |  | dropdown | Type of second layer | Normal,Mineral,Antiroot
button | ea14915d-cbfc-5882-a600-1d737d1ebd27 |  | button | Installation of second layer membrane (min. 50mm overlaps) ? | Yes,No
button | d329b150-fdc7-53d3-9b53-2355a32d4ae0 |  | button | Termination pressure bar installed to all upturns where required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | 0ded1d0c-477e-5cb0-8d10-df877cc528a1 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Wall / Slab Junction |  |  |  |  | Yes | Bentonite - Wall / Slab Junction | 47d673fb-5fe5-454d-a939-59da3bedf453
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 0eb064db-19e7-53b0-8350-adada0dbe989 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 7025bc3e-3e15-5d0a-b4a0-a3f088d737b5 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | 1a39bdfe-4053-565b-bebb-b4dbfae8e2f4 |  | dropdown | Slab Thickness | <450mm,>=450mm
select | 5c7c1bec-9fbd-5952-b7be-f7529426e7a0 |  | dropdown | No. of waterstops to install | 1,2
button | 7699adce-bf26-5891-be58-9d5be8c2cf1b |  | button | Waterstop installed? | Yes,No
button | cd9d6138-6cf7-5278-88b6-a1a17b2cb874 |  | button | Granules to junction? | Yes,No
button | 3547da49-286a-54f5-a59d-fc47ae35113a |  | button | Akwaswell to lowest 2 laps? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | bc463e54-db72-53a2-8610-52f339ffaa78 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 5e0fd8ff-f1c7-56cd-aded-408969d300d0 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | f2e3fd11-8a69-52dd-bc34-13846eafd731 |  | note | Attach Manufacturer's Signature Below
label | b1e74add-281e-5e03-bfa2-bd2199e72464 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Non-Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Non-Hydrostatic) | 4c18ac6f-956e-4fc8-833a-1dccc459afb3
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 1f308f99-bf53-5ff5-8e84-afcb801bd1a0 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 56d9ed5f-fd61-568d-a09a-e91d5524ed4b |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | e9e23db3-4fd4-500a-af63-170f2eadcbf3 |  | textbox | Notes on dewatering for Project Manager
button | 77c89c27-3163-5e1f-9ede-5b3a66ceadaa |  | button | Membrane Installed? | Yes,No
select | d507f251-6172-5968-a68d-15a8d5030e8f |  | dropdown | Minimum lap required | 150mm,200mm
button | 6a7401cf-6c5c-544f-a32d-b99bdc351c0c |  | button | Detailing to pile caps | Yes,No,N/A
button | 15685df5-1912-5baf-b179-6b601686402d |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 50eadc15-00f2-54e9-b69c-0d7ae2ec0f68 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 94e02741-8ea6-526d-bbee-a8a07204d9f9 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | e7853c94-1952-544f-a826-fbb974dd485f |  | note | Attach Manufacturer's Signature Below
label | ea4051d3-be26-599f-9bb0-2291ce771d8f |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Dewatering Wells |  |  |  |  | Yes | Bentonite - Dewatering Wells | 4ffd7a1f-4bfa-49c4-9065-ac7b501927c2
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f566a1c5-3c1c-5883-9bd7-6284cddd4ba8 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 9f3c5c58-b121-5725-9e11-a7cf6291d035 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | a7260813-e1f0-5110-96c6-69d379b9ab37 |  | button | PureGold Chips Installed | Yes,No
button | 093283bf-c2a1-5d6e-afdb-62d85c3205e2 |  | button | Builder installed Concrete Grout | Yes,No
button | 1ba209b8-b513-5a48-876f-e667a261286b |  | button | Membrane Installed? | Yes,No
button | 360984cc-b28a-5fcf-a7af-698f806e0ff4 |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | e6cd9d5a-d66a-54ef-92e5-ba63f159c3f2 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 2c3ceba7-d6b8-5c93-aa98-b5d6b2d15abd |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 66fd3717-fdb5-5829-9633-0cf644615d5a |  | note | Attach Manufacturer's Signature Below
label | 44b743eb-6c48-588f-b5d5-e6f57ac9facc |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Butynol Installation (External) |  |  |  |  | Yes | Butynol Installation (External) | 5335938c-f965-4b12-87b0-cd62bdafad69
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 70e60c1a-bc48-59a1-bdf8-39fca58a846a |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water? (Attach moisture gauge photo)
button | 90f89356-8fe9-5dfd-bdce-d65bc6e15fba |  | button | Adequate fall in substrate? | Yes,No
label | 9b083798-1e92-5b02-a42c-0fc57a83f0f5 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 57a90618-abcb-5921-b0ce-bd4e3a5d6082 |  | textbox | Add Comment
button | a64d5f7f-5bb4-5abf-8347-00f4dc4f1c01 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
button | 779c5e1f-94d9-5ce8-b8fa-2277e99b0b9c |  | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | fa98a816-3cef-5d3e-9475-c7322a5ca8f5 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | 9a8ca397-8f8f-53fd-86dd-393a2d450da6 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Internal |  |  |  |  | Yes | Internal | 57968a4d-e2e8-4313-beda-46e458010c62
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | b04847fa-a52c-5732-a343-857a52a7a3ca |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
button | 89ad7cc2-fcf5-5fa2-8b0e-7c1ce9f50571 |  | button | Adequate fall in substrate? | Yes,No
label | e36ea845-dc93-5fa7-98cb-9f4886cefdc8 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 8e3cae82-d8d1-5fc1-b563-6e0dba425d8a |  | textbox | Add Comment
button | b08dfea2-c557-5656-9af4-437981f51131 |  | button | Installation of tape or caulk to junctions. | Yes,No
button | 71d78747-1666-5f1e-b53a-002995665ba6 |  | button | Penetrations correctly detailed? | Yes,No
button | 72390178-8a43-511f-b5be-305bca3a2b0b |  | button | Waterstop correctly detailed? | Yes,No,N/A
button | 62cca217-3f3e-5015-8f3d-51eeb653338b |  | button | Installation of liquid membrane to manufacturer's specification? | Yes,No
button | eaf1aedf-07a6-52f9-86cc-99591c865963 |  | button | Installation of liquid membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - attach photos below
label | 31d01e19-2da7-5067-9368-c6e09be250c3 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Retaining Wall (Sheet) |  |  |  |  | Yes | Retaining Wall (Sheet) | 580f9ca2-ab10-4181-868e-761f83a7a897
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 64bd7617-8923-5168-9656-a7c4331b0b8f |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | 8eb419ce-e62e-5989-ab2c-f029ec9a46bb |  | button | Granules installed at cold joint? | Yes,No,N/A
button | 48ec0c39-a9b3-54a3-82fa-9c8786b67623 |  | button | Installation of sheet membrane as required? | Yes,No
button | 0e1c022c-3dbd-55d3-994b-dbbe7ac969bc |  | button | Termination pressure bar installed as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? (Attach photos)
text | 2620543b-ea90-513b-b128-773cec250b3d |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 6f8d3a4a-92b5-5e11-8eb4-ef3981248e9c |  | button | Cement sheet installed? | Yes,No,N/A
button | 3299f614-3790-561d-afcf-bbfddaff9603 |  | button | Corflute installed installed? | Yes,No,N/A
button | f44b402e-f42e-5f83-b586-a03d36d601b5 |  | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Backfilled within manufacturer's specified timeframe?
label | 3a86df96-0fe1-5cea-9f85-64889cad3d2d |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | External Liquid (Exposed) |  |  |  |  | Yes | External Liquid (Exposed) | 6ec989e4-e057-43ca-89e6-c3e752dca481
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 4998f7bf-a6c1-57e8-84d4-ce0d73b643bb |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | be2c48ae-6bd9-5ae2-ad72-3abf2e5e1390 |  | button | Adequate fall in substrate? | Yes,No
label | cbf0c469-8db1-518f-a28c-32b77a77808e |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 4cfd0687-fea7-5145-a453-36582ab066eb |  | textbox | Add Comment
button | bd85052a-ab44-573a-9ae9-d9acf80df65c |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water - Moisture gauge photo attached below
button | 1904f778-5bf9-5c58-a656-73a59cf19fd0 |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | 0c9ae91a-4dd1-5727-bac0-dc04fea975ec |  | button | Installation of base coat? | Yes,No
button | fa4a5319-8394-5ba7-9bf3-dbefd965ab0f |  | button | Base coat installed to minimum film thickness? | Yes,No
button | 642e4240-0d57-50e2-8c68-1210de6bf9ce |  | button | Installation of UV-stable top coat? | Yes,No,N/A
button | f8e584dc-842f-5e44-9560-90f0263fd0c0 |  | button | Top coat installed to minimum film thickness? | Yes,No,N/A
button | 653c1c8e-a899-5921-895c-82dd062be427 |  | button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | f0b699a6-45a0-54cc-8b30-9eac0c550a27 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Capping Beam Waterstop |  |  |  |  | Yes | Bentonite - Capping Beam Waterstop | 71838055-d272-4f75-a6a4-797bec0b8aa6
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 204a456a-b802-5de5-9425-916144de4bf7 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | a28f36c2-1669-59fd-b178-c70d296fd325 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | c0cd459e-533e-5aab-9817-d0c4ba2cb26f |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | b6c9fe04-35b5-58ae-b4ea-9782abce0f5f |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 3b2ad1fa-2dc1-5d4d-b02b-22100876b794 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | f047d248-9111-5f60-8502-fb41bac5811d |  | note | Attach Manufacturer's Signature Below
label | 314f3954-52d1-52b9-ace9-3930ed445d83 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Control Joints |  |  |  |  | Yes | Control Joints | 7362c7bd-49e8-425a-a675-00d3a8826396
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | b097ba48-a1f0-5c7d-a436-03ed5e139cb9 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Channel cut to sufficient width
text | 7bb300ef-eb1d-5e5b-8c03-e7d459f1c40e |  | textbox | Enter width
checkpoint-status |  |  | checkpoint | Polyurethane caulk applied to channel
checklist-flat |  |  | checklist | Toolbox meeting: |  |  |  |  | Yes | Add Toolbox Meeting Checklist | 78982ca4-7731-44e7-894d-1e62f355126a
checkpoint-status |  |  | checkpoint | Toolbox meeting completed & Specific Document(s) attached
text | d1b1fc58-da3b-4610-80c0-3339e6614c0c |  | textbox | Date
label | 4ddefdc2-a101-4638-b115-4a293db557ad |  | note | Site Address: 2 Vida St, Aberfeldie, VIC
text | 56842aba-7a11-4a3a-9f5b-9a5bd4664492 |  | textbox | Toolbox meeting topic
text | 05855815-bd07-4805-9fdc-c6da4789740f |  | textbox | Toolbox Item 1 - (Add any resolutions below item)
text | dcf5829a-a575-42a2-acf2-4f6eb61936d6 |  | textbox | Toolbox Item 2 - (Add any resolutions below item)
text | 07797c75-a647-4e8f-81ae-68e8b103e827 |  | textbox | Toolbox Item 3 - (Add any resolutions below item)
text | ebd33620-a3d2-4bfe-85a3-9c313ae82497 |  | textbox | Toolbox Item 4 - (Add any resolutions below item)
checkpoint-status |  |  | checkpoint | Toolbox meeting pdf attached (Add below)
label | 637ceac8-c273-46fb-9d19-40eb27c44bb3 |  | note | Bravada takes safety seriously & we encourage all persons representing the company to speak up if something is not right. If you find yourself unsure about something when it comes to safety, ASK! There is no such thing as a stupid question.
checkpoint-status |  |  | checkpoint | Sign Off – By signing this page you acknowledge your attendance of this toolbox meeting and your co-operation with our policies & procedures
holdpoint |  |  | signoff | Click to 'Add' signature's of each attendee
checklist-flat |  |  | checklist | Bentonite - PT Slab Wall Junction Termination |  |  |  |  | Yes | Bentonite - PT Slab Wall Junction Termination | 7eb7c859-0c00-47df-9ac9-529fb2ad71d5
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | a55f1e49-64c2-5638-8dc3-bb610f209474 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 1be233ab-dd54-5cb8-b6d4-58512cc7f776 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 4744c87a-c2b2-56a8-b67c-573c5fcf1d1d |  | button | Waterstop installed? | Yes,No
button | e4b742ce-d462-5d49-9bd7-431c14a4c6e1 |  | button | Termination bar installed? | Yes,No,N/A
button | 7b132194-8eb8-5f06-86d2-ff111a81da1a |  | button | Bentoseal installed? | Yes,No,N/A
button | 2feb01c8-4e93-5da7-b1b9-05d6e7cb4285 |  | button | Cetinject installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 63f8565b-55d7-5fc3-aae1-db5402ef9140 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 58625da6-70dc-5c64-ab94-6d7dff9e082c |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 17fd39e9-4fae-54ab-a755-b047446b8aae |  | note | Attach Manufacturer's Signature Below
label | be763231-7ba0-5121-b0ea-a67a203a1958 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Butynol Installation (Internal) |  |  |  |  | Yes | Butynol Installation (Internal) | 8fd61e9c-e534-4650-a478-1ded66a34555
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 7a4f83c9-72f9-5770-bd09-9c815cb30b16 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
label | 9ccf96e3-840a-503f-ac2a-d86d0e719260 |  | note | If substrate failed please provide information and required action by builder
text | 0ff865c3-49ab-5e51-a572-427ea1f98334 |  | textbox | Add Comment
button | 0170471b-1efe-5a27-bcdf-b337d92d923f |  | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | 3b6d016f-0539-51e3-8f1c-754d6025c964 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | 69f39be5-99a9-5ed2-870e-9854d21920e3 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Variation: |  |  |  |  | Yes | Add Variation | 9c770665-cbab-4840-bf0e-966b3c30c751
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | b3a57c2b-e5db-4dbb-b2fd-a1d6350ecec0 |  | textbox | Reference/Drawing/Instruction Number
text | 5da0beae-7580-4a55-837c-eb46a9a4a57f |  | textbox | Variation Area
text | 615c49e1-47c0-40fd-9110-e9a81fa06762 |  | textbox | Materials & labour breakdown (Names, Hours & Material(s)/Quantities)
checkpoint-status |  |  | checkpoint | Variation Completed
label | 21c9623a-ce87-412a-8fb1-8b9042fc2df1 |  | note | Once variation information is completed - Please SEND report to Ryman
checklist-flat |  |  | checklist | Bentonite - Shotcrete Wall Membrane |  |  |  |  | Yes | Bentonite - Shotcrete Wall Membrane | 9ed27977-68ff-445e-88bf-1b01cbd01a28
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 4116020e-eb98-5158-b950-100273950839 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | b52bac24-a7b9-5a31-9f4d-43f3686ba628 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | ef39e409-4c09-50d4-a429-48fc297692a9 |  | dropdown | Join Coverage | 50mm,75mm,100mm,50-100mm
button | 0d4aac17-d25d-5309-8d89-3984b0a8f295 |  | button | Capping Beam Part Of Installation? | Yes,No
button | 62b22e6e-ea2d-50a5-a3bf-39b07d55954d |  | button | Capping Beam Waterstop Installed? | Yes,No
select | 28c6a4cf-ec15-5027-a877-3605ae205dbd |  | dropdown | Waterstop Type | RX-102,Akwaswell,Both
button | 174ab463-a9d3-578c-a2d9-370eb52acae4 |  | button | Waterstop to drop join installed ? | Yes,No,N/A
button | 585ace39-6061-5074-825c-b9131abc623e |  | button | Detailing of penetrations | Yes,No,N/A
button | 8c7795f8-dee6-5724-91e0-1d8b0e2d0e91 |  | button | Membrane Installed? | Yes,No
select | 07c46164-b829-5d04-a45e-fec6a128a793 |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Starter bars detailed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | fb04269d-a0da-5aaa-b809-e125ca7f49cf |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | f33c9248-32ea-5020-994e-441788caf22a |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | a683dc2f-3274-5b4f-9440-28cfc939bd49 |  | note | Attach Manufacturer's Signature Below
label | ed68041f-fd09-5ce1-9cbd-a93613f6409d |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | HVAC ponding repairs |  |  |  |  | Yes | HVAC ponding repairs | b0bbd786-ba47-4df4-b468-6975f9745959
checkpoint-status |  |  | checkpoint | Localised removal of WPM715
checkpoint-status |  |  | checkpoint | Allow substrate too dry to less than 10% moisture content
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat (incl. sand broadcast)
checkpoint-status |  |  | checkpoint | Supply / Installation of low threshold epoxy screed
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat (incl. sand broadcast)
checkpoint-status |  |  | checkpoint | Supply / Installation of UV stable sheet membrane
checklist-flat |  |  | checklist | Floor Coatings |  |  |  |  | Yes | Floor Coatings | b74fdbc5-11d0-49d8-9f15-3efb8d6541ee
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | fa14180d-1e81-5698-abdb-bf283ca8d6ae |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be cleaned, mechanically grinded & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 5*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | de965c47-f92d-548d-a1c3-38de52d5f5ee |  | button | Adequate fall in substrate? | Yes,No
label | 02b0e610-9830-5399-8d03-2e78a62d44a5 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 06fc1a4b-1d2a-55f4-b691-71b9c19c96f5 |  | textbox | Add Comment
button | a0e5451d-6201-5b19-ba23-9fb32da48de1 |  | button | Installation of epoxy primer? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water?
button | 75e55f6c-6f92-5c97-8ba4-acd568f7720a |  | button | Construction joints marked for mirroring after application? | Yes,No,N/A
button | 21c186da-ec1e-51e2-8a6f-9a0dd315700a |  | button | Installation of base coat? | Yes,No
button | cbd4a0e6-ba00-59cc-86bf-1e3c2684425b |  | button | Broadcast of non-slip application if required | Yes,No,N/A
button | a6412453-25a9-5e9e-a1bc-f9beee322686 |  | button | Installation of top coat (UV stable if required)? | Yes,No,N/A
button | b27c6c36-4457-5f7a-a6fb-bb8f4b93b03b |  | button | Chase out construction joints and caulk? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | ad144663-6828-58a6-a91d-152ec738ec51 |  | note | Add Comment
label | 0f6c2c53-193d-586f-84a2-0a5f3df7740a |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bespoke Task |  |  |  |  | Yes | Add Bespoke Task | b8d2889c-58de-4960-9027-23f95c749a13
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | c5c655bc-812a-56cd-8db8-ead3d3f6d729 |  | textbox | Enter SOW description
button | 7dfb7856-51aa-52a0-a39c-28f14299cadb |  | button | Warrantable Works | Yes, No
text | 095e8e00-8304-5c90-8695-cacf2f141306 |  | textbox | Notes Relating To Works Performed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
checklist-flat |  |  | checklist | PVC Installation |  |  |  |  | Yes | PVC Installation | bc7b4871-50bf-4bba-aaf3-5f16485e5f61
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 9a06c03b-3f18-5124-9bfd-bd879a1f0c55 |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | 943ef5b1-e760-5320-9aba-e02bf0c534f6 |  | button | Adequate fall in substrate? | Yes,No
label | 17927b50-0ae1-50d2-bbbc-55a1bb113950 |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
button | 226cc09a-38ab-5b07-80bb-68f6d6a89236 |  | button | Primer installed to manufacturer's specification? | Yes,No
button | 4386d874-c5bd-56eb-8aca-50e7ce8be146 |  | button | Primer given adequate time to cure – as per manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed and suitable for membrane application - photos attached below
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
text | 1ef4ff5c-211b-5aa1-8b3b-89eabf30c7e4 |  | textbox | If inspection failed, please provide reasons and recommended course of action
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
label | 7d8c76c1-d0b6-5e53-aca5-28ad931b6c69 |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
button | 23200342-3230-5176-adcf-b92703b0f406 |  | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
button | 528c1327-4e87-533e-9def-9edd65c15342 |  | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
button | 85f9a2f9-ef40-5dc5-871f-61a836a3d161 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
button | ba5d20ed-828a-5a7d-9ed9-ca3d010a129f |  | button | Membrane Inspection Required? | Yes,No
button | c9b4e533-084d-5ef6-9e51-02f4c14fd4cb |  | button | Manufacturer Inspection Requested? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | c6075ccf-438e-56c6-a023-a10c87cc30dc |  | note | Manufacturer's signature attached below
label | f48de93a-79aa-5f42-9e29-9db8563a07a9 |  | note | Manufacturer's Report attached below
label | 12ee99ab-bc76-517f-8562-30c2658878c5 |  | note | Client Signature attached below
checklist-flat |  |  | checklist | External Sheet (Exposed) |  |  |  |  | Yes | External Sheet (Exposed) | c5c2cff1-b93e-4ec4-a732-5ff39c528c31
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 9683f7c8-830c-511e-b82c-30139569a691 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater than 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | ba87af10-0091-5c5c-9727-a75e5b3e02e1 |  | button | Adequate fall in substrate? | Yes,No
label | 0dcaf6ff-05e4-5a4c-95c3-7311adbb6901 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | c34c5850-d0aa-5110-ae89-ab94dfe82bba |  | textbox | Add Comment
button | 398d312c-6560-55c0-870f-89ec896275d7 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water - Moisture gauge photo attached below
button | 8d1e633b-8b36-5c57-a5ff-54fce1ca90c7 |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | 09515b11-ebc0-5059-9fba-3c739631d01f |  | button | Installation of base coat? | Yes,No
button | d6ea17fa-3c0b-5a84-aead-6375dfced8ec |  | button | Base coat installed to minimum film thickness? | Yes,No
button | ddfea5e3-f661-5d22-b920-714695468539 |  | button | Installation of UV-stable top coat? | Yes,No,N/A
button | 0d8bae8e-22d9-5181-888d-e6ca04ea5a25 |  | button | Top coat installed to minimum film thickness? | Yes,No,N/A
button | 6c137fb0-6551-582a-bb5e-67ac5835a9a7 |  | button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | fcca2ba9-4406-509b-b4a1-20405a36e05d |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Screed |  |  |  |  | Yes | Screed | cb46d7be-39d7-4a6a-b1e0-d14161a1d9f3
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 824d8b50-52d5-55f0-bf90-da2a9875f56d |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate cleaned & assessed for suitability to screed to - photos attached below
checkpoint-status |  |  | checkpoint | Sufficient setdown depth available to create adequate fall to wastes?
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water?
checkpoint-status |  |  | checkpoint | Minimum screed thickness of 20mm at waste available to achieve 1:100 fall?
label | bf36f36d-b3e2-5af0-93c1-fab3465ace53 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | d8216b67-715a-54ac-a238-877e92e0bbf4 |  | textbox | Add Comment
button | 7a0c15ca-3c9c-5385-b23a-59ab77d9ce4a |  | button | Screed mixed to manufacturer's specifications? | Yes,No
button | 8cfe48c0-b03b-58d3-990a-17b74bc6ef93 |  | button | Slurry applied for bonding as per manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Screed completed and suitable for membrane application - photos attached below
label | b0d8a50f-8ce7-50c1-8dac-882b63a59187 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Strip/Pad Footings (Hydrostatic) |  |  |  |  | Yes | Bentonite - Strip/Pad Footings (Hydrostatic) | e9e26816-f9a4-47c3-81a3-c0c12e87998e
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | e1698b17-d549-585c-b064-7ffe4471d1a8 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 44548e71-23ed-511c-b7f6-4a8fde9c735a |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | b140f907-e5c4-5bf1-8a1a-9f5f1af0b192 |  | textbox | Notes on dewatering for Project Manager
button | cb75b913-a18b-51a6-afbb-6e04fb9facfd |  | button | Granules to perimeter? | Yes,No
button | 3f3dfe0f-ca5c-5689-8c9e-657d0d003460 |  | button | Membrane Installed? | Yes,No
select | a3e8526d-31de-59f4-80a6-335ff35fd87c |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | e765f462-16a9-5cde-8cda-76a1c3ae3344 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 1b250b3b-3523-5345-8f82-c82c85c5a655 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | e521586b-9203-5943-bc86-4fe7feda9485 |  | note | Attach Manufacturer's Signature Below
label | dbc2c1b1-8d58-5313-a70c-6aa196faf9dd |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | ILD Testing |  |  |  |  | Yes | ILD Testing | ef35cba2-45d4-4049-8572-47354daefd59
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 25444a24-695d-5ae5-be46-43a82afa58a7 |  | textbox | SOW description entered
button | 8126a15a-8214-5a66-9a3c-7e0d79cd88a9 |  | button | ILD Test Requested? | Yes,No
button | 23b8fb88-f772-5a2e-803a-19d60c2e6a3f |  | button | ILD Test Performed | Yes,No
checkpoint-status |  |  | checkpoint | ILD Test
label | 6ed6f1ed-848d-5616-a20f-29cd3c835781 |  | note | ILD technician signature attached below
label | 83dad3f3-43e2-5cf7-b5db-bea7af604d6f |  | note | ILD report attached below
checklist-flat |  |  | checklist | Retaining Wall (Liquid) |  |  |  |  | Yes | Retaining Wall (Liquid) | f3ff12a2-0d71-4612-b3ea-67ed65008177
checkpoint-no-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 0cd1ec7f-996b-53a2-80e6-0429d713e0ac |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | 8e379a3d-5b6b-59b7-a600-b2067b4f7cf9 |  | button | Installation of liquid membrane as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? (Attach photos)
button | 55398305-2923-593a-a119-3ca7432afa95 |  | button | Cement sheet installed? | Yes,No,N/A
button | 0b485a7a-4b36-581c-9313-b0b29380e25d |  | button | Corflute installed installed? | Yes,No,N/A
button | 32d56b69-07eb-5652-838e-2f2914ee0f90 |  | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Backfilled within manufacturer's specified timeframe?
label | 45938bcb-4f66-595d-8ed4-1a73c8046804 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Entertainment area heaving repairs |  |  |  |  | Yes | Entertainment area heaving repairs | febac799-73f2-4797-9516-46183f861990
checkpoint-status |  |  | checkpoint | Localised removal of WPM715
checkpoint-status |  |  | checkpoint | Allow substrate too dry to less than 10% moisture content
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat (incl. sand broadcast)
checkpoint-status |  |  | checkpoint | Supply / Installation of Ardex repair mortar (product depending on depth)
checkpoint-status |  |  | checkpoint | Supply / Installation of epoxy hydro-static primer coat over cured repair mortar
checkpoint-status |  |  | checkpoint | Supply / Installation of UV stable sheet membrane