## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 2d6c4e84-bf93-40f8-9bf7-ce8a18d5f16d |  | checklist | Pre-Cladding |  |  |  |  | Yes | QA - Pre-Cladding | 08738175-6c31-4f26-acb5-fcf88dcc6093
checkpoint-status | 6c6acfdd-55db-42bd-90a1-876c09c1a335 |  | checkpoint | Undertray lapping at 100mm min,
checkpoint-status | 2b0d1fed-0170-4730-a615-468300e20b4d |  | checkpoint | Undertrays extend 10mm min. below all bottom edges.
checkpoint-status | bfa5bd50-b60d-4c93-b9bd-e2ca7a464ff9 |  | checkpoint | Check for unobstructed drain holes. All uncovered fixing screws to be sealed over.
checklist-flat | a645741a-5f0c-42af-8f56-d41bb8a93730 |  | checklist | Sign Off |  |  |  |  | Yes | QA - Sign Off | 15e53634-60c6-4378-a9e3-7116853504cd
checkpoint-status | 85040f00-f434-4ac6-b784-48dc35b1263f |  | checkpoint | All quality assurance issues resolved in this area.
checkpoint-status | 2d1871ec-a825-4dd2-aed6-3be2827552ae |  | checkpoint | This area is deemed to be complete and satisfactory.
holdpoint | f2f6a264-9d4e-4041-82b9-44c4acc5d843 |  | signoff | Raise Remedial / Request Sign Off
checklist-flat | 75f04531-d33e-4ae3-93bc-3457b6b9672a |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | 383dcc43-13ca-4ea3-bb67-91b10ef63653
checkpoint-status | 63a3f840-b560-43e8-8553-f80bccef5e6c |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 817173af-0fd4-5005-95e4-9e36662c74a3 | DataPoint is missing 'button' values | button | LBP Memorandum/ Record of works filled out, signed and attached
button | 875c3b22-f36b-5397-9b04-7fd172a775b9 | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation - Completed and Attached
label | 47b55924-8633-5719-b872-c4fded3b3952 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 2e481c64-b7f4-44a5-a22b-db29e1b4d7c6 |  | signoff | Request Signoff
checklist-sectioned | ddfc32c8-110b-4349-b1c1-a6b2cbadb276 |  | checklist | FC - S - Symonite Alucobond Cladding System |  |  |  |  | Yes | SYS - FC - S - Symonite Alucobond Cladding System (old version) | 5681663a-ee46-40db-a80d-528f7aa8f281
checkpoint-group | b0cb795b-0b3c-4f3c-8302-22371533011c |  | section | Pre-Start
checkpoint-status | b1c161c8-a9c0-40cd-b9d5-05cf7fef1aca |  | checkpoint | Framing Layout should provide adequate fixing points.
checkpoint-status | 235253c0-4c87-4709-ae01-d0889ed3bfaa |  | checkpoint | Check building wrap/RAB for defects
checkpoint-status | 37f8b43e-b1d9-42f9-9e29-f8ef59272221 |  | checkpoint | Check presence of all other flashings
checkpoint-group | 7e844767-8aad-415d-ad21-77e9e57de4f2 |  | section | Pre-Cladding
checkpoint-status | 4cd62993-f8f8-49d2-90ac-0dd11f721319 |  | checkpoint | Undertray lapping at 100mm min,
checkpoint-status | 1f3e7224-ac0c-433e-af33-468d01fc0757 |  | checkpoint | Undertrays extend 10mm min. below all bottom edges.
checkpoint-status | 10e97f1b-240a-4556-976b-c325c89d16d2 |  | checkpoint | Check for unobstructed drain holes. All uncovered fixing screws to be sealed over.
checkpoint-group | dca13724-97a0-4550-bbef-9fd8ff02a25b |  | section | Panel Installation
checkpoint-status | 2ade205a-0b75-40da-89a6-4f01f042587f |  | checkpoint | Fixing details. ie fixings through "WA & WB" brackets.
checkpoint-status | 877b39ea-d1f7-4698-ad7b-01daafff08c0 |  | checkpoint | Fixing/mounting brackets fitted 10g S/S screw with 35mm min. embedment.
checkpoint-status | da9641b7-ae04-43f8-992f-618fc70e60a4 |  | checkpoint | Fixings do not exceed 400mm O/C and adjusted to give a flush panel face.
checkpoint-status | 9b16e11c-c91a-4312-b9ed-eb4c243039af |  | checkpoint | Plastic H packers do not exceed 30mm total and secured by screw or sealant as necessary.
checkpoint-group | ce896926-6500-4d0c-a22b-b563380b2cee |  | section | Abutment fixings.ie fixings where panels meet surfaces other than panel.
checkpoint-status | 47d94c0a-e208-42bc-98d3-997646ece147 |  | checkpoint | At least 15mm sill(tray) to upstand cover and at least 20mm cover at jambs.
checkpoint-status | 6ad044ff-de0f-47f9-bfda-c53801ee96b1 |  | checkpoint | Fixing angle fitted to correct inset line where possible with max screw spacing of 400mm O/C.
checkpoint-status | fe150db2-c995-4d83-a2b2-78c87bdc9931 |  | checkpoint | Fall at parapet minimum 5 degrees.
checkpoint-status | 09b1610d-8f1a-41c2-8ad9-cc7fefe0d5f4 |  | checkpoint | Fixings at vertical joints are solidly packed. Back edge closer/support bracket fitted.
checkpoint-group | 5dd9b5ac-150d-41a2-993e-33fa7119d09b |  | section | Sealant
checkpoint-status | 73c5c5e8-bce7-41c8-95a3-cca92de712bb |  | checkpoint | Panel joints are have been cleaned with SikaCleaner 205 and allowed to flash off for more than 15mins but no more than 6 hrs.
checkpoint-status | 557b1eee-e78f-40bb-b41c-027b17e5f562 |  | checkpoint | Abutment joints to porous materials have been primed with SikaPrimer-3N and allowed to flash off for more than 30 mins but not more than 8 hrs.
checkpoint-status | d3e72fbe-290e-43a6-829c-3e4adce24db4 |  | checkpoint | PEF backing rod properly installed and all joints masked.
checkpoint-status | 41c7c013-2f58-47b6-a9d3-c0b6ef32c1fb |  | checkpoint | Sealant tooled off to given a flat or slightly concave finish. Inspection 24hrs. after application
checkpoint-status | 9634e970-c024-4972-9562-595711ec82b7 |  | checkpoint | Sealant colour and type - GREY, SIKAFLEX AT FACADE
checkpoint-group | 773280f2-c90d-4767-a17e-889fbe9882ce |  | section | Clean Up
checkpoint-status | fa5c99ba-b46b-4b10-ab7a-a624c9b77dfb |  | checkpoint | All masking removed and panels peeled of protective film.
checkpoint-status | f467af96-ba78-4d09-9928-bb10304d64f6 |  | checkpoint | All excess sealant and other residue removed.
checkpoint-status | 120e305d-926a-4f8e-90db-4db79f4ea6fd |  | checkpoint | All drainage holes unobstructed.
checkpoint-status | 974c121f-b735-4662-8cb1-95ce17a4795f |  | checkpoint | All rubbish removed from working area.
checkpoint-group | 0d471440-a938-4c88-940c-ef53c046a4ff |  | section | Final
checkpoint-status | e8391ad7-c2aa-401e-9e75-909705858920 |  | checkpoint | Panel layout and colours corresponds with Symonite shop drawings.
checkpoint-status | ffe5d588-0bfb-4bff-9a16-4bfff0adb597 |  | checkpoint | Check panels for visible defects. Check panel alignment(stepping etc.)
checkpoint-status | de504974-2663-4285-8fd1-32514d6aea75 |  | checkpoint | Check detailing at parapet.
checkpoint-status | ba402c00-75d5-4b82-b3e5-c09b72bc2dbf |  | checkpoint | Visually inspect seals.
checkpoint-status | 5837d7d2-9399-4b26-a9f7-fa70554e82c4 |  | checkpoint | Check all areas for unfinished clean-up.
checkpoint-group | b381d7c9-cc95-4e1c-ab5f-38503c5803e9 |  | section | Sign Off
checkpoint-status | 81653cf2-3f94-48cf-9440-62689bebddbc |  | checkpoint | All quality assurance issues resolved in this area.
checkpoint-status | 122d8bf1-47bf-40d5-ae1f-7f5e2047c4b9 |  | checkpoint | This area is deemed to be complete and satisfactory.
holdpoint | 77fc260d-57c9-4848-ada4-32e67502e4f7 |  | signoff | Raise Remedial / Request Sign Off
checklist-flat | a47508cf-dce1-4c87-911f-9be9f2b94719 |  | checklist | Sealant |  |  |  |  | Yes | QA - Sealant | 63546045-68cb-43bf-be8a-ea1261183143
checkpoint-status | eb93ea7c-6ff4-4bcb-9bc4-07e579c114d4 |  | checkpoint | Panel joints are have been cleaned with SikaCleaner 205 and allowed to flash off for more than 15mins but no more than 6 hrs.
checkpoint-status | 3981aaac-18ac-483e-8c86-6c2c4b7dc2a6 |  | checkpoint | Abutment joints to porous materials have been primed with SikaPrimer-3N and allowed to flash off for more than 30 mins but not more than 8 hrs.
checkpoint-status | eb0083cd-995e-4d97-bb51-e0d8d5b15038 |  | checkpoint | PEF backing rod properly installed and all joints masked.
checkpoint-status | a5cd9ded-d3b3-426b-bbdb-b4b2444c0934 |  | checkpoint | Sealant tooled off to given a flat or slightly concave finish. Inspection 24hrs. after application
checkpoint-status | 11c75973-cc25-40b5-bd80-a120b4451157 |  | checkpoint | Sealant colour and type - GREY, SIKAFLEX AT FACADE
checklist-flat | 7ca5b01c-ba94-405d-a204-253aba67b123 |  | checklist | Pre-Commencement Checklist |  |  |  |  | Yes | Pre-Commencement Checklist | 7aa82848-3cd2-471b-ae28-7bf32b2d3ed6
checkpoint-status | 34a99842-218a-4d3e-9d4f-bd2aa2b87d7d |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status | 7811e19a-49ea-4cf6-9ca4-02537a814117 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | e303f181-c888-453f-8726-1fc972b1ad59 |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Ryman
checkpoint-status | 5fcc2529-f5e2-4e45-906a-1488277a4de8 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | eca67d57-847a-4942-b97b-cc590f618b5b |  | checkpoint | Review Access Granted to Ryman & Relevant Parties
checkpoint-status | 4a3d4428-7f20-4b57-9293-d5ffe4ba89b3 |  | checkpoint | Matrix/Insights Setup (if required)
checklist-flat | b3a2c27e-4bd7-4964-a23e-b9e61eb8adda |  | checklist | Final |  |  |  |  | Yes | QA - Final | 89f4fe60-26f3-4a2c-bb79-f1c7725be0d9
checkpoint-status | a6aa67e3-10b6-4079-a0b5-821ad73756d8 |  | checkpoint | Panel layout and colours corresponds with Symonite shop drawings.
checkpoint-status | 4321a910-e914-4d11-a6cc-51356698ce07 |  | checkpoint | Check panels for visible defects. Check panel alignment(stepping etc.)
checkpoint-status | edfe3263-c8ce-4828-b116-0abc9b026a82 |  | checkpoint | Check detailing at parapet.
checkpoint-status | 9b6e4d8e-2195-4905-8ba9-2e1b8b274051 |  | checkpoint | Visually inspect seals.
checkpoint-status | 696f7193-7503-48c5-9f89-91bd05167c37 |  | checkpoint | Check all areas for unfinished clean-up.
checklist-flat | d0644f38-406f-4c3e-a594-b1dd75f1a782 |  | checklist | Clean Up |  |  |  |  | Yes | QA - Clean Up | b725ecca-4b65-49fb-b9c8-872e7f2ffc64
checkpoint-status | 70b6f9b2-1316-447f-85e8-9c342b4f790d |  | checkpoint | All masking removed and panels peeled of protective film.
checkpoint-status | 0fc1b1dd-0706-44dd-bd65-8a9920312aa6 |  | checkpoint | All excess sealant and other residue removed.
checkpoint-status | d16860a1-73b2-48ee-bd9a-0879fb37f872 |  | checkpoint | All drainage holes unobstructed.
checkpoint-status | 925b1b8c-6154-4a72-b8f8-84f11f61ae69 |  | checkpoint | All rubbish removed from working area.
checklist-flat | d9653b5e-141c-4a48-83dc-675379887fc3 |  | checklist | Pre-Start |  |  |  |  | Yes | QA - Pre-Start | d757c126-0137-4dd2-ad32-dfccef346a38
checkpoint-status | da2bf918-dce3-458b-a79d-aebcd37f2dd6 |  | checkpoint | Framing Layout should provide adequate fixing points.
checkpoint-status | bb197ace-fac0-4fe3-8f96-a754547a5d97 |  | checkpoint | Check building wrap/RAB for defects
checkpoint-status | 4e68244b-00d7-4cd6-ac7a-91f64bfc2e30 |  | checkpoint | Check presence of all other flashings
checklist-sectioned | cb62d56f-65de-4dac-8874-c0b0418c9d65 |  | checklist | Panel Installation |  |  |  |  | Yes | QA - Panel Installation | e5577b0a-0c56-4a90-98ea-00799770d999
checkpoint-group | d8df2aba-34ed-417a-830f-bd2036c98535 |  | section | Fixing details. ie fixings through "WA & WB" brackets.
checkpoint-status | e7b6a926-4a38-4362-9753-5c19e8a541ba |  | checkpoint | Fixing/mounting brackets fitted 10g S/S screw with 35mm min. embedment.
checkpoint-status | 01e38097-9d2f-4694-afc6-03bae7f28f05 |  | checkpoint | Fixings do not exceed 400mm O/C and adjusted to give a flush panel face.
checkpoint-status | 3f5bef9f-db9c-4beb-8ad3-ebce99f7c96f |  | checkpoint | Plastic H packers do not exceed 30mm total and secured by screw or sealant as necessary.
checkpoint-group | 21c4283a-a207-49d2-8957-504c0b324ef4 |  | section | Abutment fixings.ie fixings where panels meet surfaces other than panel.
checkpoint-status | d8729935-1545-4424-bdfb-0a21beda0943 |  | checkpoint | At least 15mm sill(tray) to upstand cover and at least 20mm cover at jambs.
checkpoint-status | 4eae53fc-4e0a-41b1-a099-7aea2a289755 |  | checkpoint | Fixing angle fitted to correct inset line where possible with max screw spacing of 400mm O/C.
checkpoint-status | ad65820f-f156-4ce8-ac0e-c37c9c695f0f |  | checkpoint | Fall at parapet minimum 5 degrees.
checkpoint-status | 356e6ea6-1a16-4f01-ac6a-60afe3a26a8d |  | checkpoint | Fixings at vertical joints are solidly packed. Back edge closer/support bracket fitted.