## ITP COVER PAGE
Ducting & Pit Inspcection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - DN1211-ITP-003 - Rev IFC-04
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Wellesley St Bus Interchange - WSBI |  |  |  |  | ITP Number: |  |  | DN1211-ITP-003
Project Number: |  |  | DN1211 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Earthworks (Excavation, Subgrade and Sub-Base) |  |  |  |  | Revision: | 1000 |  | IFC-04
Contract Number: |  |  | WSBI |  |  |  |  | Drawing Sets:
Customer: |  |  | Auckland Transport |  |  |  |  | Specification:
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | For Review | 2024-08-29 |  | R.Collier |  | Compiled draft |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | IFC | 2024-09-09 |  | R.Collier |  | For construction |  |  |  | C | Check |  | DES | Designer
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
2 | IFC | 2024-09-09 |  | R.Collier |  | For Construction |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
3 | IFC | 2025-09-24 |  | R.Collier |  | For Construction |  |  |  | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
4 | IFC | 2025-10-08 |  | R.Collier |  | For Construction with updated optimisation as per DN1211-Aurecon-RFI-R-0262 |  |  |  | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer CM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) |  | AT/MSQA | [5 empty] | Client (If Applicable) |  | AT/MSQA

## ITP
[7 empty] | ITP- | Earthworks (Excavation, Subgrade and Sub-Base)
[7 empty] | Project- | WSBI - 1211
[7 empty] | ITP No.- | ITP-003
[7 empty] | Revision- | Rev-04
Item No. | Inspection and Test Point | Acceptance/Conformance criteria | Standard/Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Engineer Rep Signature (Blank as req.) | MSQA (Blank as req.) | Comments/Closeout Details
SECTION 3 - PRE CONTRUCTION (P&G/ESTABLISHMENT)
Before You digs provided in -
SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
Aggregate MAR Provided in -
SECTION 5 - CONSTRUCTION ACTIVITY
Site Clearance
5.1 | Demolition and removal of obstructions | Submit works over approvals for Relevant NUO's where utilities found. Confirm approval to remove structure or protection requirements as per Aurecon DRG's | Aurecon Civil Spec 4.5.5 | Email confirmation where applicable or works over permit algining with the consent | Upon Discovery (May not be Applicable) | H | PE | H |  | I
Excavation
5.2 | Subgrade Testing | Contractor to Confirm subgrade strength and report to Engineer via Inspection. Clegg to be ≥ 10 value. Refer DN1211-AURECON-GCO-0155 | Aurecon Civil Spec 5.6.11 | QA sheet | Every 20m or as agreed by the Engineer | H | SE | H |  | R | I
5.3 | Line and Level of subgrade | Pavement Subgrade tolerance +/-10mm from design subgrade level (or as applicable with existing services). Excavation depth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out. To be verified on site. | Aurecon Civil Spec 5.6.9 | As builts | Each Subgrade section | H | PE | H |  | R | W
Sub-Base
5.4 | Sub-Base Level and Shape | Construct lifts between 2.5 to 5X maximum stone size to ensure good compaction (100-200m). Surface shape, finished and tolerances shall comply with requirments of TNZ B/02- -25mm/+5mm to design FL measured between centreline and pavement edge | Aurecon Civil Spec 6.7.4 TNZ B/2 | QA cheetsb and as built survey | Every 10m for each section of basecourse | H | SE | H |  | R | I
5.5 | Sub base Compaction | Clegg testing of Sub-base course to achieve CIV 25+ Refer- DN1211-Aurecon-GCO-0013 | Aurecon Spec 6.1 and GCOR-0042 | QA sheets | Every 10m for each section of basecourse | H | SE | H |  | R | R
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.1 | Redline Drawings | Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen | Downer | Redlines | Post Construction | H | ENG | H |  | H | R
SECTION 7 - SIGN OFF
|  | Customer Release Granted: |  | ☐ Yes | ☐ No | Date:
Certificate Number: