## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-092-CIV-PSDS-Fencing
ITP Number |  | 092
ITP Description: |  | PSDS-Fencing
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-02-26
ITP created by: |  | Nathan Cooper
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | Progress Street
Inspection & Test Plan
[9 empty] | Revision: | 0
[9 empty] | Date: | 2024-02-26
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings L1-CHE-STD-005 L1-CHE-STD-025 VicRoads Section 610 VicRoads Section 630 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings Section 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Steel Columns, Cladding, Handrails, etc | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings | Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. | Visual |  | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.4 | Fence Post Foundation | IFC Drawings | 32MPa concrete. Footings as per IFC drawings or standard design to match existing. Refer to IFC drawing for reinforcement details. | Measure | Each footing | IP | SE/Site Supervisor | Post and concrete dockets
4.5 | Fence Post Installation | IFC Drawings | Maximum post spacing to be 3.25m ± 250mm. | Measure | Each post | IP | SE/Site Supervisor | This ITP
4.6 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh to match existing and or IFC drawings | Visual | Each element | IP | SE/Site Supervisor | This ITP Delivery dockets
4.9 | Gate Post Foundation | IFC Drawings | As per standard drawings and or IFC drawings | Visual/Measure | Each footing | IP | SE/Site Supervisor | Post and Concrete Dockets
4.10 | Gate Installation - Post | IFC Drawings | As per standard drawings and or IFC drawings | Measure | Each Post | IP | SE/Site Supervisor | Delivery Dockets
4.11 | Gate Installation - Gate | IFC Drawings | As per standard drawings and or IFC drawings | Measure | Each Gate | IP | SE/Site Supervisor | Delivery Dockets
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /