## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-092-CIV-PSDS-Private Property Fencing | itp |  |  |  |  | ITP-092-CIV-PSDS-Private Property Fencing Rev 1 | 5aeb5a02-a825-4ad5-a219-9267f083e13a
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-092-CIV-PSDS-Fencing
label | ITP Description: PSDS-Fencing
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 26/02/2024
label | ITP created by: Nathan Cooper
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
section | Materials
checkpoint | 2.1 Concrete
label | REFERENCE: IFC Drawings Section 610.07 Table 610.071
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings.
label | METHOD: Document Review
label | FREQUENCY: Each Mix
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | REFERENCE: IFC Drawings AS41000, AS1163
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a grade of C250
label | METHOD: Document review, Visual and Measure
label | FREQUENCY: All elements
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | ○ Offset checked against the running edge prior to installation of posts.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Excavation works
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | ○ Follow asset owners guidelines for work around their service.
label | METHOD: Visual
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Ground Conditions
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | METHOD: Visual
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Fence Post Foundation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 32MPa concrete.
label | ○ Footings as per IFC drawings or standard design to match existing.
label | ○ Refer to IFC drawing for reinforcement details.
label | METHOD: Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Post and concrete dockets
date | Date Completed:
checkpoint | 4.5 Fence Post Installation
label | REFERENCE:
label | ACCEPTANCE CRITERIA: IFC Drawings
label | METHOD: Maximum post spacing to be 3.25m ± 250mm.
label | FREQUENCY: Measure
label | CATEGORY: Each post
label | RESPONSIBILITY: IP
label | VERIFYING DOCUMENTS: SE/Site Supervisor
date | Date Completed:This ITP
checkpoint | 4.6 Chain Wire Mesh Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Chain-wire mesh to match existing and or IFC drawings
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP, Delivery dockets
date | Date Completed:
checkpoint | 4.9 Gate Post Foundation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | METHOD: Visual/Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Post and Concrete Dockets
date | Date Completed:
checkpoint | 4.10 Gate Installation - Post
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | METHOD: Measure
label | FREQUENCY: Each Post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
checkpoint | 4.11 Gate Installation - Gate
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | METHOD: Measure
label | FREQUENCY: Each Gate
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP