## Reinforced Slope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004B - White Pine Bush Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Reinforced Slope (Rock Bolts, Soil Nails) |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: B1004B |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEB-SH2SOUTHHAWKESBAY/ERnXVj7oe-hIkxzokMbxu5YBhT8u9yWaIH0IhUCmYfzZMw?e=WXofSt |  | Compliance with Work Instructions and Specifications
Detailed Location: White Pine Bush Underslip
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1. Minor Earthworks
1.1 | Clearing & Earthworks | H | Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed | Prior to commencement | Visual Inspection | In accordance with TNZ F/1 | Photos | Site Engineer | CPS Engineer
1.2 | Cut/Fill Required | H | Any excavation and filling required is to be carried out. Excavation should be kept to a minimum | Prior to commencement | Visual Inspection | In accordance with TNZ F/1. | Photos | Site Engineer | CPS Engineer
2. Material Production
2.1 | Material Compliance (Rock Works) | H | Material to meet specifications dependant on material type selected | Source test of each material used (minimum 10 rocks per source) | Document Review | 1. Schmidt Hammer test (minimum of 10 rocks per source) and 90% result ≥ 50 in all direction or 2. Weathering resistance AA,AB, BB or CA (NZS4407) 3.Specific of gravity ≥ 2.56 or up size rock to compensate 4. maximum dimension of any rock ≤ 3 times narrowest dimension | Lab Reports, delivery dockets | Site Engineer | CPS Engineer
2.2 | Material Compliance (Rock Works) | W | Consistency though construction and clean of dirt | Each rock source | Monitor on site | Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken | Photos | Site Engineer
2.3 | Material Compliance Subsoil | W | Material to meet specifications | Each rock source | Supplier certification and delivery dockets | Prior to megaflow installation | Collect all delivery dockets and photos | Site Engineer
2.4 | Material Compliance and Methodology Approval | H | Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings | Prior to commencement | Document Review | Grade 500E soil nail Class II corrosion protection Lengths and diameters shown on drawings are the minimum required | Delivery Docket | Site Engineer | CPS Engineer
2.5 | Concrete Quality Plan and Work Plan | H | Concrete Quality Plan and Work Plan | Prior to commencement | Submission | Refer to section 8.3.1 for the Contract Quality Plan and Section 8.3.2 for the Work Plan "Including: - Name, qualification and experience of concrete works inspector - Form and content of concrete placement card" | Email / RFI | Site Engineer | CPS Engineer
2.6 | Concrete Supply Plant Approval | W | Details of concrete supply plant, copy of certificate of audit for plant | Three weeks prior to pouring concrete | Submission | Including: - Plant test Results - ASR Compliance Records | Email / RFI | Site Engineer
2.7 | Reinforcement Steel Certification | W | Reinforcing steel manufacturers test reports and certificates | Prior to undertaking works | Submission | Including despatch records | Email / RFI | Site Engineer
2.8 | Concrete Mix Designs | H | Submit all concrete mix designs, trial mixes and compliance records | Three weeks prior to pouring concrete | Submission | Mix Design to be approved by CPS Engineer before commencing construction | Email / RFI | Site Engineer | CPS Engineer
2.9 | Grout Mix Design | H | Test to be carried out on Grout mix before it is ordered for construction | Prior to commencement | Testing | Mix design to be approved by CPS Engineer three weeks before commencing construction | Test results to CONQA Procore | Site Engineer | CPS Engineer
2.1 | Grout Mix Check - On-site | W | Grout checked if its free from lumps & segregation | Prior to commencement | Visual Inspection |  |  | Site Engineer
2.11 | Alternative Drilling Fluid | H | Request for use of alternative Drilling Fluid (Section 7.5.2) | Prior to Commencement | Submission | If required |  | Site Engineer | CPS Engineer
3. Soil Nails Installation
3.1 | Survey Setout | H | Arrange for a set out survey to be carried out & check against design drawings including sacrificial nails | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer | CPS Engineer
3.2 | Soil Nail Construction Methodology | H | Soil Nail construction methodology plan must be submitted two weeks prior to works starting | Prior to commencement | Submission | Include sprayed concrete, grouting and tremie concrete in methodology | Methodology | Site Engineer | CPS Engineer
3.3 | Trial installation of Sacrificial Nails | H | Drill hole, install Bolt/Nail, install Grout. Location for Sacrificial Soil Nails to be agreed on Site with CPS Engineer. | Test | Visual Inspection/ Document Review | Bore logs of Drilling, installation record | Records | Site Engineer | CPS Engineer
3.4 | Sacrificial Nail Testing | H | Test after a 7 day period. Load up to the specified requirements with the CPS Engineer overseeing proceedings | Test | Visual Inspection/ Document Review | Design Team to approve grout test result prior to sacrificial testing being commenced. Calibration of testing equipment CPS Engineer to observe testing and provide feedback. | Instruction to proceed | Site Engineer | CPS Engineer
3.5 | Working Bench | H | The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times. | Prior to commencement | Measure |  | Photos | Site Engineer | CPS Engineer
3.6 | Production Nails Location | H | Location of all Test Nails to be agree on site (Section 7.8.1) | Prior to Trial | Inspection |  | Photos, Site Diary | Site Engineer | CPS Engineer
3.7 | Production Soil Nails Bore Hole Drilling | W | Drill hole | During construction | Submission | +/- 2 Degrees Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any. Submit all installation records for each soil nail and pile. | Drill Logs, submission records | Site Engineer
3.8 | Bore Hole Flushing | H | Flush all soil nail holes with water and air after drilling to remove smear and drilling debris | During Construction | Visual Inspection |  | Photos | Site Engineer | CPS Engineer
3.9 | Soil Nails Insertion | H | Insert soil nails as specified | During Construction | Visual Inspection | Soil nails must be inserted into the drill hole to the required length without difficulty to prevent damage | Subcontractor QA Records | Site Engineer | CPS Engineer
3.1 | Soil Nail Logging | W | A record is to be maintained showing the type and installation date for each soil nail | During Construction | Submission | Installation records shall include: - Length of bar - Depth of drill hole - Inclination/Verticality achieved - Level of grout placed - Batch numbers associated with grout placed in each hole | Subcontractor QA Records | Site Engineer
3.11 | Grouting | H | Install Grout. Install Grout on the same day of drilling unless otherwise approved by Designer | During Construction | Visual Inspection | Including : - Concrete despatch records - Compression test results - Slump and spread test reports Must notify CPS for any failed result and cease works until resolved | Subcontractor QA Records and Photos | Site Engineer | CPS Engineer
3.12 | Grout Sampling | H | Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch | During Construction | Testing | Must reach specified minimum 7-day and 28-day compressive strengths | CONQA | Site Engineer | CPS Engineer
3.13 | Grout Loss Recording | W | Loss of grout shall be monitored and recorded for each hole during and immediately after grouting | During Construction | Submission |  | Subcontractor QA Records | Site Engineer
3.14 | Bolts/Washer/Nuts Installation | H | Install Bolts/Nails washers & nuts | During Construction | Measure | All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed. | Delivery Dockets | Site Engineer | CPS Engineer
3.15 | Testing of Soil Nails - Each Row | H | All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified | After Construction | Submission | Certifications of all testing equipment within the last 3 months | Certifications | Site Engineer | CPS Engineer
3.16 | Testing of Soil Nails - Minimum Resting Period Before Testing | H | Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved | After Construction | Measure |  |  | Site Engineer | CPS Engineer
3.17 | Testing of Soil Nails - Testing Specs | H | Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2) | After Construction | Testing | Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails | Test results to CONQA Procore | Site Engineer | CPS Engineer
3.18 | Final Inspection Before Next Row Commencement | H | Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails | After Construction | Document Review | CPS Engineer to give approval via a NTC | Email | Site Engineer | CPS Engineer
3.19 | Subsoil Drainage | W | Install subsoil drainage as required in accordance with specification | During Construction | Document Review | As per drawing 1.5m alternate with weep holes | Photographs | Site Engineer
3.2 | Shotcreting | W | Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened | During Construction | Visual Inspection |  | Photos | Site Engineer
3.21 | Pre-Shotcreting Inspection | H | No concrete shall be placed until the CPS Engineer has had the opportunity to ensure the drawings and specification have been complied with . 48 Hours notice required. | During Construction | Visual Inspection | Compliance with Drawings and Specification | COR/Email /Photos | Site Engineer | CPS Engineer
3.22 | Shotcrete Minimum Application Requirements | W | Apply shotcrete - 200mm Nominal thick (Vertical). Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal) | During construction | Visual Inspection |  | Photos | Site Engineer
3.23 | Shotcrete Compression Testing - Core Test | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores | After Construction | Visual Inspection |  | Test results to CONQA Procore | Site Engineer | CPS Engineer
3.24 | Final Inspection - Each Shotcrete Soil Nails Row | H | Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m | After Construction | Visual Inspection | Surface Inspected by CPS Engineer & Approval given to carry on with works | Email | Site Engineer | CPS Engineer
4. As-built Requirements
4.1 | Post Construction Survey | H | Survey final position of bolts for as-built purposes | At completion of Lot | Visual Inspection | Survey report complete and conforms to specification | Survey receipt | Site Engineer | CPS Engineer
4.2 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
4.3 | Subcontractor Quality Assurance | W | All subcontractor documentation to be included in QA file | At completion of Lot | Document Review |  | Subcontractor QA Records | Site Engineer
4.4 | As-built | H | Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file | During and at completion of work. | Survey / Drawings |  | Survey receipts, As-built plans | Site Engineer | CPS Engineer
4.5 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer | CPS Engineer
4.6 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: