## Driven Pile
[5 empty] | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
[5 empty] | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
[5 empty] | Procedure: | F3002G - Driven Pile and concrete buttress |  | Name / Signature | Name / Signature | Site Engineer
| Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
| Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: F3002G - Mangahuini Sheet Pile Wall Pile Bracing Construction
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
| 1 | Survey Setout | H | Set out line of pile as per contract drawings and specification. | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer | CPS Engineer
| 2 |  | W | Any services in the area are to be clearly marked before any work commences and to be potholed to confirm their location | Prior to commencement | Survey |  | Site record sheet/Daily diary | Site Engineer
| 3 | Material Compliance | H | Driven piles to be 310UC137 | Prior to commencement | Document review | AS/NZS3697.1 & NZS3404;1997 | Data sheets and mill certificates | Site Engineer | CPS Engineer
| 4 |  | H | Walers to be 200UC52.2 | Prior to commencement | Document review | AS/NZS3697.1 & NZS3404;1997 | Data sheets and mill certificates | Site Engineer | CPS Engineer
| 5 |  | H | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade 300 as shown on the drawings | Prior to ordering steel | Document review | AS/NZS4671&NZS3109 | Detail Sheets and Mill Certificates | Site Engineer | CPS Engineer
| 6 |  | H | Any welding or mechanical splicing to be approved in writing by the CPS Engineer | Prior to welding or splicing | Document review | AS/NZS1554 part 3 | Mark Up As Built Drawings | Site Engineer | CPS Engineer
| 7 |  | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer | Prior to cutting or bending on site | Document review | NZS3109;1997 | Mark Up As Built Drawings | Site Engineer | CPS Engineer
| 8 | Pile Line | H | Check if the bench has been excavated/filled can accommodate the entire pile line | Prior to Commencement | Visual Inspection | Relevant Drawing & Survey set Out | Site visit agreement | Site Engineer | CPS Engineer
| 9 | Driving Operations | W | Check driving performance, verticality and position | Each Pile | Visual Inspection | Piles to be drive vertical checked with a spirit level | Piling Specification, Relevant Drawings Pile Card | Site Engineer
| 10 | Testing | H | Ensure penetration depth of 3.8m is achieved | Each pile | measurement/visual inspection | 3.8m embedment in river bed in acordance with Design Depth | Pile Card record | Site Engineer | CPS Engineer
| 11 | Reinforcement Cage | W | Check supply and installation of reinforcement cage | Each cage | Document Review & Visual Inspection | NZS 3109 and being in accordance with the drawings, ensure cover of 50mm from face of formwork | Reinforce cage record and site photographs | Site Engineer
| 12 |  | H | Arrange for inspection of installed reinforcement cage | Prior to placing concrete | Visual Inspection | In accordance with the drawings ensure cover of 50mm to formwork and 40mm cover to piles and waler | site photographs/ inspection report | Site Engineer | CPS Engineer
| 13 | Formwork | W | Ensure formwork is competent to contain the required volume of concrete | Prior to placing concrete | Visual Inspection | 50mm cover to reinforcing. Formwork is straight and true | site photographs/ inspection report | Site Engineer
| 14 | Concrete Pumping Operations | H | Concrete required is a 30Mpa mix design required for a pump mix is 13mm aggregate for pumping | Prior to commencement | Document review | Concrete Mix design acceptance | concrete mix design approval prior to comencement | Site Engineer | CPS Engineer
| 15 | Concreting | H | Pre-pour inspection and check sheet is required prior to comencement | Prior to concrete pour | Visual inspection | Concrete Inspection check sheet sign of | Concrete check sheet signed off | Site Engineer | CPS Engineer
| 16 |  | H | Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets | Prior to concrete pour | Test Results | NZS 3104 | Concrete docket & Concrete test results | Site Engineer | CPS Engineer
| 17 |  | H | Post-pour inspection and Check sheet for concrete placement method and finish | At completion of pour | Visual Inspection, Document Review | Concrete Inspection Record | Concrete check sheet signed off | Site Engineer | CPS Engineer
| 18 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer | CPS Engineer
| 19 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Asbuilts, NCR's and RFI's | Site Engineer
| 20 | Completion Sign Off From Fields Below | H |  |  |  |  | Signatures | PM | CPS Engineer | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: | [5 empty] | Signature: |  |  | Date:
| QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: