## ITP
[5 empty] | Inspection Test Plan |  |  | Approved / Signature
[5 empty] | Contract Name: | F5001A Hicks Bay Slip Repair |  | GHD Approver | Quality Approver | GHD Eng. | Fred Rewa / Dave Larsen
[5 empty] | Procedure: |  |  | Name / Signature | Name / Signature | Site Engineer | Amritpal Singh
| Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Jose Buernventura
| Lot No:F5001A |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:SH35 RS132 –RP 3.394
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | GHD Engineer Initials (Grey if not required) | Date(s)
Section 1: Materials Compliance - RECEIVING INSPECTIONS
| 1.1 | Rock Armour, 2 tonne rock class (D0.7m to 1.5m) | W | Hicks Bay SH35 Slip Repair-1253342-Q002 | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D700 to 1500 with a minimum specific Gravity SG of 2350kg/m3. | Material source test results, Delivery dockets | Site Engineer
| 1.2 | Granular Backfill - AP65 | H | Hicks Bay SH35 Slip Repair-12533432-G002 | Prior to commencement | Supplier material test certificate | Shall be free draining, hard, durable, well graded, crushed granular material such as AP65 with a fines content <5% with more than 2 broken faces. It shall be free from organic and vegetative material and compacted to achieve 90%MDD. Compaction maybe checked by clegg hammer. | Material source test results, Delivery dockets | Site Engineer | GHD Engineer
|  |  | H | Hicks Bay SH35 Slip Repair-12533432-G002 | Prior to commencement | Laboratory Test Results | Address of the source quarry. The geological description of the parent material. Particle Size Distribution (PSD) Test, Compaction Test and Broken Face Percentage Test Results from a Representative, General Fill Sample Tested in an independent and accredited Laboratory | Laboratory Test Results | Site Engineer | GHD Engineer
|  |  | H | Hicks Bay SH35 Slip Repair-12533432-G002 | Prior to commencement | Laboratory Test Results | Results of Compaction Tests as Specified in NZS 4402:1988 - Test 4.1.1 or Test 4.1.3 are to be carried out on the proposed backfill and the results presented to the engineer for agreement prior to construction. These are to clearly show the Optimum Moisture Content and Maximum Dry Density Achieved | Laboratory Test Results | Site Engineer | GHD Engineer
| 1.3 | Geotextile Filter Fabric Bidim A64 (or under Rock Rip-Rap on Culvert Outlet Scour protection | W | Hicks Bay SH35 Slip Repair-12533432-C003 | Prior to commencement | Manufacturers certificate | NZTA Strength Class C. Filtration Class 1 - Bidim A64 Geotextile or an approved equivalent - compliant placed under Rock Rip-Rap | Material compliance cert, Photo's | Site Engineer
| 1.4 | Deep Rock Rip-Rap (300mm-500mm dia.) | W | Hicks Bay SH35 Slip Repair-12533432-C003 | Prior to commencement | Supplier material test certificate | Apron for Scour Protection at Culvert Outlet | Material source test results, Delivery dockets | Site Engineer
| 1.5 | Guard railing | W | Hicks Bay SH35 Slip Repair-12533432-C004 | Prior to commencement | Manufacturers certificate | Guard railing system to be installed to manufacturers specification. see ITP for Guard Rail | Manufacturers spec, Delivery dockets | Site Engineer
| 1.6 | Precast RCRRJ 525 dia. pipe | H | Hicks Bay SH35 Slip Repair-12533432-C003 | Prior to commencement | Submission | Delivery Dockets are collected and signed before precast pipe materials are removed from the truck. Class 4 RCRRJ 525 pipe to comply with AS/NZS 4058 | Manufacturer cert, Delivery dockets, Photo's | Site Engineer | GHD Engineer
| 1.7 | Precast materials | H | F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001 | Prior to unloading | Visual inspection | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Manufacturer cert, Delivery dockets, Photo's | Site Engineer | GHD Engineer
| 1.8 | Hynds Mountable Wingwall for Culvert Inlet or similar approved by Engineer | H | Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1 | Prior to unloading | Visual inspection | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Manufacturer cert, Delivery dockets, Photo's | Site Engineer | GHD Engineer
| 1.9 | D1050mm Concrete Pre-cast Manhole with concrete lid | H | Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1 | Prior to unloading | Visual inspection | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Manufacturer cert, Delivery dockets, Photo's | Site Engineer | GHD Engineer
| 1.1 | AP40 (Basecourse) or approved basecourse modification | H | TNZ M/4 Section 3.2 & 3.3 | 1/source and at least 1/3 months | Submission | Particle Size Distribution, Plasticity Index, Soak CBR, Crushing & weathering resistance, Clay Index, Sand equivalent | Material Source testing and approval, Delivery dockets | Site Engineer | GHD Engineer
| 1.11 | AP65 (Sub-base) | W | NZTA | 1/source and at least 1/3 months | Submission | Particle Size Distribution, Maximum Dry Density, Plasticity Index, Soak CBR, Crushing & weathering resistance, Sand equivalent | Material Source testing and approval, Delivery dockets | Site Engineer
| 1.12 | Grade 3/5 Chip | W | NZTA M/6 | Prior to commencement | Submission | Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery dockets | Site Engineer
| 1.13 | Cement | W |  | Prior to commencement | Submission | Material compliance Certificate - Portland | Material certificate(s) | Site Engineer
| 1.14 | Bitumen | W | TNZ M/1 | Prior to commencement | Submission | Binder to meet TNZ M/1 standard. E2 Certificate | E2 Certificate | Site Engineer
| 1.15 | Review contractor's materials supplier QA documentation | H | Hicks Bay SH35 Slip Repair-12533432-G002 | Prior to commencement | Submission | Review contractor's materials supplier QA documentation | Lab test reports, Delivery dockets | Site Engineer | GHD Engineer
Section 2: Construction QA/QC - SLIP REPAIR & CULVERT INSTALL INSPECTIONS
| 2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Visual inspection | Set out extents of works and check against design drawings | Email/COR | Site Engineer
| 2.2 | Vegetation Clearance and removal of loose debris | W | Hicks Bay SH35 Slip Repair-12533432-G002 | During Construction | Visual Inspection | Remove and clear the vegetation | Photo's | Site Engineer
| 2.3 | Slope & Toe Subgrade Inspection | H | Hicks Bay SH35 Slip Repair-12533432-Q002 | Cut slope and toe of Revetment | Visual Inspection | Subgrade Approval Check sheet, Bench slope and excavate toe key of the revetment key to the design formation level. Toe key subgrade to be a minimum ultimate bearing capacity of 300kpa and requires GHD Engineer to visual check inspection & approve | Subgrade Approval Check sheet (CS-4100), GHD COR | Site Engineer | GHD Engineer
| 2.4 | Ground Improvements | H | Hicks Bay SH35 Slip Repair-12533432-G002 | During Construction | Document Review | Any additional undercuts in U/S areas to be approved by GHD engineer | Photo's, GHD COR | Site Engineer | GHD Engineer
| 2.5 | Form and cut fill batter in benches | H | Hicks Bay SH35 Slip Repair-12533432-Q002 | During Construction | Visual Inspection | The final Bench configuration will be considered and agreed on site with the Engineer. | Photo's | Site Engineer | GHD Engineer
| 2.6 | Bidim A64 Geotextile installation on the cut surface/faces | W | Hicks Bay SH35 Slip Repair-12533432-G003 | During Construction | Visual Inspection | Excavation undercut to be underlain and pinned with Bidim A64 or similar approved before placing rock and be laid/overlapped as per manufacturers recommendations | Photo's | Site Engineer
2.7 | 2.7 | Rock Armour (700 to 1500dia) placed on the toe of the slope | H | Hicks Bay SH35 Slip Repair-12533432-Q002 | During Construction | Visual Inspection | 2t rock class 700 to 1500mm to be placed in toe and on benches to form revetment. Rock to be placed individually not dumped. Slope of the top face of each rock back towards the rockery/ revetment at an inclination of 5%. Any voids larger than 300mm shall be clinched with smaller rock and or infilled with granular aggregate (smaller rock) | Photo's | Site Engineer | GHD Engineer
|  | Rock placement | H | Hicks Bay SH35 Slip Repair-12617302-01-G002 | During Construction | Visual Inspection | Engineer confirmation during inspection and monitoring that the rock placement should be well placed block shaped rock, | GHD COR report, Photos | Site Engineer | GHD Engineer
2.8 | 2.8 | Verge | M | Buttress typical details type A and F3001B-DS-GT-RP-0001 | During Construction | Visual Inspection | Verge reinstatement to match existing | Photo's | Site Engineer
2.9 | 2.9 | Replace existing culvert with new 525 diameter concrete culvert | H | Hicks Bay SH35 Slip Repair-12533432-C002 | As works progress in agreement with the GHD engineer | Visual Inspection | Exact location and alignment of the culvert as agreed on site with the engineer. Inlet and outlet areas to be shaped to be agreed on site with the engineer | Drainage Line Record (CS-4025), Photo's | Site Engineer | GHD Engineer
| 2.1 | Foundation compliance (Culvert) | H | Hicks Bay SH35 Slip Repair-12533432-C004 | During Construction | Scala testing | Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required | 1M Scala check sheet (CS-4000), Scala test results | Site Engineer | GHD Engineer
| 2.11 |  | H | Hicks Bay SH35 Slip Repair-12533432-C005 | During Construction | Visual inspection | GHD to inspect and approve formation level at outlet of Culvert | GHD COR | Site Engineer | GHD Engineer
| 2.12 | Trenching and Excavation (Culvert) | W | Hicks Bay SH35 Slip Repair-12533432-C006 | During Construction | Visual inspection | Ensure trench width is sufficient to provide enough space on either side of the pipe | Photo's | Site Engineer
| 2.13 |  | W | Hicks Bay SH35 Slip Repair-12533432-C007 | During Construction | Survey | Inspect trench profile and ensure it is correct to lines and levels as per design | Survey As-Builts | Site Engineer
|  | Inlet and outlet shaping | M | Hicks Bay SH35 Slip Repair-12533432-C003 | During Construction | Visual Inspection | Inlet and outlet areas to be shaped in consultation and to be agreed on site with the Engineer. | GHD COR | Site Engineer | GHD Engineer
| 2.14 | Bulk Fill on drainage trench and final bench | H | Hicks Bay SH35 Slip Repair-12533432-C003 | During Construction | NDM testing | Bulk Fill Earthworks Record, Place AP65 in 150mm deep layers target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 | Bulk Fill Earthworks Record (CS-4020), Test reports | Site Engineer | GHD Engineer
| 2.15 | Wingwall for Culvert Inlet and Concrete Pre-cast Manhole | H | Hicks Bay SH35 Slip Repair-12533432-C002 | During Construction | Visual Inspection | Install Hynds mountable wingwall or similar approved pointed towards approaching traffic tie in ground profile smoothly to match wingwall profile and to connect into 1050mm concrete pre-cast manhole with concrete lid. New culvert inlet pipe to have minimum 100mm drop from wingwall inverts. | GHD COR, Photo's | Site Engineer | GHD Engineer
| 2.16 | Culvert installation - new RCRRJ 525mm dia. Pipe | H | Hicks Bay SH35 Slip Repair-12533432-C003 | During Construction | Visual Inspection | Installed in accordance with typical detail and manufacturers recommendations. Culvert construction and bedding to be as per NZTA F3 Specification. Consider using excavated river run as fill compacted to achieve 95% MDD | GHD COR, Photo's | Site Engineer | GHD Engineer
| 2.17 | Apron for Scour Protection at Culvert Outlet | H | Hicks Bay SH35 Slip Repair-12533432-C003 | During Construction | Visual Inspection | Construct 2.1m long X 1.5m wide X 0.5m deep Rip-Rap (300mm-500mm dia.) apron for Scour protection at culvert outlet. Install Filter Fabric A64 or equivalent under rock Rip-Rap. | GHD COR, Photo's | Site Engineer | GHD Engineer
| 2.18 | Fence installation | M | Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001 | During Construction | Visual Inspection | Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line | Photos | Site Engineer
| 2.19 | Grass Seeding | M | Hicks Bay SH35 Slip Repair-12533432-Q002 | During Construction | Visual Inspection | All exposed earth to be grass seeded | Photos | Site Engineer
Section 3: CULVERT PAVEMENT INSPECTIONS
| 3.1 | Saw cut existing pavement | H |  | Prior to pavement construction | Visual inspection | Smooth and straight saw cut | Photo's | Site Engineer
| 3.2 | Subgrade construction | W | TNZ B2 | Every 200-300mm | NDM testing & Clegg Hammer testing | Subgrade shall be AP65 compacted to average 95% MDD with nothing less than 92% CIV>=25 | Subgrade Approval Check sheet, Clegg Record Test Sheet, Test (CS-4100) reports | Site Engineer
| 3.4 | Sub-base construction | W | TNZ B2 | Every lift | NDM testing & Clegg Hammer testing | 200mm thick AP65 sub-base compacted to Average 95% of MDD with nothing less than 92% CIV>=25 | Clegg record test sheet, Photos, Test reports | Site Engineer
| 3.5 | Sub-base construction | H | TNZ B2 |  | Survey | Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer | GHD Engineer
| 3.6 | Basecourse construction | W | TNZ B2 |  | NDM testing | 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98% Average 98% of MDD with nothing less than 95% | Test reports, Photo's | Site Engineer
| 3.7 | Basecourse Cement application rate | M | TNZ B/5 |  | Visual inspection | 2% cement stabilisation at 150mm deep basecourse | Photo's | Site Engineer
| 3.8 | Basecourse construction | H | TNZ B2 |  | Survey | Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as builts | Site Engineer | GHD Engineer
| 3.9 | Basecourse construction | W | TNZ B2 |  | Clegg Hammer testing | CIV>=25 | Test reports, Photo's | Site Engineer
| 3.1 | Basecourse construction | H | TNZ B2 | Before sealing | Pre-seal checksheet | Mosaic surface | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer | GHD Engineer
| 3.11 | Applying Bitumen | W | NZTA M/6 |  | Visual inspection | Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer
| 3.12 | Degree of saturation | W |  | Before sealing | Pre-seal checksheet | Degree of saturation should not exceed 80% | Pre-seal checksheet (CS-4060) | Site Engineer
| 3.13 | Chip seal laying | W | NZTA M/6 | During Construction | Submission | grade 3 and 5 chip seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3 | Photo's | Site Engineer
| 3.14 | Sweep & Line marking to new chip seal road | W | TNZ P/12:2000 | During Construction | Visual inspection | As per TNZ P/12:2000 | Photo's | Site Engineer
Section 4: Post Construction - FINAL INSPECTION & HANDOVER
| 4.1 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by GHD Engineer | As-builts, GHD COR | Site Engineer | GHD Engineer
|  | Inspection of site following completion of physical works | H | Hicks Bay SH35 Slip Repair-12533432-Q002 |  | Walkover/Visual Inspection | Inspection of site following completion of physical works | GHD COR | Site Engineer | GHD Engineer
| 4.2 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
| 4.3 | Completion Sign Off From Fields Below | H |  |  |  |  | Signatures | PM | GHD Engineer | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
| QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
| QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By GHD Manager: |  |  |  |  | Signature: |  |  | Date:

## SSI
SITE SPECIFIC INSTRUCTIONS
Any changes to design to be approved in writing by Design Engineer
Site Instruction details | Name | Position | Date | Quality & Design Engineer notified (date)