## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | itp |  |  |  |  | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | f8bb0e78-656e-47be-8c8c-336fb7830f4e
section | 1. Minor Earthworks
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Cut/Fill Required
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
section | 2. Material Production
checkpoint | 2.1 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Source test of each material used (minimum 10 rocks per source)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - 1. Schmidt Hammer test (minimum of 10 rocks per source) and 90% result ≥ 50 in all direction or
label | 2. Weathering resistance AA,AB, BB or CA (NZS4407)
label | 3. Specific of gravity ≥ 2.56 or up size rock to compensate
label | 4. maximum dimension of any rock ≤ 3 times narrowest dimension
label | Records - Lab Reports, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Consistency though construction and clean of dirt
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitor on site
label | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | Records - Photos
checkpoint | 2.3 - Material Compliance Subsoil
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier certification and delivery dockets
label | Conformance Criteria - Prior to megaflow installation
label | Records - Collect all delivery dockets and photos
checkpoint | 2.4 - Material Compliance and Methodology Approval
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E soil nail
label | ○ Class II corrosion protection
label | ○ Lengths and diameters shown on drawings are the minimum required
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Concrete Quality Plan and Work Plan
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete Quality Plan and Work Plan
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Refer to section 8.3.1 for the Contract Quality Plan and Section 8.3.2 for the Work Plan
label | Including:
label | – Name, qualification and experience of concrete works inspector
label | – Form and content of concrete placement card
label | Records - Email / RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Concrete Supply Plant Approval
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of concrete supply plant, copy of certificate of audit for plant
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Plant test Results
label | – ASR Compliance Records
label | Records - Email / RFI
checkpoint | 2.7 - Reinforcement Steel Certification
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Reinforcing steel manufacturers test reports and certificates
label | Frequency - Prior to undertaking works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including despatch records
label | Records - Email / RFI
checkpoint | 2.8 - Concrete Mix Designs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | Records - Email / RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Grout Mix Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Mix design to be approved by CPS Engineer three weeks before commencing construction
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Grout Mix Check - On-site
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grout checked if its free from lumps & segregation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 2.11 - Alternative Drilling Fluid
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - If required
holdpoint | AUTHORITY HOLDPOINT
section | 3. Soil Nails Installation
checkpoint | 3.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings including sacrificial nails
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Soil Nail Construction Methodology
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
label | Records - Methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Trial installation of Sacrificial Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill hole, install Bolt/Nail, install Grout. Location for Sacrificial Soil Nails to be agreed on Site with CPS Engineer.
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Bore logs of Drilling, installation record
label | Records - Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Sacrificial Nail Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test after a 7 day period. Load up to the specified requirements with the CPS Engineer overseeing proceedings
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Design Team to approve grout test result prior to sacrificial testing being commenced.
label | ○ Calibration of testing equipment
label | ○ CPS Engineer to observe testing and provide feedback.
label | Records - Instruction to proceed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria -
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Production Nails Location
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | Frequency - Prior to Trial
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria -
label | Records - Photos, Site Diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Production Soil Nails Bore Hole Drilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drill hole
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - +/- 2 Degrees
label | ○ Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | ○ Submit all installation records for each soil nail and pile.
label | Records - Drill Logs, submission records
checkpoint | 3.8 - Bore Hole Flushing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Soil Nails Insertion
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert soil nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevent damage
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Soil Nail Logging
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Installation records shall include:
label | – Length of bar
label | – Depth of drill hole
label | – Inclination/Verticality achieved
label | – Level of grout placed
label | – Batch numbers associated with grout placed in each hole
label | Records - Subcontractor QA Records
checkpoint | 3.11 - Grouting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout. Install Grout on the same day of drilling unless otherwise approved by Designer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Including:
label | – Concrete despatch records
label | – Compression test results
label | – Slump and spread test reports
label | ○ Must notify CPS for any failed result and cease works until resolved
label | Records - Subcontractor QA Records and Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Grout Sampling
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Grout Loss Recording
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Subcontractor QA Records
checkpoint | 3.14 - Bolts/Washer/Nuts Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.15 - Testing of Soil Nails - Each Row
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | Records - Certifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Testing of Soil Nails - Minimum Resting Period Before Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria -
label | Records -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.17 - Testing of Soil Nails - Testing Specs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Final Inspection Before Next Row Commencement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install subsoil drainage as required in accordance with specification
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - As per drawing 1.5m alternate with weep holes
label | Records - Photographs
checkpoint | 3.20 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
checkpoint | 3.21 - Pre-Shotcreting Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - No concrete shall be placed until the CPS Engineer has had the opportunity to ensure the drawings and specification have been complied with . 48 Hours notice required.
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with Drawings and Specification
label | Records - COR/Email/Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.22 - Shotcrete Minimum Application Requirements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - 200mm Nominal thick (Vertical). Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 3.23 - Shotcrete Compression Testing - Core Test
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.24 - Final Inspection - Each Shotcrete Soil Nails Row
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
section | 4. As-built Requirements
checkpoint | 4.1 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 4.3 - Subcontractor Quality Assurance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 4.4 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - During and at completion of work.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.6 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | itp |  |  |  |  | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | 16d67872-34dc-46d5-abd6-75d9f8e815e1
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out line of pile as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any services in the area are to be clearly marked before any work commences and to be potholed to confirm their location
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Site record sheet/Daily diary
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Driven piles to be 310UC137
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | Records - Data sheets and mill certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Walers to be 200UC52.2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | Records - Data sheets and mill certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade 300 as shown on the drawings
label | Frequency - Prior to ordering steel
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS4671&NZS3109
label | Records - Detail Sheets and Mill Certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any welding or mechanical splicing to be approved in writing by the CPS Engineer
label | Frequency - Prior to welding or splicing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS1554 part 3
label | Records - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
label | Frequency - Prior to cutting or bending on site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZS3109;1997
label | Records - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Pile Line
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check if the bench has been excavated/filled can accommodate the entire pile line
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Relevant Drawing & Survey set Out
label | Records - Site visit agreement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Driving Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check driving performance, verticality and position
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Piles to be drive vertical checked with a spirit level
label | Records - Piling Specification, Relevant Drawings, Pile Card
checkpoint | 10 - Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure penetration depth of 3.8m is achieved
label | Frequency - Each pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - measurement/visual inspection
label | Conformance Criteria - 3.8m embedment in river bed in acordance with Design Depth
label | Records - Pile Card record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Reinforcement Cage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check supply and installation of reinforcement cage
label | Frequency - Each cage
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | Conformance Criteria - NZS 3109 and being in accordance with the drawings, ensure cover of 50mm from face of formwork
label | Records - Reinforce cage record and site photographs
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for inspection of installed reinforcement cage
label | Frequency - Prior to placing concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with the drawings ensure cover of 50mm to formwork and 40mm cover to piles and waler
label | Records - site photographs/ inspection report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Formwork
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure formwork is competent to contain the required volume of concrete
label | Frequency - Prior to placing concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 50mm cover to reinforcing. Formwork is straight and true
label | Records - site photographs/ inspection report
checkpoint | 14 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete required is a 30Mpa mix design required for a pump mix is 13mm aggregate for pumping
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Concrete Mix design acceptance
label | Records - concrete mix design approval prior to comencement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Concreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pre-pour inspection and check sheet is required prior to comencement
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection check sheet sign of
label | Records - Concrete check sheet signed off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | Conformance Criteria - NZS 3104
label | Records - Concrete docket & Concrete test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Post-pour inspection and Check sheet for concrete placement method and finish
label | Frequency - At completion of pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete check sheet signed off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 20 - Completion Sign Off From Fields Below
label | ACTION (Hold, Monitor, Witness) - H
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | itp |  |  |  |  | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | f1ac2565-6c2b-4a96-baa6-00b453de60ff
section | Section 1: Materials Compliance - RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | GHD Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour, 2 tonne rock class (D0.7m to 1.5m)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-1253342-Q002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D700 to 1500 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery dockets
checkpoint | 1.2 - Granular Backfill - AP65 (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Shall be free draining, hard, durable, well graded, crushed granular material such as AP65 with a fines content <5% with more than 2 broken faces. It shall be free from organic and vegetative material and compacted to achieve 90%MDD. Compaction maybe checked by clegg hammer.
label | Records - Material source test results, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Granular Backfill - AP65 (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | Conformance Criteria - Address of the source quarry. The geological description of the parent material. Particle Size Distribution (PSD) Test, Compaction Test and Broken Face Percentage Test Results from a Representative, General Fill Sample Tested in an independent and accredited Laboratory
label | Records - Laboratory Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Granular Backfill - AP65 (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | Conformance Criteria - Results of Compaction Tests as Specified in NZS 4402:1988 - Test 4.1.1 or Test 4.1.3 are to be carried out on the proposed backfill and the results presented to the engineer for agreement prior to construction. These are to clearly show the Optimum Moisture Content and Maximum Dry Density Achieved
label | Records - Laboratory Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Geotextile Filter Fabric Bidim A64 (or under Rock Rip-Rap on Culvert Outlet Scour protection
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Strength Class C. Filtration Class 1 - Bidim A64 Geotextile or an approved equivalent - compliant placed under Rock Rip-Rap
label | Records - Material compliance cert, Photo's
checkpoint | 1.4 - Deep Rock Rip-Rap (300mm-500mm dia.)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Apron for Scour Protection at Culvert Outlet
label | Records - Material source test results, Delivery dockets
checkpoint | 1.5 - Guard railing
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Guard railing system to be installed to manufacturers specification. see ITP for Guard Rail
label | Records - Manufacturers spec, Delivery dockets
checkpoint | 1.6 - Precast RCRRJ 525 dia. Pipe
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
label | ○ Class 4 RCRRJ 525 pipe to comply with AS/NZS 4058
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Precast materials
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Hynds Mountable Wingwall for Culvert Inlet or similar approved by Engineer
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - D1050mm Concrete Pre-cast Manhole with concrete lid
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - AP40 (Basecourse) or approved basecourse modification
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ M/4 Section 3.2 & 3.3
label | Frequency - 1/source and at least 1/3 months
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution, Plasticity Index, Soak CBR, Crushing & weathering resistance, Clay Index, Sand equivalent
label | Records - Material Source testing and approval, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA
label | Frequency - 1/source and at least 1/3 months
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution, Maximum Dry Density, Plasticity Index, Soak CBR, Crushing & weathering resistance, Sand equivalent
label | Records - Material Source testing and approval, Delivery dockets
checkpoint | 1.12 - Grade 3/5 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.13 - Cement
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference -
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Material compliance Certificate - Portland
label | Records - Material certificate(s)
checkpoint | 1.14 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
checkpoint | 1.15 - Review contractor's materials supplier QA documentation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Review contractor's materials supplier QA documentation
label | Records - Lab test reports, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | Section 2: Construction QA/QC - SLIP REPAIR & CULVERT INSTALL INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Set out extents of works and check against design drawings
label | Records - Email/COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Slope & Toe Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - Cut slope and toe of Revetment
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Subgrade Approval Check sheet, Bench slope and excavate toe key of the revetment key to the design formation level. Toe key subgrade to be a minimum ultimate bearing capacity of 300kpa and requires GHD Engineer to visual check inspection & approve
label | Records - Subgrade Approval Check sheet (CS-4100), GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any additional undercuts in U/S areas to be approved by GHD engineer
label | Records - Photo's, GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Form and cut fill batter in benches
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The final Bench configuration will be considered and agreed on site with the Engineer.
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bidim A64 Geotextile installation on the cut surface/faces
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain and pinned with Bidim A64 or similar approved before placing rock and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.7 - Rock Armour (700 to 1500dia) placed on the toe of the slope
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 2t rock class 700 to 1500mm to be placed in toe and on benches to form revetment. Rock to be placed individually not dumped. Slope of the top face of each rock back towards the rockery/ revetment at an inclination of 5%. Any voids larger than 300mm shall be clinched with smaller rock and or infilled with granular aggregate (smaller rock).
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Rock placement
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12617302-01-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer confirmation during inspection and monitoring that the rock placement should be well placed block shaped rock,
label | Records - GHD COR report, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Verge
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Verge reinstatement to match existing
label | Records - Photo's
checkpoint | 2.9 - Replace existing culvert with new 525 diameter concrete culvert
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | Frequency - As works progress in agreement with the GHD engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Exact location and alignment of the culvert as agreed on site with the engineer. Inlet and outlet areas to be shaped to be agreed on site with the engineer
label | Records - Drainage Line Record (CS-4025), Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Foundation compliance (Culvert)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | Records - 1M Scala check sheet (CS-4000), Scala test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C005
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - GHD to inspect and approve formation level at outlet of Culvert
label | Records - GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Trenching and Excavation (Culvert)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C006
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Records - Photo's
checkpoint | 2.13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C007
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | Records - Survey As-Builts
checkpoint | Inlet and outlet shaping
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Inlet and outlet areas to be shaped in consultation and to be agreed on site with the Engineer.
label | Records - GHD COR
checkpoint | 2.14 - Bulk Fill on drainage trench and final bench
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - Bulk Fill Earthworks Record, Place AP65 in 150mm deep layers target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - Bulk Fill Earthworks Record (CS-4020), Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - Wingwall for Culvert Inlet and Concrete Pre-cast Manhole
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Install Hynds mountable wingwall or similar approved pointed towards approaching traffic tie in ground profile smoothly to match wingwall profile and to connect into 1050mm concrete pre-cast manhole with concrete lid. New culvert inlet pipe to have minimum 100mm drop from wingwall inverts.
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Culvert installation - new RCRRJ 525mm dia. Pipe
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installed in accordance with typical detail and manufacturers recommendations. Culvert construction and bedding to be as per NZTA F3 Specification. Consider using excavated river run as fill compacted to achieve 95% MDD
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.17 - Apron for Scour Protection at Culvert Outlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Construct 2.1m long X 1.5m wide X 0.5m deep Rip-Rap (300mm-500mm dia.) apron for Scour protection at culvert outlet. Install Filter Fabric A64 or equivalent under rock Rip-Rap.
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.18 - Fence installation
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
label | Records - Photos
checkpoint | 2.19 - Grass Seeding
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - All exposed earth to be grass seeded
label | Records - Photos
section | Section 3: CULVERT PAVEMENT INSPECTIONS
checkpoint | 3.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference -
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 200-300mm
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | Conformance Criteria - Subgrade shall be AP65 compacted to average 95% MDD with nothing less than 92%, CIV>=25
label | Records - Subgrade Approval Check sheet, Clegg Record Test Sheet, Test (CS-4100) reports
checkpoint | 3.4 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to Average 95% of MDD with nothing less than 92% CIV>=25
label | Records - Clegg record test sheet, Photos, Test reports
checkpoint | 3.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ○ Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 3.7 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - TNZ B/5
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Photo's
checkpoint | 3.8 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports, Photo's
checkpoint | 3.1 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 3.12 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference -
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 3.13 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - grade 3 and 5 chip seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | Records - Photo's
checkpoint | 3.14 - Sweep & Line marking to new chip seal road
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ P/12:2000
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per TNZ P/12:2000
label | Records - Photo's
section | Section 4: Post Construction - FINAL INSPECTION & HANDOVER
checkpoint | 4.1 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference -
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by GHD Engineer
label | Records - As-builts, GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Inspection of site following completion of physical works
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover/Visual Inspection
label | Conformance Criteria - Inspection of site following completion of physical works
label | Records - GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.3 - Completion Sign Off From Fields Below
label | ACTION (Hold, Monitor, Witness) - H
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT