## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | itp |  |  |  |  | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails
section | 1. Minor Earthworks
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Cut/Fill Required
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
section | 2. Material Production
checkpoint | 2.1 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Source test of each material used (minimum 10 rocks per source)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - 1. Schmidt Hammer test (minimum of 10 rocks per source) and 90% result ≥ 50 in all direction or
label | 2. Weathering resistance AA,AB, BB or CA (NZS4407)
label | 3. Specific of gravity ≥ 2.56 or up size rock to compensate
label | 4. maximum dimension of any rock ≤ 3 times narrowest dimension
label | Records - Lab Reports, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material Compliance (Rock Works)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Consistency though construction and clean of dirt
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitor on site
label | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | Records - Photos
checkpoint | 2.3 - Material Compliance Subsoil
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications
label | Frequency - Each rock source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier certification and delivery dockets
label | Conformance Criteria - Prior to megaflow installation
label | Records - Collect all delivery dockets and photos
checkpoint | 2.4 - Material Compliance and Methodology Approval
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E soil nail
label | ○ Class II corrosion protection
label | ○ Lengths and diameters shown on drawings are the minimum required
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Concrete Quality Plan and Work Plan
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete Quality Plan and Work Plan
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Refer to section 8.3.1 for the Contract Quality Plan and Section 8.3.2 for the Work Plan
label | Including:
label | – Name, qualification and experience of concrete works inspector
label | – Form and content of concrete placement card
label | Records - Email / RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Concrete Supply Plant Approval
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of concrete supply plant, copy of certificate of audit for plant
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Plant test Results
label | – ASR Compliance Records
label | Records - Email / RFI
checkpoint | 2.7 - Reinforcement Steel Certification
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Reinforcing steel manufacturers test reports and certificates
label | Frequency - Prior to undertaking works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including despatch records
label | Records - Email / RFI
checkpoint | 2.8 - Concrete Mix Designs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | Records - Email / RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Grout Mix Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Mix design to be approved by CPS Engineer three weeks before commencing construction
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Grout Mix Check - On-site
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grout checked if its free from lumps & segregation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 2.11 - Alternative Drilling Fluid
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - If required
holdpoint | AUTHORITY HOLDPOINT
section | 3. Soil Nails Installation
checkpoint | 3.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings including sacrificial nails
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Soil Nail Construction Methodology
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
label | Records - Methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Trial installation of Sacrificial Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill hole, install Bolt/Nail, install Grout. Location for Sacrificial Soil Nails to be agreed on Site with CPS Engineer.
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Bore logs of Drilling, installation record
label | Records - Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Sacrificial Nail Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test after a 7 day period. Load up to the specified requirements with the CPS Engineer overseeing proceedings
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Design Team to approve grout test result prior to sacrificial testing being commenced.
label | ○ Calibration of testing equipment
label | ○ CPS Engineer to observe testing and provide feedback.
label | Records - Instruction to proceed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria -
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Production Nails Location
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | Frequency - Prior to Trial
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria -
label | Records - Photos, Site Diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Production Soil Nails Bore Hole Drilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drill hole
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - +/- 2 Degrees
label | ○ Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | ○ Submit all installation records for each soil nail and pile.
label | Records - Drill Logs, submission records
checkpoint | 3.8 - Bore Hole Flushing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Soil Nails Insertion
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert soil nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevent damage
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Soil Nail Logging
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Installation records shall include:
label | – Length of bar
label | – Depth of drill hole
label | – Inclination/Verticality achieved
label | – Level of grout placed
label | – Batch numbers associated with grout placed in each hole
label | Records - Subcontractor QA Records
checkpoint | 3.11 - Grouting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout. Install Grout on the same day of drilling unless otherwise approved by Designer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Including:
label | – Concrete despatch records
label | – Compression test results
label | – Slump and spread test reports
label | ○ Must notify CPS for any failed result and cease works until resolved
label | Records - Subcontractor QA Records and Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Grout Sampling
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Grout Loss Recording
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Subcontractor QA Records
checkpoint | 3.14 - Bolts/Washer/Nuts Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.15 - Testing of Soil Nails - Each Row
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | Records - Certifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Testing of Soil Nails - Minimum Resting Period Before Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria -
label | Records -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.17 - Testing of Soil Nails - Testing Specs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Final Inspection Before Next Row Commencement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install subsoil drainage as required in accordance with specification
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - As per drawing 1.5m alternate with weep holes
label | Records - Photographs
checkpoint | 3.20 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
checkpoint | 3.21 - Pre-Shotcreting Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - No concrete shall be placed until the CPS Engineer has had the opportunity to ensure the drawings and specification have been complied with . 48 Hours notice required.
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with Drawings and Specification
label | Records - COR/Email/Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.22 - Shotcrete Minimum Application Requirements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - 200mm Nominal thick (Vertical). Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 3.23 - Shotcrete Compression Testing - Core Test
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.24 - Final Inspection - Each Shotcrete Soil Nails Row
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
section | 4. As-built Requirements
checkpoint | 4.1 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 4.3 - Subcontractor Quality Assurance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 4.4 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - During and at completion of work.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.6 - Completion Sign Off From Fields Below
label | Records - Signatures