## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | itp |  |  |  |  | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out line of pile as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any services in the area are to be clearly marked before any work commences and to be potholed to confirm their location
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Site record sheet/Daily diary
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Driven piles to be 310UC137
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | Records - Data sheets and mill certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Walers to be 200UC52.2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | Records - Data sheets and mill certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade 300 as shown on the drawings
label | Frequency - Prior to ordering steel
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS4671&NZS3109
label | Records - Detail Sheets and Mill Certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any welding or mechanical splicing to be approved in writing by the CPS Engineer
label | Frequency - Prior to welding or splicing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS1554 part 3
label | Records - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
label | Frequency - Prior to cutting or bending on site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZS3109;1997
label | Records - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Pile Line
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check if the bench has been excavated/filled can accommodate the entire pile line
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Relevant Drawing & Survey set Out
label | Records - Site visit agreement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Driving Operations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check driving performance, verticality and position
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Piles to be drive vertical checked with a spirit level
label | Records - Piling Specification, Relevant Drawings, Pile Card
checkpoint | 10 - Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure penetration depth of 3.8m is achieved
label | Frequency - Each pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - measurement/visual inspection
label | Conformance Criteria - 3.8m embedment in river bed in acordance with Design Depth
label | Records - Pile Card record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Reinforcement Cage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check supply and installation of reinforcement cage
label | Frequency - Each cage
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | Conformance Criteria - NZS 3109 and being in accordance with the drawings, ensure cover of 50mm from face of formwork
label | Records - Reinforce cage record and site photographs
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for inspection of installed reinforcement cage
label | Frequency - Prior to placing concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with the drawings ensure cover of 50mm to formwork and 40mm cover to piles and waler
label | Records - site photographs/ inspection report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Formwork
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure formwork is competent to contain the required volume of concrete
label | Frequency - Prior to placing concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 50mm cover to reinforcing. Formwork is straight and true
label | Records - site photographs/ inspection report
checkpoint | 14 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete required is a 30Mpa mix design required for a pump mix is 13mm aggregate for pumping
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Concrete Mix design acceptance
label | Records - concrete mix design approval prior to comencement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Concreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pre-pour inspection and check sheet is required prior to comencement
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection check sheet sign of
label | Records - Concrete check sheet signed off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | Conformance Criteria - NZS 3104
label | Records - Concrete docket & Concrete test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Post-pour inspection and Check sheet for concrete placement method and finish
label | Frequency - At completion of pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete check sheet signed off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 20 - Completion Sign Off From Fields Below
label | ACTION (Hold, Monitor, Witness) - H
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT