## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | itp |  |  |  |  | ITP - F5001A - Hicks Bay Slip Repair - ITP for works
section | Section 1: Materials Compliance - RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | GHD Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour, 2 tonne rock class (D0.7m to 1.5m)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-1253342-Q002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D700 to 1500 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery dockets
checkpoint | 1.2 - Granular Backfill - AP65 (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Shall be free draining, hard, durable, well graded, crushed granular material such as AP65 with a fines content <5% with more than 2 broken faces. It shall be free from organic and vegetative material and compacted to achieve 90%MDD. Compaction maybe checked by clegg hammer.
label | Records - Material source test results, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Granular Backfill - AP65 (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | Conformance Criteria - Address of the source quarry. The geological description of the parent material. Particle Size Distribution (PSD) Test, Compaction Test and Broken Face Percentage Test Results from a Representative, General Fill Sample Tested in an independent and accredited Laboratory
label | Records - Laboratory Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Granular Backfill - AP65 (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | Conformance Criteria - Results of Compaction Tests as Specified in NZS 4402:1988 - Test 4.1.1 or Test 4.1.3 are to be carried out on the proposed backfill and the results presented to the engineer for agreement prior to construction. These are to clearly show the Optimum Moisture Content and Maximum Dry Density Achieved
label | Records - Laboratory Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Geotextile Filter Fabric Bidim A64 (or under Rock Rip-Rap on Culvert Outlet Scour protection
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Strength Class C. Filtration Class 1 - Bidim A64 Geotextile or an approved equivalent - compliant placed under Rock Rip-Rap
label | Records - Material compliance cert, Photo's
checkpoint | 1.4 - Deep Rock Rip-Rap (300mm-500mm dia.)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Apron for Scour Protection at Culvert Outlet
label | Records - Material source test results, Delivery dockets
checkpoint | 1.5 - Guard railing
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Guard railing system to be installed to manufacturers specification. see ITP for Guard Rail
label | Records - Manufacturers spec, Delivery dockets
checkpoint | 1.6 - Precast RCRRJ 525 dia. Pipe
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
label | ○ Class 4 RCRRJ 525 pipe to comply with AS/NZS 4058
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Precast materials
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Hynds Mountable Wingwall for Culvert Inlet or similar approved by Engineer
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - D1050mm Concrete Pre-cast Manhole with concrete lid
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - AP40 (Basecourse) or approved basecourse modification
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ M/4 Section 3.2 & 3.3
label | Frequency - 1/source and at least 1/3 months
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution, Plasticity Index, Soak CBR, Crushing & weathering resistance, Clay Index, Sand equivalent
label | Records - Material Source testing and approval, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA
label | Frequency - 1/source and at least 1/3 months
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution, Maximum Dry Density, Plasticity Index, Soak CBR, Crushing & weathering resistance, Sand equivalent
label | Records - Material Source testing and approval, Delivery dockets
checkpoint | 1.12 - Grade 3/5 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.13 - Cement
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference -
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Material compliance Certificate - Portland
label | Records - Material certificate(s)
checkpoint | 1.14 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
checkpoint | 1.15 - Review contractor's materials supplier QA documentation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Review contractor's materials supplier QA documentation
label | Records - Lab test reports, Delivery dockets
holdpoint | AUTHORITY HOLDPOINT
section | Section 2: Construction QA/QC - SLIP REPAIR & CULVERT INSTALL INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Set out extents of works and check against design drawings
label | Records - Email/COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Slope & Toe Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - Cut slope and toe of Revetment
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Subgrade Approval Check sheet, Bench slope and excavate toe key of the revetment key to the design formation level. Toe key subgrade to be a minimum ultimate bearing capacity of 300kpa and requires GHD Engineer to visual check inspection & approve
label | Records - Subgrade Approval Check sheet (CS-4100), GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any additional undercuts in U/S areas to be approved by GHD engineer
label | Records - Photo's, GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Form and cut fill batter in benches
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The final Bench configuration will be considered and agreed on site with the Engineer.
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bidim A64 Geotextile installation on the cut surface/faces
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain and pinned with Bidim A64 or similar approved before placing rock and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.7 - Rock Armour (700 to 1500dia) placed on the toe of the slope
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 2t rock class 700 to 1500mm to be placed in toe and on benches to form revetment. Rock to be placed individually not dumped. Slope of the top face of each rock back towards the rockery/ revetment at an inclination of 5%. Any voids larger than 300mm shall be clinched with smaller rock and or infilled with granular aggregate (smaller rock).
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Rock placement
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12617302-01-G002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer confirmation during inspection and monitoring that the rock placement should be well placed block shaped rock,
label | Records - GHD COR report, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Verge
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Verge reinstatement to match existing
label | Records - Photo's
checkpoint | 2.9 - Replace existing culvert with new 525 diameter concrete culvert
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | Frequency - As works progress in agreement with the GHD engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Exact location and alignment of the culvert as agreed on site with the engineer. Inlet and outlet areas to be shaped to be agreed on site with the engineer
label | Records - Drainage Line Record (CS-4025), Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Foundation compliance (Culvert)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | Records - 1M Scala check sheet (CS-4000), Scala test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C005
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - GHD to inspect and approve formation level at outlet of Culvert
label | Records - GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Trenching and Excavation (Culvert)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C006
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Records - Photo's
checkpoint | 2.13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C007
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | Records - Survey As-Builts
checkpoint | Inlet and outlet shaping
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Inlet and outlet areas to be shaped in consultation and to be agreed on site with the Engineer.
label | Records - GHD COR
checkpoint | 2.14 - Bulk Fill on drainage trench and final bench
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - Bulk Fill Earthworks Record, Place AP65 in 150mm deep layers target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - Bulk Fill Earthworks Record (CS-4020), Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - Wingwall for Culvert Inlet and Concrete Pre-cast Manhole
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Install Hynds mountable wingwall or similar approved pointed towards approaching traffic tie in ground profile smoothly to match wingwall profile and to connect into 1050mm concrete pre-cast manhole with concrete lid. New culvert inlet pipe to have minimum 100mm drop from wingwall inverts.
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Culvert installation - new RCRRJ 525mm dia. Pipe
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installed in accordance with typical detail and manufacturers recommendations. Culvert construction and bedding to be as per NZTA F3 Specification. Consider using excavated river run as fill compacted to achieve 95% MDD
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.17 - Apron for Scour Protection at Culvert Outlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Construct 2.1m long X 1.5m wide X 0.5m deep Rip-Rap (300mm-500mm dia.) apron for Scour protection at culvert outlet. Install Filter Fabric A64 or equivalent under rock Rip-Rap.
label | Records - GHD COR, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.18 - Fence installation
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
label | Records - Photos
checkpoint | 2.19 - Grass Seeding
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - All exposed earth to be grass seeded
label | Records - Photos
section | Section 3: CULVERT PAVEMENT INSPECTIONS
checkpoint | 3.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference -
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 200-300mm
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | Conformance Criteria - Subgrade shall be AP65 compacted to average 95% MDD with nothing less than 92%, CIV>=25
label | Records - Subgrade Approval Check sheet, Clegg Record Test Sheet, Test (CS-4100) reports
checkpoint | 3.4 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to Average 95% of MDD with nothing less than 92% CIV>=25
label | Records - Clegg record test sheet, Photos, Test reports
checkpoint | 3.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ○ Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 3.7 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - TNZ B/5
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Photo's
checkpoint | 3.8 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports, Photo's
checkpoint | 3.1 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 3.12 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference -
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 3.13 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - grade 3 and 5 chip seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | Records - Photo's
checkpoint | 3.14 - Sweep & Line marking to new chip seal road
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ P/12:2000
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per TNZ P/12:2000
label | Records - Photo's
section | Section 4: Post Construction - FINAL INSPECTION & HANDOVER
checkpoint | 4.1 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference -
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by GHD Engineer
label | Records - As-builts, GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Inspection of site following completion of physical works
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover/Visual Inspection
label | Conformance Criteria - Inspection of site following completion of physical works
label | Records - GHD COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.3 - Completion Sign Off From Fields Below
label | ACTION (Hold, Monitor, Witness) - H
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT