## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev3 | itp |  |  |  |  | FHC-ITP-006 - Class 3 Crushed Rock Rev3
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – Using the correct and complete set of drawings
note | – All drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Material Mix Design
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Document Review
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Transverse Joints
note | FREQUENCY: Check prior to placing material
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Longitudinal Joints
note | FREQUENCY: Check prior to placing material
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Lot Size
note | FREQUENCY: Check prior to placing material
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Signed ITP
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Layer Thickness
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Signed ITP
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Proof Rolling
note | FREQUENCY: Proof Roll each layer
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 173.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP/ WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer & Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
note | FREQUENCY: Prior to Testing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Table 204.161
note | • Cl.304.08 (a)
note | • Cl.304.11 (b)
note | • Cl.304.11 (c)(i)
note | • Table 304.111
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Signed ITP
note | – – – – – – – – –
note | AP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.2 Compaction Testing
note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
note | • Cl 304.11 (b) Table 304.111
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off; Test reports
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.3 Compaction Testing (Small Lots)
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 173.04 d
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test Point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Records, Lot Register
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.4 Material Grading - Post Compaction
note | FREQUENCY: First Lot Only
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
note | • Class 4 - As per Table 304.101 - VR Spec. 304.10
note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off; Test reports
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.5 Plasticity Index - Post Compaction
note | FREQUENCY: First Lot Only
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
note | • Class 4 - 0 to 10
note | • Class 3 - 0 to 10
note | • Class 2 - 0 to 6
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off; Test reports
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.6 Survey Conformance
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
note | • Surface level tolerances:
note | • Range x = +6, -16mm
note | • Max S = 15 mm
note | • 40 measurements per lot (Minimum)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Survey
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: