## Master List Templates
Id | Type | Name | Values | Prompting Name
4379daa1-4f49-41cd-8e9d-ff69a7b63830 | checklist | Water Tanks and SW Pump Station checks |  | Sewer Pump Station:
54469624-c256-4588-a709-dcbbb751c344 | section | Water Tanks and SW Pump Station
6a018d49-9573-4ab5-bdfb-10af0ddf1794 | checkpoint | Plans Issues are correct
e02cf41c-5820-4507-8dfd-4c235f995d9d | checkpoint | Pump Station plans issues and correct - showing components and IL
ce73d0a1-033e-43f4-a3bc-b4d9a141567a | checkpoint | Check Plans for Sizing and pipe materials
ce7c9867-8b03-4802-b4bd-458a5dd547e9 | checkpoint | Subgrade Test - Use Scala or Shear Vane - 3 Blows per 100mm or 60KPA
0d2230e4-cd69-4bb4-b6af-16aa933623d5 | checkpoint | Water Tank - Size and Spec correct
4297ab91-1acb-4a2b-83b4-d54411d7c464 | checkpoint | Imported filled correctly as per engineer spec
c380b077-ab0a-4197-bb7d-a6a654f4d20c | checkpoint | Backfilled in layers of 300mm - Test every 10m - 4 Blows per 100mm or over 30CIV on Clegg
c380b077-ab0a-4197-bb7d-a6a654f4d20c | checkpoint | Anti Floatation deadmans and straps installed correctly
96dc4394-ec5f-4a23-8cf0-c9987c7a810d | checkpoint | All trenches compacted with Compactor
8930dd54-c05b-43b1-8830-6e844b12a7a5 | checkpoint | Services required for pump station - Power, Comms, Water, etc
8930dd54-c05b-43b1-8830-6e844b12a7a6 | checkpoint | All Stormwater link pipes installed corect as per plans
53cafcb2-58f5-4275-a4f0-131ede1cccc2 | checkpoint | Manholes Hauched as per Detail and Code
aaa510f0-2172-4735-a9d7-269875fe8e6a | checkpoint | All pipes tested
ab2669b3-8ce2-4aa6-b2f5-1a165364c7c4 | checkpoint | Photos Taken
bdaf27eb-ebdb-458d-a86c-6b3faf66cb47 | checkpoint | Engineer/ Council Inspection passed