## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
59740568-c7a3-450f-8aea-be2af74d63d5 | checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 01 - Waterproof Ensuite Base |  | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 01 - Waterproof Ensuite Base
933d8624-d86f-438b-a664-4b7d8a51e313 | section | 2 - Construction Inspections
86840d61-1425-40c6-8981-478123887092 | checkpoint | Inspection Details
cab155b4-74d4-5342-ae84-c217811c4561 | textbox | Level:
d278206d-34b9-5c5b-af74-7bcce90290cb | textbox | Zone:
b37b6a11-d6db-4494-bffd-7d7d5039d854 | checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
7dae2d54-b4c3-5662-b25f-58440329b49b | note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
9a44f26b-9c94-591a-a0df-0ae149ba1df5 | note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
a02612c5-d492-5064-8ec9-131dbdb74f0f | textbox | Test/ Inspection - Measurement
5a0ebc78-8e58-5712-a893-4d8b125b2d4d | note | Test/Inspection Frequency - Each wet area, every 20m2
bbd5f677-061e-505a-9bac-7dcc1dae9a0c | note | Inspection: Subcontractor - WS (I)
98053fc2-c300-5985-bc3c-02b3564a5c9f | note | Inspection: John Holland - PE (S)
9f7fe22a-d79a-4077-b495-080430b4cc39 | checkpoint | 2.2 - Drainage installation - puddle flange installation
69ce85fd-c696-5026-aade-b1033defe3b4 | note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
93278d6a-b2d4-52b3-a12b-67f0d71ab7b9 | note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
55817f8e-9d79-5428-b997-11ff375e6842 | note | Test/ Inspection - Installation and Inspection
ce639751-bbf8-5257-9377-888466c52b2c | note | Test/Inspection Frequency - Each wet area
2c71b00b-4ada-5ec6-979c-885132fae44b | note | Inspection: Subcontractor - HS (I)
da96cfab-912c-5f1b-86d2-738b2ca57b99 | note | Inspection: John Holland - PE (S)
84c29cbe-b312-42d4-a52d-7685891b4eb8 | checkpoint | 2.3 - Substrate condition Inspection
ec3ed5f6-f743-5233-8375-3ada45fc3f2d | note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
ae5ab77f-512d-5734-a601-6f14b3ab51aa | note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
0bf076fd-0d42-5659-a561-e4362fb7d767 | note | Test/ Inspection - Inspection
92cc4c40-15e7-55d2-a78b-d18290925495 | note | Test/Inspection Frequency - Each wet area
d024a955-68a0-552f-b99e-33bbd31b3dde | note | Inspection: Subcontractor - WS (I)
c86b420d-986b-5c90-a645-20cf2ba319c0 | note | Inspection: John Holland - PE (S)
61d41109-867d-4b1a-bd58-cb82845611ca | checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
40520f26-64f6-5c0f-b638-6cd1a4dff83f | note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
d4b1eef4-f45d-5b24-9ede-c2c07349738e | note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
069d8f0a-5124-51e1-8fc0-66115823cb52 | note | Test/ Inspection - Measurement
519ef3a0-bb52-5229-a7ad-c8ad588713bf | note | Test/Inspection Frequency - Each wet area
ca1c2cc5-27d8-5966-b8d4-2c40dbc7b5d4 | note | Inspection: Subcontractor - WS (I)
3598ad4b-457a-5843-ab58-69c152123627 | note | Inspection: John Holland - PE (S)
315be017-08d2-4b83-a1cd-c4ce1ca24d05 | checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
cc3d2b9a-dc72-552a-a9a3-31187f762a47 | note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
4e2c9c9d-5e67-5e32-a66f-1d857a53105e | note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
8f156b79-6ffc-5f9f-b88a-1a0b823e971f | note | Test/ Inspection - Installation and Inspection
aa933a73-4d8a-5d2a-9010-05ae22a86a2c | note | Test/Inspection Frequency - Each wet area
64f944de-f209-5e06-9394-28170400a53a | note | Inspection: Subcontractor - WS (I)
5ef0827b-10f4-58ff-93c9-233ce397cdb8 | note | Inspection: John Holland - PE (S)
5cc33188-24ed-5c84-9e3e-94ca1516c445 | textbox | Records & Comments - Measured fall:
4a67ed99-4dfa-49eb-a21c-ebc073cb4938 | signoff | AUTHORITY HOLDPOINT
1cf907ad-1c5b-4fea-8240-04de37f5db22 | checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
2c2f6391-634d-5384-8f8b-382fe93d889c | note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
c66f6a54-921f-56c3-8558-8400af563f9b | note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
83d9f20d-a91d-5ed4-8ad8-2d993e6abd22 | note | Test/ Inspection - Measurement
9ab5178f-8456-50d7-836c-c2210d891c1a | note | Test/Inspection Frequency - Each wet area
e90e5de1-2b86-5c9c-8e7b-da0588df70d2 | note | Inspection: Subcontractor - WS (I)
031ac72d-1011-5efb-9649-ef2a0215609c | note | Inspection: John Holland - PE (S)
acf0c027-0885-4552-9b81-ae034c48c4d8 | checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
8164abc1-7d15-5f07-b869-24343c4fd591 | note | Specification Reference - GBA-SPE-AR-AS-0001
5f063bc9-3d58-5cc0-bd48-a344161e4fbc | note | Acceptance Criteria - Everything ready to install
e06bedfc-1f3f-5fda-bfd2-ee6daef9162c | note | Test/ Inspection - Review & Verify
92e58d5a-0c80-558d-9cb0-76962823167a | note | Test/Inspection Frequency - Each wet area
6c695e7f-14cc-5b4c-b262-570eb3030e1e | note | Inspection: Subcontractor - WS (I)
ebaed9a2-34cd-568d-b823-c6d00a2b8ade | note | Inspection: John Holland - PE (S)
addf77d8-c97c-548c-8f85-e5194480ded3 | textbox | Records & Comments - Temperature Reading:
29883a80-0d27-4461-96cb-1283130a2d61 | checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
86e29860-093d-52e0-b0a1-9b85a00de41d | note | Specification Reference - GBA-SPE-AR-AS-0001
144337bf-1bd8-52fb-b6ac-70e76f22dde2 | note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
1b3eaf21-cdfd-5f05-837c-ffb4f2e02486 | note | Test/ Inspection - Visual Inspection
5452aa3c-e6f5-5d8f-ba9e-7540ac37c165 | note | Test/Inspection Frequency - Each wet area
8051adf3-226d-546c-88fc-37d3855dbd86 | note | Inspection: Subcontractor - WS (W)
d228a58d-0761-565d-a3aa-3f5ec9aeeef1 | note | Inspection: John Holland - PE (I)
a61f299c-a0dd-585c-8c28-05de4b690e41 | note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
63e78437-84e0-5638-90db-3c81b3fd8502 | textbox | Applicator Names:
bf5e7ce3-1425-56b9-b743-1693c59b1b72 | textbox | Temperature at placement:
4c6c8efb-59b8-49de-a203-5668c6ddfc68 | signoff | AUTHORITY HOLDPOINT
deb324ad-1b8e-439a-95f6-e6348a4c775c | checkpoint | 2.9 - Apply TREMCO Primer - take a photograph of the primer container with technical details and a photo/video of the application
89d85569-b2b6-554d-96fa-89b914617217 | note | Specification Reference - GBA-SPE-AR-AS-0001
db9b0b4b-e1e4-5ed6-9206-3c11f8a38233 | note | Acceptance Criteria - TREMCO Primer Applied
d67219d5-dd27-52d9-8d97-b5c14e003d93 | note | Test/ Inspection - Installation and Inspection
c5d53ba2-748c-5f75-91ad-ce71da825180 | note | Test/Inspection Frequency - Each wet area
c2fcd4eb-ba40-56b6-bff4-20bdb845bbec | note | Inspection: Subcontractor - WS (I)
616f6811-f317-5ae3-af59-e65536d65342 | note | Inspection: John Holland - PE (W)
9bf79cc2-93bd-442f-825b-f30b0b6170aa | checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
3d92a60c-051a-500c-b867-ff84ecc08df4 | note | Specification Reference - GBA-SPE-AR-AS-0001
509630be-6971-5a3d-a59b-49ccb31db15b | note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
3aa5329a-ba93-5d34-bdb0-045179e3b6cf | note | Test/ Inspection - Installation and Inspection
4aa6c2df-a697-5da1-bf84-80477b9db942 | note | Test/Inspection Frequency - Each wet area
e6b6615a-0e5b-5c42-8964-8b1c64311cd2 | note | Inspection: Subcontractor - WS (I)
3f6ade71-e247-5d34-898b-66dee0f1a723 | note | Inspection: John Holland - PE (W)
38dd4a97-35e6-476a-9fb8-4084502ee9c8 | checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
317e1b92-8802-5e5a-956a-d9ce8d661085 | note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
9b9f7dd3-f09a-56ad-90c5-331a0051e721 | note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
184cfd7f-d7d6-58ce-bcb7-cf1575a47f40 | note | TREMCO Primer curing times
6bc9df63-e8bd-52ef-a81a-670d33e68365 | note | Full Cure time: 2-3hrs
4dff7a03-420d-5241-a3fa-1b23d2e0633b | note | Test/ Inspection - Installation and Inspection
75db2579-c861-5010-ab88-1eeb4f569e2e | note | Test/Inspection Frequency - Each wet area
08e554fd-308b-5243-80de-7972b93aa0ed | note | Inspection: Subcontractor - WS (H)
9a888972-1ce4-5333-8d2a-d8e0122ff390 | note | Inspection: John Holland - PE (H)
d9a515da-6af7-5334-8463-3f981137ffe0 | note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
9c990c1f-10d9-538a-b699-cf977d97472a | textbox | Layer 1 time:
a087d945-1063-587b-91a8-c52ed373a756 | textbox | Layer 2 time:
4a93cbe7-a467-45dd-8d67-fafca36f39a7 | signoff | AUTHORITY HOLDPOINT
127d0941-9ea9-48c7-b069-b349045924f6 | checkpoint | 2.12 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
12278258-7b9e-5b7d-9f79-a0e8c0285e16 | note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
6f48394e-75d8-5105-a295-74b0ea9a666e | note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
f64e8c31-c670-59f9-ad79-9ec36200ce91 | note | Test/ Inspection - Test
ca0e3a3a-9f82-5fba-850a-61249c1e9cdc | note | Test/Inspection Frequency - Each wet area
c621ddc7-eeb0-5318-a3f1-f1e41a67f2c9 | note | Inspection: Subcontractor - WS (I)
d60e6895-d165-56a0-8236-b443b78fcb1f | note | Inspection: John Holland - PE (W)
d70b92f0-7305-527f-a4f6-c4d42052d5ae | note | Inspection: Site Manager - DC (W)
5af2c79b-2f16-50e8-85f4-1a9fe5b08cf2 | note | Records & Comments - Pass or Fail
da57220a-066e-58d1-b860-2a355a1c98c1 | textbox | Observed setting time:
6687c715-89b4-49f5-8e4c-6203c47e6cd5 | section | 3 - Close-Out
2a28bbc2-add1-4467-87a2-6887e8217d36 | checkpoint | 3.1 - ITP close-out.
fd341994-e22a-548a-8351-5e7f77dd4f2c | note | Specification Reference - GBA-SPE-AR-AS-0001
0ea06e54-47aa-5586-944e-38b41eb4e685 | note | Acceptance Criteria - All prior items of this ITP have been complied with.
8abf0876-4966-5a61-856b-756f056a4944 | note | Test/Inspection Frequency - Each Lot
e29a7d93-3be7-51a2-a99e-8944387123eb | note | Inspection: John Holland - QR (R)
39e1033b-341c-5f4c-9596-88d345b5cc88 | note | Records & Comments - Check all measurements are recorded and photos attached.
7a6ef1be-8cc7-5622-8735-7c840d8b8c09 | note | All records loaded into the Work Lot System and Verified.
de4d4179-ff62-4d57-bd82-92f025abb427 | checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 04 - Epoxy Cove to Ensuites |  | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 04 - Epoxy Cove to Ensuites
c734ef3c-d082-43dd-b892-2eed0f383abd | section | 2 - Construction Inspections
bdbc18d0-7dd0-455f-8720-dfaff741ae33 | checkpoint | Inspection Details
8b44dd3a-1dd7-5e2b-b6c0-9e3dc9125b2d | textbox | Level:
ca25acb0-8685-5754-9fc6-f7eaff176cfc | textbox | Zone:
49941a0f-54e1-4085-a4fb-4c92224fac28 | checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
e1ac63f6-b7ea-5323-accd-ee9a613c3b1e | note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
ef11dab9-2ffd-5ed9-bb6d-de3ee537eb8c | note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
c2040d9c-e30d-5642-b636-0fafc03a1cca | textbox | Test/ Inspection - Measurement
bbea77f2-6bf9-54f5-bf52-65f4ca7f8702 | note | Test/Inspection Frequency - Each wet area, every 20m2
a705ab1d-a415-5a57-845f-b65714ca18fd | note | Inspection: Subcontractor - WS (I)
a60f884f-2c6f-52ff-8846-727e559f9662 | note | Inspection: John Holland - PE (S)
37a25879-a1ad-48e5-a6dd-8825841d1496 | checkpoint | 2.2 - Drainage installation - puddle flange installation
373f8b11-da38-5935-8f45-e1bf80021ca4 | note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
a6d5c264-63bd-571d-bca7-55c87dfea678 | note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
306dabaf-7cf9-537f-8b1d-25a7f2e97ec2 | note | Test/ Inspection - Installation and Inspection
cc2afce6-cc82-5b18-b4f9-239c1775c09d | note | Test/Inspection Frequency - Each wet area
5a44069d-8a63-5167-aeb1-fe9c94ea88c8 | note | Inspection: Subcontractor - HS (I)
e755d374-d6cb-51f5-bcc0-77e9c5f51cc0 | note | Inspection: John Holland - PE (S)
39c8d950-5a76-4d03-aa1c-c05cfb5ecdbd | checkpoint | 2.3 - Substrate condition Inspection
b7fd1834-ea58-5cb9-a8c3-29ae50b3855c | note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
ad61b424-cb6c-5074-834d-927bc8ac2117 | note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
b8d1a0cf-f9fe-5e75-91ee-ea6f24cd7d25 | note | Test/ Inspection - Inspection
a07b0e8a-4cff-5376-b47a-13aa7efa09db | note | Test/Inspection Frequency - Each wet area
151641f0-4702-5d1a-bac8-be06b1c2745b | note | Inspection: Subcontractor - WS (I)
9b7e919c-e1b5-53a2-9e2f-56ee7d10f9cc | note | Inspection: John Holland - PE (S)
a601365f-6e77-4399-8d00-322843ae8bb7 | checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
981ff686-6e70-5a67-b39f-5bb0fd9432f5 | note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
914c2cfc-597f-5508-8019-85e943023d41 | note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
00c922dd-5533-537f-a362-9a756fec2745 | note | Test/ Inspection - Measurement
93e9d3a5-9e46-5322-b932-0953f984630d | note | Test/Inspection Frequency - Each wet area
b2b4e84b-5d87-523e-a3fa-fbfbe113be39 | note | Inspection: Subcontractor - WS (I)
96ee8337-de4c-5f5a-85e9-c091b536e549 | note | Inspection: John Holland - PE (S)
1f6c1b4b-fcc3-42f1-adc8-36e500f6f1b9 | checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
406176f4-4554-5426-ad3d-da278b800fe3 | note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
9bb203ff-a316-5f66-ba5b-6934ed1a9ab1 | note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
4bd81646-8343-5bc3-8ff1-311547cf8684 | note | Test/ Inspection - Installation and Inspection
c1b61334-83b1-5534-943b-0e6de72119bb | note | Test/Inspection Frequency - Each wet area
80a5f57f-55e5-5656-83bb-f81dc78df407 | note | Inspection: Subcontractor - WS (I)
f5616b07-321b-5a43-8f4a-43f834cac152 | note | Inspection: John Holland - PE (S)
589b81e9-f340-5d8e-bfac-6f535c27afa1 | textbox | Records & Comments - Measured fall:
f3c0748d-b0cc-4fc1-8439-08f7bb8b714e | signoff | AUTHORITY HOLDPOINT
3c4f683b-91aa-4f67-b347-2e7c2145fbcc | checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
b3f69db0-dba9-53fc-8ea5-4d4a378c7fd2 | note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
4d8245fe-ef0e-5aa1-92bf-88ce03b08077 | note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
b6007af8-2102-526f-8985-ce32ef31c0aa | note | Test/ Inspection - Measurement
cc6cf3e3-b293-5fef-9e92-7494bac9a7a5 | note | Test/Inspection Frequency - Each wet area
b33fe59d-10d3-5b9c-bd8f-19a67a4ffcc6 | note | Inspection: Subcontractor - WS (I)
e17026dd-80d7-50f7-b184-93d88771ae16 | note | Inspection: John Holland - PE (S)
e19e33b6-1f33-4aca-9148-5c9abc494f49 | checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
64f5601a-719b-53e6-8389-76e77785bf78 | note | Specification Reference - GBA-SPE-AR-AS-0001
74e866dc-38b3-5aee-8ae3-1850bedafff6 | note | Acceptance Criteria - Everything ready to install
40d0420f-2b2b-5020-aa20-67555d8e74ed | note | Test/ Inspection - Review & Verify
b12fc576-01c3-5cbc-8963-e07348c70bcb | note | Test/Inspection Frequency - Each wet area
f621b8c4-00a3-50cc-9ae3-7c89a57525b4 | note | Inspection: Subcontractor - WS (I)
5e69ad1a-5cac-518f-8abd-6511b5940cca | note | Inspection: John Holland - PE (S)
2210d925-09b5-55f3-9a3b-fbcea6016da4 | textbox | Records & Comments - Temperature Reading:
ceff4968-9ca1-4991-88a5-1acf5614ab50 | checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
0d664132-112f-5ac9-b5b5-6590a2845cf5 | note | Specification Reference - GBA-SPE-AR-AS-0001
a1dd07ac-8da9-5ca7-a9e6-62035ff64326 | note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
076681d0-d3a6-5ccc-be7a-cb9f199a3e35 | note | Test/ Inspection - Visual Inspection
fdaee7ac-ee82-526b-9577-9a90eed74e0a | note | Test/Inspection Frequency - Each wet area
aa59c6af-6247-5e5c-a774-c6f341f152d3 | note | Inspection: Subcontractor - WS (W)
194a5620-5aab-58c1-a74c-8f81e852046c | note | Inspection: John Holland - PE (I)
debd0064-2fd1-597f-87b1-25d4568a824e | note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
eb44bd52-f7e9-56ae-8395-a417e425e7d1 | textbox | Applicator Names:
b31696f2-7600-53f4-86d2-c908d13e3ab2 | textbox | Temperature at placement:
a0e3a80a-fbfd-4a25-96b1-d16679b1e628 | signoff | AUTHORITY HOLDPOINT
1e3963cb-016f-433a-a739-2550219fa2ee | checkpoint | 2.9 - Apply Flowcrete Resin Primer (with sand) - take a photograph of the primer container with technical details and a photo/video of the application
5ccedb61-96f9-5f5e-b805-a8e11ce40292 | note | Specification Reference - GBA-SPE-AR-AS-0001
c2386289-08e6-5c7e-891c-8f0dd3b7f439 | note | Acceptance Criteria - Flowcrete Resin Primer (with sand) Applied
47aebeca-aef8-5b76-ab1b-c532b818178a | note | Test/ Inspection - Installation and Inspection
1abcf3f7-f741-5a18-9a46-c91d29711479 | note | Test/Inspection Frequency - Each wet area
02595bde-4792-559a-9ee8-a6105717cc1d | note | Inspection: Subcontractor - WS (I)
6d9f2045-41fb-5399-8a27-f04f604deb31 | note | Inspection: John Holland - PE (W)
676ecb67-7415-4c43-8eff-c692cf16c19e | checkpoint | 2.10 - Apply Epoxy layers in line with data sheet and the figures in AS3740 - take photograph of epoxy container with technical details and photo/video of application - note details of timing on checklist
fb6352dd-f98e-5e13-a791-35f4f8335117 | note | Specification Reference - GBA-SPE-AR-AS-0001
ec49e960-bee5-560f-9e9d-60da86c58130 | note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
d8c92336-8168-58e1-86c6-69272972ab72 | note | Test/ Inspection - Installation and Inspection
ee5fad69-30aa-537c-a98a-6cda3f7cfdaa | note | Test/Inspection Frequency - Each wet area
5abaa3f3-17ec-599b-b9ec-c68fb85ab1e6 | note | Inspection: Subcontractor - WS (I)
8c137040-9261-5bd0-b9ca-059719e99ae0 | note | Inspection: John Holland - PE (W)
1bc67400-3e08-4bf0-8f74-a9cbc8cb1fa3 | checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the epoxy and completion of installation.
95fa2159-a2d9-50d2-bd38-23b9f88c11a0 | note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
bd5d45a4-38f1-5fa5-b50a-0d81f28d04cf | note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
d0e87f00-1bea-5f19-9d7b-6672934cca74 | note | Flowcrete Resin Primer (with sand) curing times
0aa49114-7063-51d1-a972-f66a16bec950 | note | Full Cure time: 24 hrs at 20°
a4999ec0-f4f3-5944-8247-010d5bd93d0e | note | Test/ Inspection - Installation and Inspection
e63cd52b-b3ed-58ef-85dd-1c50a0e9245f | note | Test/Inspection Frequency - Each wet area
5a91e466-c82e-566d-b3c0-7f3cdc08060a | note | Inspection: Subcontractor - WS (H)
d0c443cc-eaf5-5833-b24e-14da88829335 | note | Inspection: John Holland - PE (H)
5dc53f70-1462-5c8f-a5e6-1984b837f2be | note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
5bf8efe4-a08a-54ca-a5a2-98619ddca488 | textbox | Layer 1 time:
02126d05-2608-5a32-b1ca-b9ec114d7b3c | textbox | Layer 2 time:
c0097244-56a0-43a4-aa0f-767ec349654d | signoff | AUTHORITY HOLDPOINT
d0f9ea95-1d5e-4b56-9060-71aa7792f624 | section | 3 - Close-Out
0ec7112c-9734-4e04-8531-ba042e63f529 | checkpoint | 3.1 - ITP close-out.
3ca1e8d2-507c-54bf-9aba-1093510275fe | note | Specification Reference - GBA-SPE-AR-AS-0001
9b118d20-303d-5b78-8331-69993bfaa41e | note | Acceptance Criteria - All prior items of this ITP have been complied with.
f5466cd7-7f88-5a93-a8b3-32f98ac2b8dc | note | Test/Inspection Frequency - Each Lot
c70cd5e9-550f-5cba-a373-676e2d6bc7b8 | note | Inspection: John Holland - QR (R)
74a0c27e-f4dd-5420-a0a2-d401064317e1 | note | Records & Comments - Check all measurements are recorded and photos attached.
b281b954-d1cd-5bfc-9aa8-1cf841d873b5 | note | All records loaded into the Work Lot System and Verified.
c4906f59-254c-4ca2-9822-357f5e713f8f | checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 05 - Vinyl Flake to Ensuite Floors |  | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 05 - Vinyl Flake to Ensuite Floors
c28ba002-b3ac-4bbe-b0f4-9f7573ba6971 | section | 2 - Construction Inspections
0c7e8ec2-c349-4f33-8385-c7fc98cf53e2 | checkpoint | Inspection Details
415b1164-049e-5a92-a55b-0049e0b7dce6 | textbox | Level:
885ad02b-22d0-5543-b3e3-c96bf542113b | textbox | Zone:
5f96d6e5-bea7-4172-b43f-19118ee76f49 | checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
cfb919b5-9e6e-5a6b-b66b-5f5bc6e939f4 | note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
e807ebf8-d893-5ee4-990f-272407cdf3a8 | note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
63b50365-5111-5445-ac2e-144e52899119 | textbox | Test/ Inspection - Measurement
602464c3-46b6-5f67-9bfd-3ec69e3bca92 | note | Test/Inspection Frequency - Each wet area, every 20m2
4c75f12b-0107-5600-8719-0f996af69985 | note | Inspection: Subcontractor - WS (I)
902a4373-3ad8-5772-a0a5-e406a2f1e588 | note | Inspection: John Holland - PE (S)
ac7e3aa4-93b8-40cf-96ba-a8cb8bb94175 | checkpoint | 2.2 - Drainage installation - puddle flange installation
5c0e4391-1168-5b4b-9118-334d6036cf04 | note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
921034ca-f2e6-548b-8a4f-d78e63654036 | note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
16f60a1f-20d5-5f84-a86e-962dba489934 | note | Test/ Inspection - Installation and Inspection
6d860e06-1e34-50f6-9a29-0922ee009992 | note | Test/Inspection Frequency - Each wet area
baf5ee5c-0e92-5bc5-9251-890b539af18d | note | Inspection: Subcontractor - HS (I)
bb08898c-1290-5256-9004-2c7195edaceb | note | Inspection: John Holland - PE (S)
451ce4f2-0eeb-4e9f-9d21-ffeb6481fa9f | checkpoint | 2.3 - Substrate condition Inspection
8b5e64bd-5ab5-5bcb-a20c-91e67826bb0d | note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
a90fd467-dac2-52f8-a637-96816d673e37 | note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
cbbdbb7a-b12b-538a-ba9e-9465599a1412 | note | Test/ Inspection - Inspection
488c4f06-b24c-5891-88bd-3de9eb0b0eb5 | note | Test/Inspection Frequency - Each wet area
46f25f13-8dcc-55d8-abf6-01caddae9bae | note | Inspection: Subcontractor - WS (I)
01918f5a-a62a-5543-8071-cb4d1baa551f | note | Inspection: John Holland - PE (S)
57516d56-0197-4206-b6f0-f704669cf29c | checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
7e30bd7a-a394-5e52-8e2b-e90bf6ed2671 | note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
b0bee1ba-0704-56be-9986-7487fa5d3d9c | note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
899768cf-d202-5af1-9bc4-558587574e57 | note | Test/ Inspection - Measurement
2db40c69-cc17-5ee8-a2b9-a429f0b522d2 | note | Test/Inspection Frequency - Each wet area
1204017b-eba1-5cbe-8ed3-1f37730e0a3a | note | Inspection: Subcontractor - WS (I)
7908f551-408e-5269-b162-b80c9d53fb4f | note | Inspection: John Holland - PE (S)
3899c94f-a97a-4864-8e25-b00e2059104b | checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
dbf5d570-57e2-5f82-901f-af91d7a55e0c | note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
2f5bb83d-4ef0-5c64-8812-dee843de4fc7 | note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
e706a161-e8dd-5ba4-82b9-2e8472a920f2 | note | Test/ Inspection - Installation and Inspection
486a12d3-83ad-52f4-b6a4-bbe667843fd9 | note | Test/Inspection Frequency - Each wet area
26d2c6c3-ce22-5399-a7b4-3f7bd0bd96aa | note | Inspection: Subcontractor - WS (I)
f7ef25b3-e25d-545d-bc90-e08a31e00b06 | note | Inspection: John Holland - PE (S)
e4fa2196-271b-5956-b295-7d0c7cc06663 | textbox | Records & Comments - Measured fall:
86a26802-4b33-4b92-aa4d-719184367bc1 | signoff | AUTHORITY HOLDPOINT
e72c1616-0944-4a67-bf3c-aa38d6045715 | checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
84fd2d7b-92d2-50c8-8b4c-33182e6e8e73 | note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
726237b3-c192-526e-9569-524b59b27dd9 | note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
e72731aa-7c17-5f5c-977f-c0e1c9eb5bf2 | note | Test/ Inspection - Measurement
16543341-122f-5f4f-88db-23da69202627 | note | Test/Inspection Frequency - Each wet area
8d5a623d-bcd1-5909-8baf-7381beb83178 | note | Inspection: Subcontractor - WS (I)
f623f607-f4c1-5908-b5d8-21223bcd0614 | note | Inspection: John Holland - PE (S)
3f0b5d97-5ace-4af5-a078-6d8a30d62353 | checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
0cb74ebb-f341-5b13-8665-f2702de93725 | note | Specification Reference - GBA-SPE-AR-AS-0001
eeb6ed38-d8a6-50ff-9a5c-6d9b7a14c99b | note | Acceptance Criteria - Everything ready to install
64d8befb-344c-5b9e-8f7d-87c388f8bda3 | note | Test/ Inspection - Review & Verify
a7dbc55b-4480-53dd-a2ba-8d8279fe1deb | note | Test/Inspection Frequency - Each wet area
588d2595-081b-5b7c-a513-4668bc5abe99 | note | Inspection: Subcontractor - WS (I)
0f7f455d-e189-5e37-8332-304d95690bf4 | note | Inspection: John Holland - PE (S)
53ae6d5f-cd63-5a6a-bbee-e812c556e020 | textbox | Records & Comments - Temperature Reading:
f073275e-51a3-409b-bf04-fceb083ef85a | checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
b0cc3902-a5d1-54e6-8070-6a221c59062a | note | Specification Reference - GBA-SPE-AR-AS-0001
1a70b786-cf2c-54c3-a3c6-7cfd796be88b | note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
4af4785a-a7e7-5307-865a-86ad72aeb847 | note | Test/ Inspection - Visual Inspection
195cb60f-2403-5036-b62e-e29c9d854b06 | note | Test/Inspection Frequency - Each wet area
cd84f065-338a-52fb-b907-bd311c5bdd58 | note | Inspection: Subcontractor - WS (W)
f4bbeb9d-526a-5c7f-ae48-ad2c07890e90 | note | Inspection: John Holland - PE (I)
8d8ea405-90f7-5a76-9398-2a84d628630e | note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
341e9dda-34c2-5e5e-8cbd-16359370d5fa | textbox | Applicator Names:
386db646-f48d-56ca-8364-f08d96700311 | textbox | Temperature at placement:
e34ee2bf-db4b-442e-8a74-f89fe63448fa | signoff | AUTHORITY HOLDPOINT
9c99cf2b-b1aa-44b4-94be-ae2114356106 | checkpoint | 2.9 - Apply Flowcoat OP Suck Coat Primer - take a photograph of the primer container with technical details and a photo/video of the application
e3122210-9ae9-56ef-a784-ee3a80388162 | note | Specification Reference - GBA-SPE-AR-AS-0001
ff4e932e-851c-5fcb-87b3-e8ae7b8dd496 | note | Acceptance Criteria - Flowcoat OP Suck Coat Primer Applied
d1f97a51-7c03-59a6-a531-e24e3a100f3e | note | Test/ Inspection - Installation and Inspection
d796dc43-ec64-5817-aa37-f8c88905d3cd | note | Test/Inspection Frequency - Each wet area
5dbc6b13-81f9-534d-8d10-d60e13b54058 | note | Inspection: Subcontractor - WS (I)
04adc975-d651-5b6b-bda2-54898b786fbf | note | Inspection: John Holland - PE (W)
c4e48dd3-9747-4c57-9517-7953ebb8bcdb | checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
209b129e-f19f-57f3-af76-66faf117ab2d | note | Specification Reference - GBA-SPE-AR-AS-0001
31a01307-523f-5e58-94cd-959457fdf79c | note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
9ac5ea0f-b91b-55f5-8b84-bd97a7e126b3 | note | Test/ Inspection - Installation and Inspection
98cd52ae-d375-58b7-a326-792ee62b7c37 | note | Test/Inspection Frequency - Each wet area
e7ff1a29-15d5-5de3-91c9-36d134b4f757 | note | Inspection: Subcontractor - WS (I)
e74bed99-df4b-5fe6-829c-9f2ad15dfc72 | note | Inspection: John Holland - PE (W)
40c90799-ba42-4665-886b-0791850c4c0f | checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
c2bc5d1b-31df-519a-8025-c9cb4f124bf7 | note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
2ecdab18-26d8-5b8d-bc33-4a09c80093e1 | note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
cb3bf72d-2a9e-5f3b-83b4-6e29fdf6d8e5 | note | Flowcoat OP Suck Coat Primer curing times
5de24166-10b0-5eaa-b4c3-060c95738ce4 | note | Full Cure time: 24 hrs at 20°
d23cb288-9dd4-50ee-95fe-f8f8bb54964a | note | Test/ Inspection - Installation and Inspection
b88e01ab-5435-530d-b17e-6ac4f6960621 | note | Test/Inspection Frequency - Each wet area
4041bc98-e091-50e1-8751-bfe5bbe08e9c | note | Inspection: Subcontractor - WS (H)
b8b72147-7b88-5028-abab-ffd391c599fe | note | Inspection: John Holland - PE (H)
130b47f7-9251-5a38-8d03-3940f4c18cc8 | note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
3bfaccd6-57ee-5516-bc52-892b1ba67172 | textbox | Layer 1 time:
09b3e165-98a6-582c-a793-8281b1b8be7d | textbox | Layer 2 time:
cb92591d-1409-47f3-95fc-887797a84204 | signoff | AUTHORITY HOLDPOINT
d5981e78-c4d1-4234-a15c-b1cde469bf6a | checkpoint | 2.13 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure protection has been applied to Vinyl Flake.
632da26a-cd51-5841-a1ad-135e1e74e25e | note | Specification Reference - GBA-SPE-AR-AS-0001
57819992-f3c5-515f-81fa-1f62807a0a2d | note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
35b11093-6ba7-5d66-ab06-d63c250fd448 | note | Test/ Inspection - Installation and Inspection
1b57491c-95d7-55b3-9be3-aa40343f4816 | note | Test/Inspection Frequency - Each wet area
9c6110b2-0d59-5d71-b7e7-0142062d9786 | note | Inspection: Subcontractor - WS (W)
d1f09f6a-0761-55c3-9e0c-2535b8fb39ec | note | Inspection: John Holland - PE (I)
495798c3-f99c-415b-965d-d123f2b463a1 | section | 3 - Close-Out
68541eb7-bed1-402b-aa98-c3e25999740c | checkpoint | 3.1 - ITP close-out.
2b3c1272-db5d-59d2-bfd6-8a3e01931947 | note | Specification Reference - GBA-SPE-AR-AS-0001
ccf39850-9ffa-56fb-b728-6273a8d5fbe9 | note | Acceptance Criteria - All prior items of this ITP have been complied with.
9428baa5-81bf-5791-96f6-14f648143d78 | note | Test/Inspection Frequency - Each Lot
8495c185-5a72-5011-87eb-5b77d93f3e3d | note | Inspection: John Holland - QR (R)
0cad43d9-b45c-5f4f-869e-74c679be2d1e | note | Records & Comments - Check all measurements are recorded and photos attached.
604e9271-7ca1-52e1-ad4a-059dc66cbad9 | note | All records loaded into the Work Lot System and Verified.