## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| 91d26fa5-d4ce-55fc-ad63-d4e5ca215890 | checklist | Add Application of Hychem PMMA Waterproofing System Checklist |  | Application of Hychem PMMA Waterproofing System |  | 0abaa31b-a04e-45f1-91d3-4fe40d5f169e
| d7ad8134-16e4-575a-8788-70f60b9191ae | checkpoint | Preparation of area by captive shot blasting & mechanical anchor cut around perimeter
| 44c850fe-21e8-5cc1-ab4e-9c19829bd164 | checkpoint | Application of Hychem Polyac 18 Primer @ 0.3-0.5kg/m²
| d53a01cf-9410-532e-a96c-64b05846c273 | checkpoint | Application of Hychem Polyac BDM-M (DU) Waterproofing Membrane @ 1.8kg/m²
| 348faf84-f372-5c2f-b722-d01a82fcae92 | checkpoint | Application of Hychem Polyac 55 & Polyac Filler SL Wearing Layer @ 2kg/m² w/ broadcast of 18/40 sand to general areas & bauxite to turning areas @ 3kg/m²
| 00e0746f-e673-5c65-a14c-c4dccea34453 | checkpoint | Application of Hychem Polyac 61 (DU) top coats @ 0.8kg/m² in Traffic Grey RAL7042
| 8b0d76d8-a2bd-592a-b159-4edae9d9bfc9 | checklist | Add Crack Repairs Checklist |  | Crack Repairs |  | 69d307a9-7e6c-43e3-a4d1-e4ec5c1600a2
| ff5b0eda-6cc1-571c-8095-aa0a3c03c981 | checkpoint | Identify cracks requiring repair
| 686f1d34-9eaf-5723-a9bc-f46a50d67c52 | checkpoint | Mechanically chase out crack
| 4da56a18-96ab-5d51-b1b6-a957147d8ca8 | checkpoint | Application of Hychem Polyac 18 @ 0.3-0.5kg/m²
| e965910b-e6b7-5ff6-b2ca-c3db1a7dfaf0 | checkpoint | Application of Hychem BDM-M Membrane (DU) @ 1.8kg/m²
| d1febbc9-6d1f-5b53-a749-36b227229217 | checklist | Add General Information Checklist |  | General Information |  | 4d1e05d0-40b5-4334-80e1-7ce7e5aac3a6
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| 03552e0c-8443-4d64-aeb1-91ea178364b1 | textbox | Client:
| 9a9a5acc-12b0-440b-9eff-ffb6729c5058 | textbox | Contractual Works:
| 663c6a26-4c01-4817-a26f-2f4529050ad8 | textbox | Supplier:
| b0a3e70a-d668-4ffe-9888-dc4c7174127d | textbox | Area Size: |  |  | m2
| ce82e516-8478-483a-b970-ef0ea241dd03 | textbox | Plan (See Attached)
| 556f3c0c-3e44-4a8f-8373-42c8d113eab1 | textbox | Warranty:
| 71bb5887-6fc2-5325-8571-af4400160fa3 | checklist | Add ITP 0003 |  | checklist |  | 84bb926d-954c-4740-b7d3-d9dff7ace41c
| 203faf94-71c0-55e2-adb6-6b99d5c58027 | section | 1.Preliminary /Design Items
| 32767b3f-40e5-5bbf-b629-64d48522f1be | checkpoint | 1.1 approved IFC drawings are to be received prior to commencing procurement or shop drawings
| 2dc8223a-28c7-4425-84ff-deb8740800c7 | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| 6f37f1d5-1c07-4239-8cea-2f3cfd4e7c44 | note | Timing/Frequency: prior to commencement
| e4e57684-6c38-4dc7-ae62-469db049c54d | note | Acceptance Criteria and Verification Record: approved construction drawings
Invalid dependant | 8a1e6b0b-db43-5e7b-a71f-202f845d4fd9 | signoff | Sub Contractor Hold Point
| 6d0d5d71-48a7-509f-9f40-0120824cd242 | checkpoint | 1.2 Each work lot for the total works is to be identified
| d6febcb5-fbfe-47c3-8488-5c60fdb9fb55 | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| 385d3fb6-c2b7-45ea-8656-084355ec5451 | note | Timing/Frequency: prior to commencement
| f613cc5d-16dc-4f67-978a-124f0b8c7452 | note | Acceptance Criteria and Verification Record: Lot Register/Diagram
| e4a156c7-4514-5c9b-acfa-b3156a9bea03 | checkpoint | 1.3 Before commencing to install flowcrete epoxy/polyurethane submit the manufacturers' published niformation for products to be used
| 4cf4732d-568a-483e-8e0a-c54ed9f372f1 | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| ef183808-ec9d-4418-9355-d315117b4510 | note | Timing/Frequency: prior to commencement
| 46633513-1b78-47e1-a82c-2931ccc22485 | note | Acceptance Criteria and Verification Record: Material technical data sheets and safety data sheets
| 6519ea89-24a5-534b-9bca-c73e61a6b5ed | checkpoint | 1.4 Submit proposed epoxy materials types and systems,inc. tech.data and full product descriptions
| 524e6bf4-f2d3-47f1-aafc-6d5227d769e6 | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| aff06ba9-8a24-4da3-8f11-0583a1df9b57 | note | Timing/Frequency: Timing/Frequency
| e62dbe3a-d80c-4d29-8427-449d3d55af54 | note | Acceptance Criteria and Verification Record: manufacturer technical manual full product details and properties product msds certificates of compliance with specification from suppliers
| fe0e5905-f0d6-5bc0-bcf9-606347096e9c | section | 2. Installation - Pre Laying
| ec1d187b-20c5-5667-aa65-881f42d5252a | checkpoint | 2.1 Set out and levels are to be in accordance with the specified requirements
| aec7303e-1003-42b7-bc95-eedf8a94dcec | note | Applicable Standard: approved construction drawings
| b155f7f8-d33f-4de9-b878-f63fc0615e87 | note | Timing/Frequency: at commencement of installation
| 71163ecb-af81-440b-b26c-20fdd466008b | note | Acceptance Criteria and Verification Record: ITR
Invalid dependant | 23a83f61-9861-5c05-acc4-9ceb235e0c0b | signoff | Sub Contractor Submission / Hold Point
| 1ee96a59-d657-586c-903f-3695e3839b6c | checkpoint | 2.2 storage of product as per supplier recommendation
| 1ee8041a-56f0-4ad1-bee7-edd519dd6213 | note | Applicable Standard: relevent flowcrete product data sheet flowcoat sk, flowseal uv data sheet
| 4163ae33-46c9-4a76-a036-f39de32469d7 | note | Timing/Frequency: on delivery to site
| 0f79783c-460f-4ed5-9614-d0f7fe28af50 | note | Acceptance Criteria and Verification Record: ITR
| 1114fd5f-5e03-58a4-a415-bfeaf6937ce3 | checkpoint | 2.3 Surface preparation - substrate compressive strength >25mpa
| 05714f49-26fb-4217-bfd8-a8cd65b8066c | note | Applicable Standard: relevent flowcrete product data sheet flowcoat sk data sheet
| 15bfae4e-d5ad-4500-b774-7302875b822f | note | Timing/Frequency: prior to installation
| 118b17bc-c572-4c03-99c1-f9a7795fbe57 | note | Acceptance Criteria and Verification Record: ITR
| 5828027e-ef00-5993-9c44-014aa2bf85b2 | checkpoint | 2.4 Surface preparation - moisture content < 75RH
| a856daf3-2230-4ab6-a4fa-2ab0fe52fc6f | note | Applicable Standard: AS1884 & ASTM F2170 using insitu probe Method.
| af94565d-f82f-4458-acfd-c6d6b2f627cb | note | Timing/Frequency: 3 per first 100m2, 1 per 100m2.
| 58ae662f-d447-4def-96cf-63bb49100043 | note | Acceptance Criteria and Verification Record: ITR
| e4c84321-f879-57f7-84bf-7d0c33218636 | checkpoint | 2.5 Surface preparation surface prepared for adhesion to achieve concrete surface by - grinder/shotblaster
| ea4a715a-6774-42d7-a9d4-2acce2a8f6ca | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| dcf03fe4-4d5d-4d5f-9e8c-9598c09ed1a5 | note | Timing/Frequency: prior to installation
| aae6aa47-d54f-453d-969c-f3d54a2dd802 | note | Acceptance Criteria and Verification Record: ITR
| 899dde14-04fe-5342-9e33-9d4c0f8d61b8 | checkpoint | 2.6 Carry out moisture test
| 8d22a672-27f5-4a7a-91e9-0a8d01bc233e | note | Applicable Standard: J0024-WBR-0937-000-AR-SCN-0579_5
| 63cd698a-1a6b-48e4-a12f-4b3884e789cd | note | Timing/Frequency: prior to installation
| ffda3948-3e35-432f-8c9e-5cd5458df092 | note | Acceptance Criteria and Verification Record: moisture test meter: Wagnr rapid RH4.0 EX ASTM F2170 if moisture content <75Rh apply 1 coat of flowcoat sk if moisture content >75Rh apply 2 coats of deckshield ed
| a5c2be9c-db06-5477-8d34-58639a3a8a15 | checkpoint | 2.7 Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: mixing station method sufficient available product correct tools available sufficient man power adequate unimpeded floor access free from other trades check other trades have not entered
| a28d933a-1aec-4909-a2be-a610ecb9f60d | note | Timing/Frequency: prior to installation
| 65630e45-e6d6-4d52-a8a8-6d71841b01a0 | note | Acceptance Criteria and Verification Record: ITR
| eb18ca5b-c236-5e45-95a4-e29e75cc74ab | checkpoint | container
| 2b91d3a3-f46b-4a62-9ff4-c7b0b0120ce8 | checkpoint | container
| 6db400ec-521b-4311-9960-fdbd708ae19d | checkpoint | container
| 8ed239b6-773f-4a94-81e8-07926ba7baf3 | checkpoint | container
| f3d496a1-8d69-40bc-ad36-29b1c34a03b7 | checkpoint | container
| 1b793797-c8b3-4c84-87c8-725e55f85394 | checkpoint | container
| d83792bb-ae55-4826-bcf2-b0fe1c40eed2 | checkpoint | container
| 30c799f0-5dd0-45c3-9761-de9da0d9c20e | note | label
| 3d9999f3-7a03-4588-b1ba-d8a606eb5572 | note | label
| 9fb084d1-5b6a-4c33-81cb-201b13342d13 | note | label
| 45fd8679-7b20-49f1-bd64-1e35fc5a15e8 | note | label
| 3bd53377-27b8-4af3-8958-08145c4f37ed | note | label
| 5baf5718-3b58-4968-8d05-68232a9fa572 | note | label
| 06b11257-9e16-4b62-8656-d14f46103ba3 | note | label
| 70b023ef-0140-400d-968a-c2995858ae40 | note | label
| 218341f6-8405-46a2-aba2-0813dd3d8d0d | note | label
| bd07102f-18f0-5c8c-b0a0-4cd1cb677588 | checklist | Add MRP Checklist |  | MRP |  | fa5bcf56-8317-435d-97b7-63a02fdc0e7a
| 31004f57-e9d5-5561-9834-e2079dd9be0a | checkpoint | Mechanically grind floor
| 8f3ad2ec-563f-5d2a-9508-4b45a3c7dc4d | checkpoint | Application of Sika 94 epoxy primer
| ada27768-3aed-56a4-97cf-bf0fa23f9b6b | checkpoint | Application of Sand/Sika 94 epoxy sub fill to falls (1:100)
| 95739cf6-7d09-5d64-ba40-0b78712ea10e | checkpoint | Application of Sand/Sika 94 cove mix to form 50mm radius cove
| 330b9034-4a56-5821-b284-13f7248f3fce | checkpoint | Application of Sika 94 suck coat to sub fill and coving
| d1d6b716-88a3-5a53-a3da-e816fe3d2f8f | checkpoint | Application of Sika Purcem 4-5mm system (Dusty Grey)
| f7fbe741-3064-5946-a8e9-20f47c37e7e1 | checklist | Add New Supermarket Checklist |  | Supermarket Checklist |  | f1d99d64-47fa-4b70-90cc-138c6ec1204d
| 7cda211a-9d62-509d-ad7f-55e0b53d7349 | section | Project Details:
| 255ed54c-6adc-507a-9476-314ab61e0c48 | checkpoint | Project Details
| 14e94dc7-a342-40de-a059-6f6c7889cb7e | textbox | Store:
| 2f5af8ab-f40f-41f2-a022-d102d5a01178 | textbox | Ref Number:
| f72e416e-f79f-461e-b227-23acdfacf00f | textbox | Address:
| 9a5cb7dd-10db-432b-bdce-2ae1872a0b4f | textbox | Location of Defect:
| da1c5b4b-7e84-49b2-b38b-68706f01e245 | textbox | Description of Works:
| c4912b48-d1bd-55ea-9145-e503fa0afefc | section | Bakery Dept
| 0cf3748e-c8f4-58bc-a9f2-2277869aa92b | checkpoint | Bakery Oven
| 75e4126a-7260-5fc9-8339-2a3b74626b1f | checkpoint | Prover Oven
| 596b8a49-66f0-5f5c-a0b4-3b0f80b60d59 | checkpoint | Foh Prep Area
| 30459883-ab80-5c4b-8e50-13232cd4d9c0 | checkpoint | Boh Prep Area
| 40c8fd80-6e33-5d7c-ac5e-ea415bfbf716 | checkpoint | Coolroom
| d7fc12a0-4a02-5235-bf17-dc7ac2a006de | checkpoint | Freezer Room
| 8323575c-4bed-5ecb-9319-6f7df847795b | section | Deli Dept.
| 8b49f0d4-3419-59c9-9557-78cb1b0b323c | checkpoint | Foh Seafood
| 26860227-1afa-56ef-bcd2-c06cefcfc500 | checkpoint | Foh Salad
| d3962a37-7de7-5258-87a1-b5fef1c3c178 | checkpoint | Foh Cheese
| 3fb2ac5b-6365-4839-bb44-f824837ea760 | checkpoint | Foh Salad
| 48e002c8-1404-576a-83e9-a90ce9852ea9 | checkpoint | Foh Meat
| 63b9e4b8-6d0d-476c-9599-e4585c4cb2fc | checkpoint | Boh Prep Area
| 1d179c4a-08ab-5c5d-8a38-9d28a7c5c08f | checkpoint | Chicken oven
| 70bf8b38-b656-497b-8e1d-c89e44ae701a | checkpoint | Coolroom
| dfbd799f-2b98-48a2-8dc4-4b890308d4d5 | checkpoint | Freezer Room
| 1b30b7f2-c1dd-57e3-87d7-dd263fae9ee6 | section | Meat Dept
| 277671cb-670e-4fb5-87b5-7ee90ced6e62 | checkpoint | Foh Prep Area
| 400622c5-efee-4f9b-b380-59b9dc07421a | checkpoint | Boh Prep Area
| 36b7324d-2095-4eb9-865a-4022c9b2df37 | checkpoint | Coolroom
| 66e4ad29-0991-450c-8dee-9c9b1d0fbe29 | checkpoint | Freezer Room
| 137bc12d-5512-5fc1-a5e9-77069ce711c5 | section | Produce Dept
| fc17f27a-3367-4437-8d80-d0203bd634ac | checkpoint | Boh Prep Area
| 2b42feae-ee6e-462e-a7ed-053f104a4212 | checkpoint | Coolroom
| 0db33588-3256-49c5-acb2-301ae6f9d12f | checkpoint | Freezer Room
| e8f750c7-489a-5228-bd29-9e5a21fde64f | checkpoint | BOH Walkways
| 271c15c2-dc31-596f-a1fa-37dd7f43bf36 | checkpoint | Dairy Cool Room
| 7420e069-1483-43a2-a6c9-097b0146dd86 | checkpoint | Freezer Room
| 44dc0a31-42b6-51ec-bd8f-58417e92a7e8 | checkpoint | Loading Dock Area
| e00b44bc-0a08-5f13-acf3-7a9d6290c900 | checklist | Add Product Checklist |  | Product Checklist |  | 3db0dabd-fc00-45d3-8e55-1383d5957749
| dd83a12b-5a86-556f-acc7-1dce3104441b | checkpoint | Product information
| bfa0af79-951d-56a9-a844-cac81a23b1ce | checkpoint | Area of application
| 3c37081f-eeda-5e23-a070-4c52929723ea | checkpoint | Batch No. input or photographed
| f0022c6f-4642-58b2-94fe-524690bd235b | checklist | Add QA Checklist |  | QA Checks |  | 27455fa0-cd02-4e8c-a1d2-e9085276a2cb
| ab49d568-9d75-5ce0-87f5-7b29ce4b0ba5 | checkpoint | Moisture Test
| ee9dc83b-144a-596a-9418-efc47324c835 | checkpoint | Preparation
| 8be43f28-65fc-5f71-b269-0cae1f7c506d | checkpoint | First coat
| a9608c76-33d4-59bd-81a6-57ba10e298b1 | checkpoint | Second coat with non-slip
| bc709695-4039-5407-8ee6-0dcd5122a53b | checkpoint | Line-marking
| f0ffd1e2-3dab-50f3-be12-aeb1ec69baa9 | checkpoint | Final inspection
| ce517b1b-c382-516a-814b-affe2459b380 | checklist | Add Site Details |  | Site Details |  | fc270f82-618d-43df-bba6-1a520462c35b
| 8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
| 8447c4d0-eaa5-42ec-aeed-e8d1395bdbcd | textbox | Job #:
| c10b816d-086f-4c88-b3c9-2332c5383283 | textbox | Project:
| 2434bc2b-43b3-4827-bc40-eb2f18ebc48f | textbox | Address:
| 8265a9b0-9c33-496b-a9c0-aab327f1e9f3 | textbox | Client:
| 6a558a92-9dab-4f30-8d10-0c099f99aca1 | textbox | Site Supervisor:
| c55f0edb-6bb2-4eec-8bbc-de2b85372099 | textbox | Mobile:
| f9ea5144-a86e-48d2-a3e7-27c0518eb95c | textbox | On-Site Contact:
| f2537a84-c189-4c62-b74f-94edf32d2bd5 | textbox | Mobile:
| bc55937c-70b9-4ded-9dd4-a59b411ccf94 | textbox | Office Phone:
| acab750a-1bcd-46a0-98fb-c5a11866a116 | textbox | Email:
| 480ec3ad-aa8d-477f-b5e1-d963314f64b8 | textbox | Aconex Contact:
| 64f5704c-60fe-4d01-8b22-5ab6d79c630d | textbox | Email:
| 4d1d7e2f-af8d-57cb-becf-39b15c245741 | checklist | Add Voltex Checklist |  | Voltex |  | 27eb7b54-59c8-46ae-95f1-520d6808fa58
| be127d0b-b6e8-5ebf-bc20-25b262c79826 | checkpoint | Area clear and acceptable
| a6b1d106-f043-50eb-a961-fc86b6c59370 | checkpoint | Substrate preparation
| 257422e7-f3bf-5a9c-b461-11ff9b78dd41 | checkpoint | Voltex laps to spec
| ab6738ef-1112-5125-a5c4-c46abdeada52 | checkpoint | Granules have been applied
| 78bb654f-e78c-57d9-9d9d-6ddb427ae7c7 | checkpoint | Bentoseal has been applied
| ce69bc80-0fa2-5049-a51e-03f87ff08ef7 | checkpoint | Water stops: Aqua swell or Rx 101. Or Rx102.
| 27c2e70d-f2e7-54b4-ae30-0a3af25eb8ae | checkpoint | Pressure strips applied
| fe1e6c17-e976-5885-b99e-88f26307c9d2 | checkpoint | Area defect free and signed off by Danlaid
| 4cb325ab-2b09-5611-8b61-b4cf8ac0d4b5 | checklist | ISD Building Checklist |  | ISD Building Checklist |  | 5e286c2f-7436-45ea-976a-8d9ce16e05b6
| 31004f57-e9d5-5561-9834-e2079dd9be0a | checkpoint | Mechanically grind floor
| ac11cdc3-d8c2-57aa-bb5a-bfadd762e8f5 | checkpoint | Application of Deckshield ED primer
| 0aa20fe3-e191-5e33-b699-8cd77eb5e5df | checkpoint | Application of Flowcoat SK (Black)
| bd961b95-622a-5dfb-b9bd-337ac364654b | checkpoint | Application of Flowseal UV (Satin Black)
|  | checklist | New Danlaid Generic Project Template |  | Danlaid Project Template |  | e579536c-cfeb-4ea5-87cf-c4a8f31b82c7
|  | checklist-flat | Site Details
|  | checklist-flat | SWMS
|  | checklist-flat | OH&S
|  | checklist-flat | MSDS
|  | folder-progress | Variations
|  | checklist-flat | Site Deliveries
|  | checklist-flat | Monday Daily Works Diary
|  | checklist-flat | Tuesday Daily Works Diary
|  | checklist-flat | Wednesday Daily Works Diary
|  | checklist-flat | Thursday Daily Works Diary
|  | checklist-flat | Friday Daily Works Diary
|  | checklist-flat | Saturday Daily Works Diary
|  | checklist-flat | Sunday Daily Works Diary
|  | checklist | PA12 |  | PA 12 Areas - Maintenance Bays |  | ec12c2b3-cc30-4458-bb22-6e3f397e116b
folder-normal is not dependant but can't have own status |  | folder-normal | Test for moisture - RH to be less than 75 RH
folder-normal is not dependant but can't have own status |  | folder-normal | Prepare substrate - Diamond Grinding
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: Mixing station method. Sufficient available product. Correct tools available. Sufficient man power. Adequate unimpeded floor access. Free from other trades. Check other trades have not entered.
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: product mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Apply primer as required as in accordance with flowcrete specification as 1 x coat universal epoxy (RH<75). 2 coats Deckshield ED (RH>75)
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of priming. Regular use of wet film thickness gauge to meet requires thickness levels
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave floor as new
folder-normal is not dependant but can't have own status |  | folder-normal | Seal joints if required, as follows formed joints 25mm deep, with filler and bond-breaker
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete
|  | checklist | PA13 |  | PA 13 Areas - Hangars/Depot Buildings |  | 27ff0ff1-592f-4e7b-961b-d9b748356edd
folder-normal is not dependant but can't have own status |  | folder-normal | Test for moisture - RH to be less than 75 RH
folder-normal is not dependant but can't have own status |  | folder-normal | Prepare substrate - Diamond Grinding
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: Mixing station method. Sufficient available product. Correct tools available. Sufficient man power. Adequate unimpeded floor access. Free from other trades. Check other trades have not entered.
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: product mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Apply primer as required as in accordance with flowcrete specification as 1 x coat universal epoxy (RH<75). 2 coats Deckshield ED (RH>75)
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of priming. Regular use of wet film thickness gauge to meet requires thickness levels
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave floor as new
folder-normal is not dependant but can't have own status |  | folder-normal | Seal joints if required, as follows formed joints 25mm deep, with filler and bond-breaker
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete
|  | checklist | PA14 |  | PA 14 Areas - Simulator Bays ISD |  | dd2e7eba-3308-4a3e-8fce-0cd6a2c215c0
folder-normal is not dependant but can't have own status |  | folder-normal | Test for moisture - RH to be less than 75 RH
folder-normal is not dependant but can't have own status |  | folder-normal | Prepare substrate - Diamond Grinding
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - contractor and subcontractor to agree on the day's scope of works in advance: mixing station method sufficient available product. Correct Tools available. Sufficient man power. Adequate unimpeded floor access free from other trade. Check other trades have not entered.
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: product mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Priming: apply primer as required as in accordance with flowcrete specification as 1 x coat universal expoxy (RH<75) 2 x coats Deckshield ED (RH > 75)
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of priming. Regular use of wet film thickness gauge to meet required thickness levels.
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave flooring as new
folder-normal is not dependant but can't have own status |  | folder-normal | Seal joints if required, as follows formed joints 25mm deep with filler and bond breaker
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete
|  | checklist | PA23 |  | PA 23 Areas - Vinyl Flake Epoxy Flooring - Foyer |  | dc7a2ed8-eb82-4b79-9d6a-0ec8e9872291
folder-normal is not dependant but can't have own status |  | folder-normal | Test for moisture - RH to be less than 75 RH
folder-normal is not dependant but can't have own status |  | folder-normal | Prepare substrate - Diamond Grinding
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: Mixing station method. Sufficient available product. Correct tools available. Sufficient man power. Adequate unimpeded floor access. Free from other trades. Check other trades have not entered.
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: product mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Apply primer as required as in accordance with flowcrete specification as 1 x coat universal epoxy (RH<75). 2 coats Deckshield ED (RH>75)
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of priming. Regular use of wet film thickness gauge to meet requires thickness levels
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave floor as new
folder-normal is not dependant but can't have own status |  | folder-normal | Seal joints if required, as follows formed joints 25mm deep, with filler and bond-breaker
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete
|  | checklist | PLANT ROOM |  | Plant Rooms - Waterproofing Sikalastic 488 PU |  | b6a75f88-be78-46a1-bc35-22ef78985139
folder-normal is not dependant but can't have own status |  | folder-normal | Surface preparation. Surface prepared for adhesion. To achieve concrete surface suitable for sika 161 Primer
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: Mixing station method. Sufficient available product. Correct tools available. Sufficient man power. Adequate unimpeded floor access. Free from other trades. Check other trades have not entered the prepared area - post preparation
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: sika 161 product data sheet mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Priming: apply sika 161 primer as required as per sika method statement and as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of priming
folder-normal is not dependant but can't have own status |  | folder-normal | After priming: apply base coat of sikalastic 488 @ 0.6kg/m2. Intermediate coat of sikalastic 488 @ 0.3kg/m2. Broadcast sand. Top coat with sikalastic 488 @ 0.3kg/m2
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave floor as new
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete
|  | checklist | WINDOW SILLS |  | Window Sills - Waterproofing Sikalastic 400N |  | 60a29875-545a-4955-a450-2c43755820ea
folder-normal is not dependant but can't have own status |  | folder-normal | Surface preparation. Surface prepared for adhesion. To achieve concrete surface suitable for sika 400N
folder-normal is not dependant but can't have own status |  | folder-normal | Day's scope - subcontractor and contractor to agree on the day's scope of works in advance: Mixing station method. Sufficient available product. Correct tools available. Sufficient man power. Adequate unimpeded floor access. Free from other trades. Check other trades have not entered the prepared area - post preparation
folder-normal is not dependant but can't have own status |  | folder-normal | Mixing: product mixed as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Priming: apply sika 400N base coat required as per sika method statement and as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Priming: apply sika 400N base coat required as per sika method statement and as per product data sheet
folder-normal is not dependant but can't have own status |  | folder-normal | Application: applied product within 5 days of base coat
folder-normal is not dependant but can't have own status |  | folder-normal | After priming: apply base coat of sika 400N @ 0.5kg/m2
folder-normal is not dependant but can't have own status |  | folder-normal | Cleaning and final inspections. Visual inspections of completed works. Cleaning if required to leave floor as new
folder-normal is not dependant but can't have own status |  | folder-normal | Final Inspection Completed (confirming no damage/defects) The subcontractor must undertake a defects inspection and complete making good of such defects prior to offering the works as practically complete