## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 01 - Waterproof Ensuite Base | [5 empty] | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 01 - Waterproof Ensuite Base
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply TREMCO Primer - take a photograph of the primer container with technical details and a photo/video of the application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - TEMCO Primer Applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | TREMCO Primer curing times
note | Full Cure time: 2-3hrs
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
note | Test/ Inspection - Test
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
note | Inspection: Site Manager - DC (W)
note | Records & Comments - Pass or Fail
textbox | Observed setting time:
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 02 - Ensuite Walls | [5 empty] | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 02 - Ensuite Walls
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply Flowcoat Resin Primer - take a photograph of the primer container with technical details and a photo/video of the application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flowcoat Resin Primer Applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Flowcoat Resin Primer curing times
note | Full Cure time: 24 hrs at 20°
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 03 - Epoxy Screed to Falls (Entire Ensuite) | [5 empty] | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 03 - Epoxy Screed to Falls (Entire Ensuite)
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply Flowcrete Resin Primer - take a photograph of the primer container with technical details and a photo/video of the application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flowcrete Resin Primer Applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply Epoxy layers in line with data sheet and the figures in AS3740 - take photograph of epoxy container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the epoxy and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Flowcrete Resin Primer curing times
note | Full Cure time: 24 hrs at 20°
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 04 - Epoxy Cove to Ensuites | [5 empty] | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 04 - Epoxy Cove to Ensuites
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply Flowcrete Resin Primer (with sand) - take a photograph of the primer container with technical details and a photo/video of the application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flowcrete Resin Primer (with stand) Applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply Epoxy layers in line with data sheet and the figures in AS3740 - take photograph of epoxy container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the epoxy and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Flowcrete Resin Primer (with stand) curing times
note | Full Cure time: 24 hrs at 20°
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.
checklist | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 05 - Vinyl Flake to Ensuite Floors | [5 empty] | *Standard ITP - Aus Standards - Wet Area Waterproofing WP-05 - 05 - Vinyl Flake to Ensuite Floors
section | 2 - Construction Inspections
checkpoint | Inspection Details
textbox | Level:
textbox | Zone:
checkpoint | 2.1 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Moisture content in the concrete must be lower than 4.5% as measured using a Tramex CME Moisture Meter
textbox | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area, every 20m2
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.2 - Drainage installation - puddle flange installation
note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - HS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Substrate condition Inspection
note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
note | Test/ Inspection - Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate falls - measurement - note actual fall on checklist, take photos
note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.5 - HOLD POINT: Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Measured fall:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
note | Test/ Inspection - Measurement
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
checkpoint | 2.7 - Subcontractor Pre-placement Check: Confirm temperature is acceptable for membrane installation
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Everything ready to install
note | Test/ Inspection - Review & Verify
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (S)
textbox | Records & Comments - Temperature Reading:
checkpoint | 2.8 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
note | Test/ Inspection - Visual Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
note | Records & Comments - Do not apply sealant to a substate surface is below 10C or the surface temperature is above 40C.
textbox | Applicator Names:
textbox | Temperature at placement:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Apply Flowcoat OP Suck Coat Primer Primer - take a photograph of the primer container with technical details and a photo/video of the application
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Flowcoat OP Suck Coat Primer Applied
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.10 - Apply membrane layers in line with data sheet and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with data sheet requirements, timing between layers in line with the data sheet
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (I)
note | Inspection: John Holland - PE (W)
checkpoint | 2.11 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
note | Flowcoat OP Suck Coat Primer curing times
note | Full Cure time: 24 hrs at 20°
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (H)
note | Inspection: John Holland - PE (H)
note | Records & Comments - Pass or Fail. Record film thickness and vertical termination heights.
textbox | Layer 1 time:
textbox | Layer 2 time:
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.13 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure protection has been applied to Vinyl Flake.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
note | Test/ Inspection - Installation and Inspection
note | Test/Inspection Frequency - Each wet area
note | Inspection: Subcontractor - WS (W)
note | Inspection: John Holland - PE (I)
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
note | Specification Reference - GBA-SPE-AR-AS-0001
note | Acceptance Criteria - All prior items of this ITP have been complied with.
note | Test/Inspection Frequency - Each Lot
note | Inspection: John Holland - QR (R)
note | Records & Comments - Check all measurements are recorded and photos attached.
note | All records loaded into the Work Lot System and Verified.