## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d4c27083-312b-4209-bf70-e69a86d7dff5 | checklist | Checkers Checklist - Abutment Base -Type B-12M |  | Checkers Checklist - Abutment Base -Type B-12M
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
54468d46-366d-41c3-bd69-9d2cd33b03ad | checkpoint | Site Safety / Workers Safety
9a34992b-56de-410a-ab84-1a30ddb64f8d | checkpoint | Availability of updated shop drawing
c4a0dc3b-5883-410d-bb11-62c1ee646312 | checkpoint | Double Check the Ferrule placement -Type BB
608cf51b-49d7-4c4b-8b06-0864875c4468 | checkpoint | Overall Measurements of construction Element
35e16c61-503f-47ff-bc8c-464fe41dbc7f | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm)
88cfa12a-0355-45b0-b95f-a4ca734b5ee8 | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
b6b8e2a9-f7e2-4105-b50b-fd75af97f16d | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
5e9b082b-9deb-425d-b57a-ba6d1c8f8e9b | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
58173099-c801-4ae2-90f0-95a9850b5025 | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
43294c7f-e059-4c1a-8f29-f46745dd145c | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
d30fc2e8-e84c-4cf6-abb8-fd92ea2b2a71 | checkpoint | Concrete cover check minimum 30mm
61f1e5c2-4400-439f-a34e-f95498194d10 | checkpoint | Panel length check, alignment check -4400x800mm
842c05bf-eccd-4d2a-bd4e-eaac8059ba0e | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
f550c924-1dab-49ab-855a-f69d75efc507 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
324e8a8c-5a31-4a09-8b21-1e76165e42c6 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
7abd2f8d-8386-45d1-8eaf-5a81e562c312 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
729ece2d-ee64-4d7e-b078-e6ce3769ec1e | checkpoint | Curing Procedure arranged
cc5d0aec-cb9f-4d57-8e5d-169b5c8fef87 | checkpoint | Photo Taken
030af2a0-b63d-4211-af19-e2d7bd88dcfa | checklist | Checkers Checklist - Type B- Bridge Plank |  | Checkers Checklist - Type B- Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c8cdb1f8-b0fe-4eea-8d32-e8b9ad053142 | checkpoint | Site Safety / Workers Safety
56323356-4589-4c89-b6b3-b45f8f3d4f64 | checkpoint | Availability of updated shop drawing
70a4415a-48f5-41d2-8b11-24afa5b1a1f0 | checkpoint | Double Check the Ferrule placement -Type A (600+1450)
3ad162dd-c6a5-54c4-8e41-aa5fe96873b4 | dropdown |  | 600F1450F, 550F1450F
90290a8a-4562-4bc4-8083-083ce9f84fb9 | checkpoint | Overall Measurements of construction Element
95c8ded7-74ac-458f-a033-908b75de827c | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm)
7fe9ecba-00bd-481c-a1d4-d2e875670b1d | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
9df92e1a-1578-422b-acc6-247498038637 | checkpoint | Concrete cover check minimum 30mm
e9df32cc-5bf8-4147-95de-bdb9e26414f2 | checkpoint | Panel Thickness check,alignment check (150mm)
7429bc2f-000c-5dfc-bba0-6e184bcd8b29 | dropdown |  | 150mm, 200mm
05af30c5-f49e-494a-8404-56d73b0e5a87 | checkpoint | Panel length check, alignment check (4500mm)
2bd3d9ad-e48d-5789-8686-4915c3bda1f5 | dropdown |  | 5000mm, 4500mm
97930e67-bf5a-4b95-85e8-d26ec9d3510c | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
031cda75-2260-4053-912b-499c05b567f7 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
5da31b0f-115b-4057-b02b-9ed70c649e0e | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
8a83c279-a538-465a-b049-56f14b70c659 | checkpoint | Curing Procedure arranged
6cf0de48-026d-4a28-a1cb-84bec7981942 | checkpoint | Photo Taken
b58598ad-21d4-4a1e-98f5-d3c3b10d892b | checklist | Checkers Checklist - Type B-12M- Bridge Plank |  | Checkers Checklist - Type B-12M- Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9ef00271-a2a7-4ac9-81c0-cde2fb97349d | checkpoint | Site Safety / Workers Safety
f3d35ead-b270-4829-95b2-0ed1e97b3dc3 | checkpoint | Availability of updated shop drawing
98e8f628-bc08-4e77-8802-8a35285d9bcc | checkpoint | Double Check the Ferrule placment -Type BB
a0a20cc8-43ce-4713-abe5-657b479cdf82 | checkpoint | Overall Measurements of construction Eliment
1e9d7935-efd9-4fc9-8433-947b4f34a9f7 | checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
7e9b7c25-7e08-4059-bd7b-c2273b6a19c0 | checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
faf23493-4f26-4547-844f-41f4531012ba | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
f1e72625-695f-4f10-9e70-04b98e4e099b | checkpoint | Concrete cover check minimum 30mm
06f5024d-f9ec-43f9-aadf-028386555c0c | checkpoint | Panel Thickness check,allignment check -150mm
da6f3a21-bc0b-46a0-82ef-232d6c583069 | checkpoint | Panel length check, allignment check -4500mm
44023201-5b81-4088-9bcc-c8b6af8ce8c0 | checkpoint | Diaganal length check, allignment check
0ff719eb-ecde-4b05-b4cf-c67401eb6605 | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
c56d978c-7e32-4c74-8915-da695d8e3f25 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
9e0c67c7-425b-4238-99af-e7afe427364e | checkpoint | Reinforcement (Reo) placed, cleaned, tightned
c03639b9-5943-4185-9f63-e7b9f8eea4a6 | checkpoint | Curing Procedure arranged
261a7386-61b8-445c-9161-29e40ae8c4ba | checkpoint | Photo Taken
066386e9-098d-424a-8532-897bbd7d9461 | checklist | Checkers Checklist - Upper Wall -Type B-12M |  | Checkers Checklist - Upper Wall -Type B-12M
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4d6049f4-d707-452b-bcc6-c61b5c9f2dbd | checkpoint | Site Safety / Workers Safety
1b70c412-ae6e-4871-9aaf-e776dfa56532 | checkpoint | Availability of updated shop drawing
cc9ee048-6a4a-4f7f-8102-a7a5d2e8fb38 | checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
35e88c7d-7148-54b0-8ac4-526d47c0f66e | dropdown |  | Other
71f01736-3e18-5138-a6d6-6ecb8129b968 | dropdown |  | 684mm
abc94e91-71f4-4f2f-a823-9a5fbaccb6e4 | checkpoint | Overall Measurements of construction Element
65d64908-b8de-4ef9-82cb-5029f84c29b7 | checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation
c1d240e1-8e44-4470-94f4-da6384123488 | checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
043c4688-2598-4ac8-860e-505df98ad939 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
81e4d1ae-4421-4f40-b813-1a62ca95d1cf | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
2cdd02a2-6a4f-48c5-8f7c-6e54fe042f61 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
c9db98dc-8e8e-474e-822d-3dc0470bad22 | checkpoint | Concrete cover check minimum 30mm
ea491907-0b26-4e66-9c6e-67b1fe81f6cd | checkpoint | Panel Thickness check,allignment check -200mm
5e125479-5fcb-460d-a4af-9616c81410a7 | checkpoint | Panel length check, alignment check -5000x800mm
7a1b12a2-3dda-4ff6-abac-243cceb8ed50 | checkpoint | Diagonal length check, alignment check (5034 mm or close to this)
5c408683-ef40-425c-8ab1-2e4ae9755239 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
d055331b-4c0d-4573-ae66-ccc7e259de81 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
68a19c2f-274c-4bf1-b603-cab7cd75261a | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
6fac7936-2195-4d73-9f71-1eb278125777 | checkpoint | Curing Procedure arranged
184fcfbc-771b-444b-add1-475118cb5584 | checkpoint | Photo Taken
da241d22-08fb-4d81-99e4-f3dfc6a7c9c7 | checklist | Installers Checklist - Abutment Base - Type B-12M |  | Installers Checklist - Abutment Base - Type B-12M
18b9672b-ab99-4425-ba03-c13e9ef6a755 | section | Job Approval Documents/Construction Documents
eef26868-0a86-4677-b2f8-61ab46418a43 | checkpoint | Availability of updated shop drawing
969adab4-dda1-4331-b4ae-65bfb3ac1e85 | checkpoint | Complete Material "Bucket List"
8ee869bf-c1b2-4ea7-a810-52007a443ae7 | checkpoint | ID Plate
1f436a16-d0fd-5983-8073-006ebf840cea | textbox
5398de78-e036-48c3-9960-3e7d70d5207b | section | Pre-Pour Check Approvals
b01a93b5-69f0-4f92-aea2-a1463039153b | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
c8dd7629-5975-40c6-9d31-08f68cdb3727 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
9a9bc5d5-d590-43fb-8d8c-fec08b1dc69d | checkpoint | Temporary Fix ID Plate to Formwork
b23c2f4c-e687-4ef6-bfda-cd5591c7eac3 | checkpoint | Double Check the Ferrule placement -Type BB
5a2738f6-a679-4ca2-b2ec-2c772e029f7c | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
bfdec6a2-8e77-4711-9c88-7ca6eeb0c6dc | checkpoint | Embeded Items - Fixed Firm & aligned -Check
615eb833-4e9c-5ae8-8a57-c858ece0ae6e | tickbox | Ferrules - Position,Size,Orientation -M24 (96mm)
4736bbc7-0818-5a73-bfd5-4c968433593b | tickbox | Ferrules for Dowels - Position, Size -M24 (96mm)
ee0d3e0f-002e-59dd-8234-6c8a72cc9dcd | tickbox | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
506e60dc-626f-463d-ba58-1eb3d1e01eae | checkpoint | Concrete cover Check - minimum 30mm
f07eca85-94ba-4f16-9c9e-9244136b8528 | section | Quality Assurance
28571fea-2451-48e0-87f1-5e3df4f12412 | checkpoint | QA - Final Check of ALL measurements
3115d37e-a87b-418d-85d6-87aad151ab08 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
ea821f08-33df-4c05-b944-ab1d050e3343 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
cb76dda4-05a8-4eb6-839f-706a89c0a96e | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
24e96074-d8b9-5ab7-9888-5128b4d0bfda | date | Pour Date
182c100f-0adf-47a6-afa1-97f247db9e33 | checkpoint | CONCRETE TEST Procedure
be72619d-02bd-4d0a-9b6a-0dbce5fa3455 | checkpoint | APPROVAL FROM ENGINEER
fa4dca23-ce97-41c8-9da9-07bd7d2cbb1f | section | Other Arrangements
bd97e758-06fa-4b02-80d3-19f05cf73133 | checkpoint | Concrete surface Finish Requirement arranged
9ff398a6-8662-5a31-ab26-9a5194ee41c1 | dropdown | Finish: | Fine finish, Broom finish
9d8f107d-b22e-40a4-9c89-cb4a172f9dd5 | checkpoint | Curing Procedure arranged
fce73cb5-a6e1-4095-a6ed-ff6b43d814b3 | checklist | Installers Checklist - Type A - Bridge Plank |  | Installers Checklist - Type A - Bridge Plank
1bb6e8f2-4b8e-482e-8f64-51cecc540565 | section | Job Approval Documents/Construction Documents
188925bd-b050-4ce2-93cb-fa46fdd22905 | checkpoint | Complete Material "Bucket List"
7a5d3fa3-4fe3-4f21-99d9-175f5998774d | checkpoint | Eye Anchor - 2.5T
cde6dbaf-036a-5ff7-b1ba-39f93b69b639 | textbox
352e3cc8-bc12-4a5f-a73f-9798911de1f0 | checkpoint | Ferrules - M20 x 96mm
cf37eee7-90a3-5bde-93f7-0b1a9bed8590 | textbox
14bf7870-8cad-47a0-a930-c3439f88cea4 | checkpoint | ID Plate
789968c6-aaa5-5423-99bc-6a389b87ceb7 | textbox
12535983-b292-4f15-9cc1-277a43df46f8 | section | Pre-Pour Check Approvals
9923e0df-8f4c-473d-b3a8-2b472321790d | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
f04629c4-eec9-4b7c-a9eb-da2a69f9d2bc | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
cb2a1cd8-7b5e-4a9e-8b92-050a3d6a8cd0 | checkpoint | Temporary Fix ID Plate to Formwork
79690ace-0293-4fd7-8bdf-26cf6045fa78 | checkpoint | Double Check the Ferrule placement -Type A
ea8a050e-88e4-49df-bc9f-cc6b3b5ec271 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
115d88f1-8302-44e6-b033-a5703015a098 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
e09c43a1-c5ea-4fcb-909f-31cf2b28febe | checkpoint | Concrete cover Check - minimum 30mm
71f9e967-4ccb-4424-87a7-608a0203fcd4 | section | Quality Assurance
30ab27bb-8301-4a3c-acc8-e245db460bb9 | checkpoint | QA - Final Check of ALL measurements
63796298-2841-4f7e-8917-697c35c10575 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
6607c965-574e-48c5-982f-22161151a303 | checkpoint | QA - Concrete mix design ,variations%, adjustments%,mix time
36ca3359-1273-4e32-b7fd-c23715e2cbfe | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
d91e17d5-f907-5565-9339-d160eb73cea4 | date | Pour Date
ab16a28f-3b02-4b6f-a998-dfb41e9af4cc | checkpoint | CONCRETE TEST Procedure
80e348cb-e853-4bd6-8b21-4f8e5598f2b5 | checkpoint | APPROVAL FROM ENGINEER
758a0d0c-5b50-4b3e-8aa1-98f8b3a8a6b6 | section | Other Arrangements
19d67d71-73ec-4d60-a956-e15533ac953e | checkpoint | Concrete surface Finish Requirement arranged
4c32305f-b223-58cf-8491-6adae17977ca | dropdown |  | Fine finish, Broom finish
a938a6c2-d5c2-49e5-996e-7282f744c8be | checkpoint | Curing Procedure arranged
e313a87b-8367-488e-b7e1-274703965393 | checklist | Installers Checklist - Type B-12M- Bridge Plank |  | Installers Checklist - Type B-12M- Bridge Plank
d8965f53-5690-434f-b371-51a750afe002 | section | Job Aproval Documents/Constrction Documents
99811267-5368-458a-8c3f-14466e2cddbe | checkpoint | Availability of updated shop drawing
d0d8d700-e358-409d-9f01-21a964dedfba | checkpoint | Complete Material "Bucket List"
2c509c02-4dd2-458d-a100-8565ac6c6841 | checkpoint | Eye Anchor - 2.5T - 04
2d0b37b6-da5a-4c68-85c8-bf46994b4f4f | checkpoint | Ferrules - M20 x 96mm - 10
76fdac2d-a887-4ad9-802d-95a88e89112a | checkpoint | ID Plate
285edd32-2c9d-5335-adae-1b9b768ad9c9 | textbox
757c03d5-34f4-402c-a62e-1d3fc5a2a82f | section | Pre-Pour Check Approvals
0251d230-9fda-4824-b088-4dd1ca55b5d6 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
03947496-2300-45ea-9ac1-53ba97941d22 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bb21bff1-f615-448e-bec4-7b0d9e984718 | checkpoint | Temporary Fix ID Plate to Formwork
d398735f-dda8-4dbf-95f8-da41f53b8442 | checkpoint | Double Check the Ferrule placment -Type BB
787fe559-9169-4616-89bd-a41fcb7f7202 | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
56a6facf-0fbb-49e0-a0ba-813fcf6196ff | checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check
b1c81b49-4250-586b-bff9-f3178e0b431e | tickbox | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
1cc45314-6de6-5836-ad8f-eb31c18e5bd8 | tickbox | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
a13d17cb-51f6-4967-ae25-9518b29b1425 | checkpoint | Concrete cover Check - minimum 30mm
9c9716bd-9760-4787-8123-b6a05713ae0f | section | Quality Assuarance
1d16f512-fd05-4b07-a1df-fceee20fb730 | checkpoint | QA - Final Check of ALL measurerments
4f08277e-ec79-4f00-ad2f-0c63505419cc | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
e5c44b2c-cd51-4542-a869-40d564f24d20 | checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
60b63d7f-77fa-49f6-9446-87d87f926e33 | checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
a8024c7d-7d51-5a48-90ae-e17200f6300d | date | Pour Date
751a6c18-a024-4f70-8904-cf7a72588563 | checkpoint | CONCRETE TEST Procedure
f976cf0f-0ca0-4213-9e5c-1220694878b9 | checkpoint | APPROVAL FROM ENGINEER
d4c10407-b339-4fde-9cdb-45e751db113e | section | Other Arangments
a10c64df-b2cb-4732-9976-5ab4a738e176 | checkpoint | Concrete surface Finish Requirment arranged
41fd5a7a-de26-57c4-b9a9-c9230f7656cb | dropdown | Finish: | Fine finish, Broom finish
3fadde2a-2c16-417b-8790-c18c83df3fe0 | checkpoint | Curing Procedure arranged
0e85757a-0656-49ec-817c-58d5c4e18854 | checklist | Installers Checklist - Upper Wall l -Type B-12M |  | Installers Checklist - Upper Wall l -Type B-12M
74e8b93c-2bcf-4705-bf8f-1fe952488abd | section | Job Approval Documents/Construction Documents
debc6c79-bd31-479c-b8a4-332bdd4af050 | checkpoint | Availability of updated shop drawing
4a073f26-bee7-4a77-8f1f-db1bddad666f | checkpoint | Complete Material "Bucket List"
52dc1c9f-f129-4854-add0-7c90125fe324 | checkpoint | Eye Anchor - 2.5T(170mm) - 04
f93c42f8-4d5e-4ab8-9f84-a89442d003b9 | checkpoint | ID Plate
f7c4bb31-8810-5ce4-b3fc-8f6d400db73b | textbox
26bc110a-3641-4655-bc1b-978ff0f8c9f5 | section | Pre-Pour Check Approvals
b0f69b2a-04dd-4543-94f9-9b761acc650e | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
f6b26909-d50e-46d6-b229-f7de5c4cde1d | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
9b8c9c6b-7b41-42ac-9c43-bea98e2cc60f | checkpoint | Temporary Fix ID Plate to Formwork
1a9486d4-5202-41a8-88d3-90c4c2b69f8d | checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
bb2bf441-56b7-583a-a4ea-9cc0febd11fb | dropdown |  | Other
717a8ef7-7de9-5d3e-9147-6bd04502a0e1 | dropdown |  | 684mm
8d01b4c4-95e7-4225-9e09-895c2f36ca30 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
81f93fc3-9e89-4493-97de-dee716405373 | checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check
48484faa-1806-5728-a599-1dd0cc5b3f31 | tickbox | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
3288a8ae-39b7-507e-ad65-0e6646f5172c | tickbox | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
1f98c569-e012-58a9-b57c-66b5541e1b26 | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
24d6f7d6-5bca-5804-83ba-539e9c7c2a8f | tickbox | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
f5d7f77b-7f56-4774-b72c-abb7d87871df | checkpoint | Concrete cover Check - minimum 30mm
95f3b138-5966-4e96-91a5-188f2d9cf079 | section | Quality Assurance
4b5fc13c-82c5-436a-8ab4-df8da87463b0 | checkpoint | QA - Final Check of ALL measurements
4a954ff5-44a9-43f1-9ab2-2ef5da5dd2c8 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
d288c352-9719-4ec0-8579-40afce6ae5d1 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
514e07fe-a838-4b29-b8c5-bc487c9b07d9 | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
5852147e-7b32-5208-ae40-b414c3686645 | date | Pour Date
fb840062-3d7e-4aec-9129-116e5688f796 | checkpoint | CONCRETE TEST Procedure
7df0fda0-4820-49f6-a3db-463f300311ae | checkpoint | APPROVAL FROM ENGINEER
ef54b165-af8a-4a7e-a93a-5acfbfbdc6d5 | section | Other Arrangements
d1f4b4d0-84b2-448f-8ce1-32e7c9b45645 | checkpoint | Concrete surface Finish Requirement arranged
6ddb4ad4-2091-5138-baf8-5f406f82ca75 | dropdown | Finish: | Fine finish, Broom finish
d87a24a0-5254-4f9e-b8fa-ba0b70417088 | checkpoint | Curing Procedure arranged
8aaed07e-41e5-47e6-8428-cb2c4f9651b3 | checklist | Precast Components ITP |  | Precast Components ITP
649eac7a-24a1-484f-ab50-2488c5886339 | section | Documentations
0d6793bc-979e-4495-aed1-7009f5567ff2 | checkpoint | Special Instructions
700122c6-bd2e-4a57-89e3-ea6a36265a39 | checkpoint | approved Shop Drawings
5783a3ed-ca37-5ca3-99cb-f0bdb004ca99 | tickbox | 4.2m Wide Deck Panels (DP)
8606427c-7be6-50c7-8195-dcc2b888bf05 | tickbox | Abutment Base (UB)
c2a8de1a-d7b9-5087-abc9-cd426dfe22be | tickbox | Upper Wall (UW) 684mm
21e047e8-c28f-43bc-9544-a15311a0e425 | checkpoint | Other
231a8077-50bc-4970-a0e8-3b6a15000c4d | section | Job Approval Documents/Construction Documents
7ea9af7d-604a-43ef-a48e-5232e0961b9e | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
df4610a7-d3be-4a48-95e3-cba86be85095 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
b62fc6da-ee86-4c15-be3d-049a0d2e7b78 | section | Pre-Pour Check Approvals
29da24d5-2969-4863-8757-42254ce1d6c2 | checkpoint | Formwork
da9403aa-8765-4802-857e-42ce41ca92ba | checkpoint | Reinforcement(Reo)
4e39489e-e8a0-4c1d-8b32-5aad8998f74c | checkpoint | Embedded Items and their placement
6d64ad74-f629-4c94-aef3-721b7c278d42 | checkpoint | Lift Procedure
2c69c0b3-daa6-45ca-9d5f-3767830e6d02 | checkpoint | Concreting (mix design
7892ef4f-78df-4d74-ad47-14e82d68959c | section | Test on Concrete (requests and approvals)
1afdebd5-065e-428c-b8c9-d429f5b6f84c | checkpoint | Request From Client
c8b41490-f07d-4f81-98f8-c87fc6c13992 | checkpoint | Test schedule and Test Results
fc5ada55-72ce-456b-86d0-554a6eed509b | section | Transport 01
2c1e94f7-5b17-4e35-86d7-5eff91fe76bb | checkpoint | Any Lifting, Loading, Transport Instructions from Client
bbfe3a94-a555-4167-840f-2908bb7b2f7a | checkpoint | Transport Vehicle Approvals
1cb758a2-8535-4ba1-a807-745cd4cfd006 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
786b7ceb-958e-48ae-be02-1ba5bdfff70f | section | Transport 02
6b6c7d61-5cd7-42cc-8216-54271d2c5d87 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
66e16289-7d07-443e-8774-e0fb15b2188a | checkpoint | Transport Vehicle Approvals
159e1aae-be8b-4bfd-9cc2-aa848ba8b271 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
091ac9e4-999e-4be9-9958-46f917f386a9 | section | Transport 03
e234366d-a0cd-41b8-af82-ed2d70a58e5c | checkpoint | Any Lifting, Loading, Transport Instructions from Client
b728fbd0-565b-4870-b851-6b1b3bb9ca54 | checkpoint | Transport Vehicle Approvals
cbb3b02b-d396-40f4-8039-54da61f17a8e | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
37353da9-ad21-4709-a7da-45d6b732ff91 | section | Transport 04
f98eaf24-7aea-469c-9ecc-aaa851a7c6fd | checkpoint | Any Lifting, Loading, Transport Instructions from Client
a9008323-dc59-493a-ae1a-1aa3a2adfd22 | checkpoint | Transport Vehicle Approvals
3160da16-3522-4cd4-8445-8f3521cfc2a1 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
2eb65eed-ba45-4314-a74a-51a57e6eb8b4 | section | Other Documentations
7b263883-16c3-4726-b56b-7a5e323ab26b | checkpoint | Special Instructions
0a7cf9f2-d43f-41fc-8b13-8c7e6ef019cd | checkpoint | Other
4e700de5-7ae5-4297-93a9-d325e5a3476c | section | Installation
f685bbbf-7992-475d-b460-0b1865d124cf | checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
ab4a8389-e739-4a0d-a921-47cb4b5e70c1 | checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
719ecb2a-455f-5d99-bf31-9ecc98284056 | tickbox | Set out
14979a0a-c424-5bab-a62e-dc1b94cb0db1 | tickbox | Core Holes
9aa7aed0-7056-574b-98ed-442dc9d9ec4c | tickbox | Install dowels
2c111f04-cbcf-4846-a351-910d4d91e571 | checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
aa203702-cc22-46a3-bf11-ed2941d4a3de | checkpoint | Grouting and sealing
a6f48959-7d64-4567-96aa-98ba7934e3c8 | checkpoint | Remove back propping when instructed by consulting Engineers.
0f6c0316-15c1-41be-9332-2b95de0f26b9 | section | Final Inspection
d120fede-865f-47e0-a199-04ff71a57da4 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.