## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
52fc5ad3-80f5-4a71-9521-f031873906e5 | checklist | Checkers Checklist - Abutment Base -Type B-12M (2025-FF - STOCKS) |  | Checkers Checklist - Abutment Base -Type B-12M
a618a538-bd59-4797-9fce-67a2a5c005eb | section | Details
255e9fa7-0a4d-4751-bee3-6024926060b3 | checkpoint | Site Safety / Workers Safety
f8805d03-8013-4e58-9bd2-9466a53dc4b5 | checkpoint | Availability of updated shop drawing
515cbbc1-3fbd-43df-bdc4-3db7948d7853 | checkpoint | Double Check the Ferrule placement -Type BB
cb870674-277c-421a-ac0d-d4806972835d | checkpoint | Overall Measurements of construction Element
6d0a6c49-c39a-40a8-b4d8-9df694c83643 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm)
a14f8c4b-c98f-47ac-bad5-d156e433038f | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
e24b3726-319d-4828-8ba0-181bbcad72d6 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
1b7abbf3-1501-4b79-b419-f9421d96ffe9 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
18937814-1a24-4c79-865d-18df74932c96 | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
b5d672fa-a35e-4813-bb07-209de90e1b84 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
e051e298-a90f-4f81-9d4e-73759348be57 | checkpoint | Concrete cover check minimum 30mm
511130eb-911e-4825-88b0-a606439656f8 | checkpoint | Panel length check, alignment check
b9416ea0-6f3d-42e9-a322-4911d9db9149 | checkpoint | Diagonal length check, alignment check
0477f20a-ba70-47ce-8c02-1e87169ad9ea | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
59e6a35b-efd4-4b2a-834c-815d1ddf2125 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
6ee24348-cb17-4485-bfca-e0b7c5762219 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
f318b312-d5d9-42e0-9836-08e02964089e | checkpoint | Curing Procedure arranged
776d35f1-7d5d-4af0-b67b-f23a2cff26f6 | checkpoint | Photo Taken
1783230c-a974-4027-a628-b53d77f2e335 | checklist | Installers Checklist - Abutment Base - Type B-12M (2025-FF - STOCKS) |  | Installers Checklist - Abutment Base - Type B-12M
3c58051a-681e-4538-8f7d-6c30a3e87e69 | section | Job Approval Documents/Construction Documents
9e06fc8e-ba0f-4b2c-ad6c-3b396fb3800b | checkpoint | Availability of updated shop drawing
850a3efd-e1db-421a-a6ae-66e58a4fcfb7 | checkpoint | Complete Material "Bucket List"
48b9cd07-bff5-4444-afb5-9c7a25f1019a | checkpoint | ID Plate
669d81f1-11fb-575b-9e51-c37fc9b98d28 | textbox | ID:
e16f861a-10ed-4bcd-86d9-ee747528cc71 | section | Pre-Pour Check Approvals
8c9736e3-6e34-466a-91ba-7ffd87e8973b | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
1bf0bbd6-0e41-4f71-9cbc-4c27f1c142dc | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
0e11ed6e-ff70-4d9a-a982-694185cb6ab0 | checkpoint | Temporary Fix ID Plate to Formwork
fddf2caf-acea-4028-989e-59676fbabfdc | checkpoint | Double Check the Ferrule placement -Type BB
1692b9cf-24b8-4542-af59-c43a0b72a21a | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
8dbb59ac-ff7e-4d2b-b97c-9fd1ca63f27d | checkpoint | Embeded Items - Fixed Firm & aligned -Check
0ee9cc16-208e-54bc-9643-0900cfba7add | tickbox | Ferrules - Position,Size,Orientation -M24 (96mm)
012d6cf3-26f5-51a3-ad44-fc7e410f6e75 | tickbox | Ferrules for Dowels - Position, Size -M24 (96mm)
da97b63c-dfda-5c25-9d93-717f65a46184 | tickbox | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
d16ab654-34f2-4fb9-8a48-a6cf2a68daa5 | checkpoint | Concrete cover Check - minimum 30mm
984ddd6e-3253-4ef8-9939-67c5c417bd6e | section | Quality Assurance
7cefdc82-37f3-4369-af44-9cca5733859d | checkpoint | QA - Final Check of ALL measurements
646823c4-44cc-4af6-920d-b69915e05fb9 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
83433da5-3686-4078-be19-f9fa3f3a9dfd | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
3763a462-e041-420c-b922-122101ce4618 | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
af0df34e-25b4-5a27-aa28-232a309c22d8 | date | Pour Date
28648170-d9ae-4be5-bbf6-16350dd6d613 | checkpoint | CONCRETE TEST Procedure
82a3d261-7fb9-4d13-bffd-b0829f4b4fe1 | checkpoint | APPROVAL FROM ENGINEER
06761a02-014d-4645-94cc-6fbd1058daac | section | Other Arrangements
db91490c-0131-4848-8830-dbdf6dac9336 | checkpoint | Concrete surface Finish Requirement arranged
501e46fd-1a94-5618-953b-da8458e0e022 | dropdown | Finish: | Fine finish,Broom finish
1f110128-a362-4e22-827f-804e84ab4bcd | checkpoint | Curing Procedure arranged