## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHC-ITP-029 - PVC TGSI Installation | itp |  |  |  |  | FHC-ITP-029 - PVC TGSI Installation Rev0
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Placement of TGSI
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Completion
checkpoint | 3.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: