## Master List Templates
Id | Type | Name | Values | Prompting Name
139ae613-a60f-4f08-bb5e-4d8e697fa9a5 | checklist | Nuraply 3PM - Concrete Substrate Checksheet |  | Nuraply 3PM - Concrete Substrate Checksheet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f4a07723-5ff8-4961-8780-f0bb3d1168c8 | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content.
3f12e6c9-8c89-4273-9f8e-06a8c217713b | checkpoint | Surface smooth and clean with falls as per plan.
4149219f-48e7-4313-b6a9-b4112ea9b539 | checkpoint | Cavities and cracks filled, flushed off and cured.
688a114c-ce47-4afd-b96c-570ad125cd7c | checkpoint | Concrete surface firm with any soft concrete or laitance removed.
ebf68020-f8b9-4518-bf5f-35fa86cfcb45 | checkpoint | Ponding areas removed.
299ef00c-7a33-41f6-905c-a0501cd4821f | checkpoint | Roof drains and overflow recesses formed to fit rebated outlets.
6b662681-7916-4bfc-91e9-2011292df67d | checkpoint | Mortar or Nuralite Bitumen fillets to all upstands and smooth 5mm radius to all external edges
ddbd9520-0913-495f-91bd-4f1ce83afd28 | checkpoint | If terminating into a chase, pre-form the chase and ensure it’s straight and 20mm deep.
dbabf6e8-93c3-4ce7-bd19-0063be925a67 | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
2b0b98b5-c153-41b7-85c9-f4b867be6abe | checkpoint | Construction joints incorporated in slab as per designer’s specification.
dabe5da4-8c9a-40d2-a617-0cb52901f2e6 | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
5df12d1e-b54d-5bc3-907b-8e814ce5b18c | textbox | Additional Notes
ee5afa23-bfc9-4863-97a3-a2e629df981e | checklist | Nuraply 3PM - Timber Substrate Check sheet |  | Nuraply 3PM - Timber Substrate Check sheet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
27c93b1e-96e0-451f-9dbf-90fd9fb9db9c | checkpoint | Structure complies with the New Zealand Building Code and plywood complies with AS/NZ 2269
2c33c34d-b4be-4914-af8b-48e52cf3a9b9 | checkpoint | H3.2 CCA treated plywood sheets 17mm thick for roofs, 21mm thick for decks.
727d03e6-d25c-4159-9198-ba04bd26c7cb | checkpoint | Strandboard laid as per plywood with rafters and nogs at 400mm centres.
ca3072cb-bba7-4977-9fe0-c2ae515fdf64 | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks. Unless otherwise specified.
85316bb2-5476-498c-a53a-25a8d4999988 | checkpoint | Sheets stagger lay (fully offset) with falls as per plan.
50a321b2-1adc-4563-858f-b7e79528c23e | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges.
49e6c035-ffc6-4e14-821b-eef43e29f882 | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments.
446d971f-ee7c-42c7-8aa8-c0af6040a0bf | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing.
5e18d823-e4b9-4e16-acd1-517597b56bbc | checkpoint | Fillets installed to all internal junctions and neatly fitted.
2a8f3954-136d-4098-82be-28aa683f03eb | checkpoint | Mitres neatly formed.
9b5cc42f-26c4-4196-aa4b-0bc0fd8538da | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface.
4f725843-f7c6-4d8b-9240-125eb1e70d26 | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush.
aa50dd50-c2ea-4f55-bba4-7973079b7d17 | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
3be0bf5d-4ebf-4469-97c9-63b12612746d | checkpoint | Substrate dry, (less than 20% moisture), clean, firm and suitable condition for laying.
337982d1-a903-5211-9bb3-a0f4d5df51e1 | textbox | Additional Notes
d7e8da38-eb1b-44b6-9cb1-8df17c40a208 | checklist | Nuraply 3PM QA Capsheet |  | Nuraply 3PM QA Capsheet
658d48d1-7c25-42a1-a97e-4d1863f1e7f0 | section | Details
1ac2a029-821d-453e-95f4-ef24b7cb3242 | checkpoint | Substrate readiness form completed
d86aac6d-27e9-4a9e-a8b0-e728ab1fdc5c | checkpoint | Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
f825dd8d-5f55-414e-b50e-6f26bb385060 | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
5dd51845-7c15-4b0f-ab62-38b3d0aeff88 | checkpoint | Roof drains & overflows installed to specification and watertight
b9cc62ad-9a57-4ce3-b688-c0ec65eca1ea | checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer or adhesive used as per specification.
7e376c18-1ae5-41c2-845a-75ded34603e8 | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination.
19885259-2646-45ff-b6c4-42957a626403 | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off.
90c4b26a-4f17-4551-a51a-2eed298c3e29 | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
74b8821c-b222-456a-86b3-f4c546bf4d61 | checkpoint | Overall installation free of wrinkles, creases and splits
e8f96b05-31ea-41e1-8d50-d268ea00bf3b | checkpoint | All penetration details completed to specification including under/over flashing
55489d05-e7f3-4d94-b8f2-16dbe24d46ca | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
13d021f1-0696-5ffe-80d9-12f4ee8df408 | textbox | Additional Notes
9907e02b-b50d-4f0c-8f99-289b9868d605 | checklist | Nuraply 3PT QA |  | Nuraply 3PT QA
c0109349-e071-4342-80da-42d55748dacc | section | Details
26fe7c6d-b6b0-49d0-b624-43a4004fcbc8 | checkpoint | Concrete Substrate checklist completed before work commenced.
8ab4b445-5763-4176-b82c-5a868d464647 | checkpoint | Any movement joints installed to approved specification/detail.
49bf3525-d87b-45dd-9874-4284e4345f4c | checkpoint | Mortar/concrete fillets fitted to all internal junctions and corners chamfered at a 45° radius.
0fd59664-a1e8-41ae-a087-0ed96b38f5f6 | checkpoint | All corners and upstands incorporate reinforcing or underflashing
00bdab01-1bd7-49a2-9c21-d8f1b35c8300 | checkpoint | Under-slab membrane extends beyond footing and carefully protected until vertical membrane installed.
329bef83-7ec8-4c1e-ad2b-134825e81db6 | checkpoint | Side laps 80mm and end laps 150mm fully torched and seamed. Bleed visible on all joints.
6d1de61f-fcaa-4aa8-a3cc-cc185770aa08 | checkpoint | All penetrations installed to specification including under/over flashings.
dd0862cc-3668-4410-a286-cffb5744325a | checkpoint | Junction of the floor and wall membranes installed to specification fully bonded and watertight.
6412346a-d4ca-4872-8177-17f92b1a5c66 | checkpoint | Any membrane punctures or mechanical damage to membrane repaired to specification.
ac3bc206-2866-47fb-9ae7-8baae95a9151 | checkpoint | Membrane termination completed to approved detail.
b3a3567f-8aee-4ba6-8bb0-6d5b62f36653 | checkpoint | Membrane protection boards installed correctly.
4573a3b9-5493-431c-ad95-23a7503ddd78 | checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
913e93fb-d49f-524c-8705-452ff8d8bcf1 | textbox | Additional Notes
c7e4c259-c0e7-4ead-a012-fa4fdd932703 | checklist | Nuraply 3PT Substrate Checksheet |  | Nuraply 3PT Substrate Checksheet
a74a1b27-e168-45ef-9ed8-5da6bc73fe33 | section | Tanking
2609bac2-4597-493e-8b76-300e93a12e3e | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content.
1d0db673-c736-410e-818c-15a479d5ae6c | checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured.
d910cd0d-a953-476a-91b5-0848a9d4162d | checkpoint | Waterstops installed to construction joints if applicable - located 50mm from rebar.
fa28f563-695e-4dfc-8ab3-ce58acb05879 | checkpoint | Concrete surface firm with any soft concrete or laitance removed.
578234da-3a5b-42aa-ab4c-d4d122825c2d | checkpoint | All protrusions removed. Surface free from foreign matter
922db009-5285-4293-855f-c01b98f97825 | checkpoint | Mortar or Profili bitumen fillets to all upstands and smooth 5mm radius to all external edges
f43522e8-bcb8-4d07-9dbd-53fd96c731e0 | checkpoint | If terminating into a chase, pre-form the chase and ensure it is straight and 20mm deep.
af12a36f-77e0-4481-b8de-9a2b96e44c3b | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite system.
163280e9-b644-420a-9a9c-12c8fadf0417 | checkpoint | Confirmation that Nuraply 3PT or Nuraply 3PG (if plants will be nearby) to be installed.
10c98ac6-8641-58dc-aab4-a9e5f16696d9 | textbox | Additional Notes
5ef5d5ef-7749-4c7c-abf3-05418894f791 | checklist | Nuraply 3PTM QA Footings |  | Nuraply 3PTM QA Footings
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1bdd3988-4c9e-44b8-b518-137ed398d6ed | checkpoint | Concrete Substrate checklist completed before work commenced.
25f0f343-8a2e-4d36-8aad-404e47538e31 | checkpoint | Any movement joints installed to approved specification/detail.
d95dd979-d09a-4241-98f8-bd7e814bb21b | checkpoint | All corners and upstands incorporate reinforcing or underflashing
b69b6fc4-b287-40ba-aa13-9d7ab8ed8eec | checkpoint | Under-slab membrane extends beyond footing and carefully protected until vertical membrane installed.
4818cccb-2097-437d-8fd6-9ab54e3b38aa | checkpoint | Tags installed to footing membrane
8c176bb1-a146-427a-b527-23e1c2386c42 | checkpoint | All penetrations installed to specification including under/over flashings.
5d52e7c1-e461-49ee-a17a-8e9bbd94a72f | checkpoint | Any membrane punctures or mechanical damage to membrane repaired to specification.
ac2de577-be3a-56a3-9128-6d1bab4e0271 | textbox | Additional Notes
947cabd7-2abb-448c-906a-56f95e51f4f0 | checklist | Nuraply 3PTM QA Underslab |  | Nuraply 3PTM QA Underslab
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ec5896f-5b68-400c-be5e-ac1d72f25a81 | checkpoint | Concrete Substrate checklist completed before work commenced.
012c763e-8dd4-41cb-9022-8ab6482617a8 | checkpoint | Any movement joints installed to approved specification/detail.
8ea2ad1e-737a-406f-967a-509ab6cfb752 | checkpoint | All corners and upstands incorporate reinforcing or underflashing
a4284c4e-f3b2-4968-ba95-53235106afa3 | checkpoint | All penetrations installed to specification including under/over flashings.
a79ccb6e-d1b8-42ab-aa13-251f38e7134b | checkpoint | Any membrane punctures or mechanical damage to membrane repaired to specification.
791e02bc-8c83-5406-88f6-f08b92146cef | textbox | Additional Notes
44e15c04-5f21-45a2-a4d5-189358a4bc77 | checklist | Nuraply 3PTM Substrate Checksheet |  | Nuraply 3PTM Substrate Checksheet
b9fd9a61-2ade-483d-8d94-bc9874d4b4a6 | section | Worksite
e2277429-2480-4e45-963d-af7483cd2c26 | checkpoint | Smooth substrate with no sharp rocks.
9cb09fd4-8118-4dbe-a9d1-53298ed99d72 | checkpoint | Slab/ concrete pour height confirmed.
77cfd3c5-f2ea-464d-b748-37044af585bc | checkpoint | Pipes and services installed and back filled.
ef6d2824-de08-5515-8152-c880d9e85849 | textbox | Additional Notes
faffd4c2-4e6f-432f-a1bd-b631cdbadd50 | checklist | Nuraply Enertherm QA |  | Nuraply Enertherm QA
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d9f4bb57-7def-4a1c-a35c-9a60f553adbe | checkpoint | Sheets stagger lay (fully offset).
f0e7b020-0d21-48df-a9a2-915509d5d160 | checkpoint | Any gaps in the insulation filled to prevent thermal bridging.
6ef35ba1-ee77-4b0f-af81-742b1c5da07c | checkpoint | Material fastened with the correct quantity of IKOfix Thermal Break Flanges and Fixing Screws or approved Adhesives.
704fa3dc-ee1d-4b8f-8c5e-e8018d4bf298 | checkpoint | Edges of insulation supported by metal sheet ridges or ALU tape.
3f4daf3d-176e-4a96-b13b-67aa7a795459 | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
7b215646-966b-4f50-9857-4f5e0a70d27e | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
e08ea72e-a6e4-518b-b82a-2b98cf2109cf | textbox | Additional Notes
41d726e2-2c1e-4d76-8e83-8672816a55ca | checklist | Nuraply FSA QA Basesheet |  | Nuraply FSA QA Basesheet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4e623396-aefa-4e44-8743-5d1c10e93b6a | checkpoint | Substrate readiness form completed
25633d24-b42b-43de-9116-38dd37bbb0f5 | checkpoint | Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
73d20b18-1441-4018-baff-aecde0c39ca7 | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
4ee2b9de-dd8b-4efb-8f7a-84ac2ba8cc75 | checkpoint | Roof drains & overflows installed to specification and watertight
2a7aae31-222a-4b3e-8cf4-b8aa6cc884a4 | checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer or adhesive used as per specification.
0da88e53-3277-541b-99c0-45100d466665 | textbox | Additional Notes
f479f867-e217-4c53-b4bb-a6a8d7feaea1 | checklist | Nuraply Vapor Barrier QA |  | Nuraply Vapor Barrier QA
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b4884036-0218-4c1a-a27c-bc598abfb194 | checkpoint | Structure complies to the New Zealand Building Code
e281c76e-7c1b-48ff-8d64-bacc8433d1ed | checkpoint | Confirm the substrate slope complies with plans.
c77e48c4-4e4a-473a-9e7d-38b2b63cfe70 | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface.
7d1ed107-8a41-4649-ae13-aee35de3df9a | checkpoint | Ensure only approved accessories to be used for drainage and venting.
7f190ad2-327b-48d5-929f-a4b8152dc99e | checkpoint | Ensure NURAPLYU ALU vapor barrier extends above PIR height.
5f91cd66-bb80-4b18-88df-03d63aef8b4c | checkpoint | Ensure the NURAPLY ALU vapour barrier is installed correctly and that any damage has been repaired.
423a68de-0c93-4e70-879b-afc47fab5db0 | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
66e52b73-290a-47b2-9802-9f079d85a381 | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
6af99418-d41b-55be-82b5-af8647b9d3b2 | textbox | Additional Notes
98926fee-5e85-4bd8-ada1-1f4742f63214 | checklist | Project Details |  | Project Details
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fe9297c2-ef93-4a89-9699-943e67a2def6 | checkpoint-no-value | Project Details
ad445944-47af-5fcd-b345-0afd74e68301 | textbox | Project Name
a3249090-1811-583f-b14d-39905d05ab80 | textbox | Form completed by
42f1e1ed-ebbc-5d52-a6bb-7242b68e7ebc | textbox | Company
fd24b38c-9ee4-5322-b86a-d7629d591d2b | textbox | Area ready