## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITR-E-04 Schedule of Test Results DB |  |  |  |  | Yes | ITR-E-04 Schedule of Test Results DB | 02f4c0af-eea8-4006-aae5-ac3e68ea71fa
checkpoint-status |  |  | checkpoint | Upload completed ITR scans
checklist-sectioned |  |  | checklist | ITR-I-15 Pressure Instrument Installation |  |  |  |  | Yes | ITR-I-15 Pressure Instrument Installation | 08afbc73-9655-47e8-8c8c-84a4d00745e0
checkpoint-group |  |  | section | Pressure Instrument Installation
checkpoint-status |  |  | checkpoint | Check Instrument Nameplate details are correct in accordance with the instrument index.
checkpoint-status |  |  | checkpoint | Pressure Instrument calibrated before installation (ITR-I-07 Instrument Calibration)
checkpoint-status |  |  | checkpoint | Instrument mounted as per hook-up drawings
checkpoint-status |  |  | checkpoint | Air line/Impulse line are correct material to site specifications
checkpoint-status |  |  | checkpoint | Air line/Impulse line are routed tidily and as per hook-up drawings
checkpoint-status |  |  | checkpoint | Correct bolt size and material/grade used
checkpoint-status |  |  | checkpoint | Local indicator is mounted and easy to read, easy access for technicians
checkpoint-status |  |  | checkpoint | Instrument and tubing are adequately supported as per drawings
checkpoint-status |  |  | checkpoint | Isolation valve installed
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 8b1df3ed-715e-5075-afd2-d7f8af6acc53 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 691f5cfd-3da1-5f9c-ae83-090c8757c974 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 96f179de-b16d-52da-a657-9e816fb8990f |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-14 Motor Control |  |  |  |  | Yes | ITR-E-14 Motor Control | 0c925328-5e22-46b2-a422-8e4656f4a8a2
checkpoint-group |  |  | section | General Motor Control
checkpoint-status |  |  | checkpoint | Check all labelling and warning signs are correctly installed and visible
checkpoint-status |  |  | checkpoint | Check control equipment is clean and free from dust, debris and tools
checkpoint-status |  |  | checkpoint | Check preservation and transit items are removed
checkpoint-status |  |  | checkpoint | Check there are no mechanical damage and no damage to paintwork
checkpoint-status |  |  | checkpoint | Check correct earthing is installed as per design from earth grid to the controls, the cable trays and the motor
checkpoint-status |  |  | checkpoint | Check all cabling to control gear and motor is undamaged, supported and tidy
checkpoint-status |  |  | checkpoint | Check earthing bar and connections are correct and tight
checkpoint-status |  |  | checkpoint | Check incoming and outgoing power cables are terminated and glanded correctly
checkpoint-status |  |  | checkpoint | Check phase identification on power cables is correct and visible
checkpoint-status |  |  | checkpoint | Check incoming connections U1, V1, W1, outgoing connections U2, V2, W2, busbars and connecting links are correct and tightened to required torque
checkpoint-status |  |  | checkpoint | Check all other nuts and bolts are tight
checkpoint-status |  |  | checkpoint | Check spare gland entries are plugged with correct rated plugs
checkpoint-status |  |  | checkpoint | Check all doors, drive cover, motor connection box and other protective guards are installed correctly and all live parts are protected
checkpoint-group |  |  | section | Variable Speed Drives (VSD)
checkpoint-status |  |  | checkpoint | Record VSD Nameplate Details
text | 1be1b366-f99e-5da4-a03f-80e0f52f103a |  | textbox | Volts (Input)
text | 32fee5d8-9058-5716-a056-4906776ac01f |  | textbox | Amps (Input)
text | ae1c17da-a642-54e2-a88e-19b4d7fbc690 |  | textbox | Amps (Output)
checkpoint-status |  |  | checkpoint | Check mains Voltage (usually 690VAC) matches VSD nominal voltage (input)
checkpoint-status |  |  | checkpoint | Check input power and motor cables are appropriate and capable of carrying the load current. For motors >30kW a symmetrical shielded motor cable must be used.
checkpoint-status |  |  | checkpoint | Check all internal cabling and auxiliary wiring is complete as per latest design drawing, properly supported, neat and undamaged
checkpoint-status |  |  | checkpoint | Check control signal cables use twisted pairs
checkpoint-status |  |  | checkpoint | Check control signal and profibus cables shield is earthed at one end
checkpoint-status |  |  | checkpoint | Check analogue and digital signals are run in separate cables
checkpoint-group |  |  | section | Check that voltage segregation is applied along the length of cables:
checkpoint-status |  |  | checkpoint | Distance between input power and motor cable >300mm
checkpoint-status |  |  | checkpoint | Distance between input power and control signal cable >200mm
checkpoint-status |  |  | checkpoint | Distance between motor cable and control signal cable >500mm
checkpoint-status |  |  | checkpoint | Check there is no power factor compensation capacitors installed on the outgoing power cables
checkpoint-status |  |  | checkpoint | Check gland plates with single core power cables are non-magnetic at VSD and LIS
checkpoint-status |  |  | checkpoint | Check mains voltage cannot be applied to the VSD output by means of a bypass connection
checkpoint-status |  |  | checkpoint | Check appropriate auxiliary 24VDC fuse / circuit breaker is installed at MCC
checkpoint-status |  |  | checkpoint | Check VSD Incoming Supply has appropriately rated fuse disconnection switch (that can be locked in opened position)
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | e63d3407-035d-501b-9b25-795794bea565 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 1c4e8bc8-ca14-5a98-8fa8-e4a477d9d39e |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | e0407951-1eb4-5509-af71-58a2c5066295 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | JHA - Job Step |  |  |  |  | Yes | JHA - Job Step | 0ceb3186-ca90-4114-a163-388de7fb1b6b
checkpoint-group |  |  | section | Task Step - add task step for each individual task
checkpoint-status |  |  | checkpoint | Task Step - add task step for each individual task
date | a48b2c81-093f-5e98-be8c-236609789678 |  | date | Date:
text | 6b98b1ca-508f-5366-b7ec-ae4ef67212dd |  | textbox | Task step number (eg. Step 1, Step 2 etc):
text | 7eb469f5-54e5-5d76-a824-d5f435427697 |  | textbox | Task details:
text | dfc5ed6c-2157-50ca-bbda-36357b9c0504 |  | textbox | Hazards:
select | cbf17e3e-ae78-5244-8475-6f548e263140 |  | dropdown | Initial score (Likelihood x Severity 1 - 25) - Refer to risk matrix | 1, 2, 3, 4, 5, 6, 8, 9, 10, 12, 15, 16, 20, 25
text | 184a0d4a-7f2a-58b4-abae-8581740717cf |  | textbox | Potential consequence:
text | 5b3103bb-2a95-5c2d-b57c-6af6e6111cb1 |  | textbox | Controls:
text | b785a921-9f58-5f35-b41f-e9b114505897 |  | textbox | Recovery steps:
select | 169c0eb2-8e66-59b1-bcea-961d5c17378c |  | dropdown | Residual score (Likelihood x Severity 1 - 25) - Refer to risk matrix | 1, 2, 3, 4, 5, 6, 8, 9, 10, 12, 15, 16, 20, 25
checklist-sectioned |  |  | checklist | ITR-I-09 Commissioning Instruments |  |  |  |  | Yes | ITR-I-09 Commissioning Instruments | 0dea2eba-b796-42ac-8c7c-f58ce5322714
checkpoint-group |  |  | section | Required Data
checkpoint-status |  |  | checkpoint | Required Data
text | 700f3079-173d-5bcd-83d0-4152c6429cf4 |  | textbox | Instrument range:
checkpoint-status |  |  | checkpoint | Installation complete
checkpoint-status |  |  | checkpoint | Point-to-point
checkpoint-status |  |  | checkpoint | Haz. Inspected
checkpoint-status |  |  | checkpoint | Tag correct
checkpoint-status |  |  | checkpoint | Hook-up correct
checkpoint-group |  |  | section | Alarms & Set points
checkpoint-status |  |  | checkpoint | Alarm Lo
text | 6ae769b7-1206-55ac-aa0e-56dfd25eb207 |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Alarm Lo-Lo
text | aca0445b-4e51-50cc-a40f-3205f8335a85 |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Alarm Hi
text | c59b0629-c461-52dc-988f-8ba1eefdbda0 |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Alarm Hi-Hi
text | cf36d635-abf5-5661-b36b-8fa8c82dbb62 |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Set Point 1
text | adb37473-05e2-551b-acd9-3c2072a2dfc3 |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Set Point 2
text | 4a8f0683-03fc-5835-9db7-f9d41f7a0d9f |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Set Point 3
text | da95ca27-c968-5edf-9fdc-9af72281620c |  | textbox | Activated:
checkpoint-status |  |  | checkpoint | Set Point 4
text | 46afdf3a-1948-56a7-b60e-b6982266bbaa |  | textbox | Activated:
checkpoint-group |  |  | section | Calibration settings
checkpoint-status |  |  | checkpoint | Calibration settings
text | 298f0a53-0362-5751-ae32-22f78409a54e |  | textbox | Zero
text | 525d255f-4045-5542-9785-c9e2abc3b636 |  | textbox | Range
text | 2d4fe49b-e263-5577-b0cf-b201204996a3 |  | textbox | Other (Specify)
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 2e255d59-a738-5e39-9b17-6e0c579113d2 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 99674c3b-acd5-597a-bb9a-bf2bb0a581d6 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 6b236778-a3cb-5649-aea8-66019cb7f31a |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-06 Control Panel |  |  |  |  | Yes | ITR-E-06 Control Panel | 1827948d-28dd-45c7-b0c4-34df9e514251
checkpoint-group |  |  | section | Control Panel
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | Check holding down/mounting arrangement is correct.
checkpoint-status |  |  | checkpoint | Check for mechanical damage.
checkpoint-status |  |  | checkpoint | Check that panel is correctly earthed.
text | 21fe2a89-b314-513c-a50f-a62110cccab9 |  | textbox | Check earth continuity between panel and local earth system is <1.0 Ohm
checkpoint-status |  |  | checkpoint | Check tightness of circuit connections.
checkpoint-status |  |  | checkpoint | All internal cabling and wiring is correctly numbered, colour coded and terminated
checkpoint-status |  |  | checkpoint | Ammeter scale and current transformer correct.
checkpoint-status |  |  | checkpoint | Check internals for cleanliness.
checkpoint-status |  |  | checkpoint | Check manual operation of selector switches, MCB, push buttons, etc.
checkpoint-status |  |  | checkpoint | Incoming cables correctly glanded, terminated and labelled.
checkpoint-status |  |  | checkpoint | Unused holes are sealed.
checkpoint-status |  |  | checkpoint | Heaters correctly installed.
text | e984c2b0-9eeb-58d9-ac82-8247e88d7771 |  | textbox | Heater circuit Insulation Resistance:
checkpoint-status |  |  | checkpoint | Fuse rating correct.
checkpoint-status |  |  | checkpoint | Padlocking facilities correct (if applicable).
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 6ed803f6-ef27-58d8-953c-1ab83614607c |  | textbox | Make:
text | 0d6b7455-2d19-54b1-aaaa-86d53ad5b662 |  | textbox | Model:
text | 67e79ee3-3769-562c-b1d4-f936fdbbfdea |  | textbox | Serial No:
text | afef1523-ed1a-5123-a2e5-27f0e8ee0567 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 6ce07407-bd1d-5433-8e4d-a0dc30767635 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | feeda30d-fd46-5886-9abf-4cbe7f25bf26 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 4058f8a1-6a93-594e-9649-6ace7e201d6b |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-12 Electrical Earthing |  |  |  |  | Yes | ITR-E-12 Electrical Earthing | 3112eeb8-3552-40f3-ba90-7a3e10d60f12
checkpoint-group |  |  | section | Earthing System
checkpoint-status |  |  | checkpoint | Earthing System
text | 14b8f791-0371-5954-80ac-06e9d9ea89ff |  | textbox | Electrode type
text | 00a248bc-8784-5a54-a84e-c77ed4392414 |  | textbox | Electrode length/size
text | ea27eb87-a04f-5fe4-a97b-2b9f3240cbfc |  | textbox | Location of Electrodes
text | 029a341f-a7fd-5f91-9445-1651791c1ecf |  | textbox | Method of installing electrode
text | bafc011d-39a8-59fc-802f-2761d8f57554 |  | textbox | Method of attaching to electrode (e.g Clamp, Cad Weld, Lug & Bolt)
text | 73f651af-4b3b-5f68-a3ef-b4a107adaf4f |  | textbox | Number of electrodes
checkpoint-group |  |  | section | General Items
checkpoint-status |  |  | checkpoint | Confirm earth grid layout
checkpoint-status |  |  | checkpoint | Ensure grid layout is in accordance with design drawings
checkpoint-status |  |  | checkpoint | Record number of grid interconnections
checkpoint-status |  |  | checkpoint | Ensure all metalwork is earthed as required
checkpoint-status |  |  | checkpoint | Check welding of earth bosses and associated surface finish
checkpoint-status |  |  | checkpoint | Ensure that earth cables/conductors have adequate mechanical protection i.e. conduits, kick-plates, PVC duct through concrete etc. at points of high exposure.
checkpoint-status |  |  | checkpoint | Ensure that brazing or welding of all joints has been completed correctly.
checkpoint-status |  |  | checkpoint | Ensure that adequate corrosion and weather protection has been installed around all connections, joints, lugs, Cad (thermal) welds and earth bosses
checkpoint-status |  |  | checkpoint | Ensure that earth electrodes are located within a protected, covered and identified surround.
checkpoint-status |  |  | checkpoint | All earth bosses and studs tight and fitted with shake proof washers and coated with protective coating.
checkpoint-status |  |  | checkpoint | MEN Link Installed (If applicable)
checkpoint-group |  |  | section | Earthing Conductors
checkpoint-status |  |  | checkpoint | Ensure that earthing conductor size is correct in accordance with approved installation drawings.
checkpoint-status |  |  | checkpoint | Check cable terminations/joints to ensure that all lugs/barrels have been crimped correctly.
checkpoint-status |  |  | checkpoint | Check terminations to ensure that all connections are correct, clean, greased and tight.
checkpoint-status |  |  | checkpoint | Check that all bi-metal connections have been performed correctly to manufacturer's requirements.
checkpoint-status |  |  | checkpoint | Ensure that the earth cables to the main earth electrodes are terminated at each end of the main earth bar.
checkpoint-status |  |  | checkpoint | Ensure that earth cable identification markings are in place.
checkpoint-status |  |  | checkpoint | Ensure that earth connections are not multi-coiled or 'pig-tailed' but are terminated as straight as possible.
checkpoint-group |  |  | section | Earth Bar Installation
checkpoint-status |  |  | checkpoint | Check for correct assembly of equipment
checkpoint-status |  |  | checkpoint | Check fixings and mounting points conform to project specification and are secure
checkpoint-status |  |  | checkpoint | Check for equipment levels and alignment
checkpoint-group |  |  | section | Earth System Testing
checkpoint-status |  |  | checkpoint | Using an Earth Resistance tester, measure earth resistance between electrodes or main earth bars & the earth body.
text | 58536edc-284c-5842-9e54-481dfdb44dfb |  | textbox | Record results:
checkpoint-status |  |  | checkpoint | Measure earth continuity from each earth point and/or equipment earth frame to the nearest electrode or main earth bar
label | 586349c6-1454-53e4-9750-72f0676894fb |  | note | Note: Sketch a layout of earth electrodes showing electrode numbers and distances and attach below
checkpoint-status |  |  | checkpoint | Earth Grid Test Results (electrodes connected)
text | 7a05727c-297b-5b11-b0f2-757176b6f306 |  | textbox | HV Earth grid:
text | a5fdddbb-5abb-5095-8b36-2e5bec830a0c |  | textbox | LV Earth grid:
text | ef5d2265-4c4f-5780-bc0b-c451e0f63fa6 |  | textbox | Combined HV/LV Earth grids:
text | bd2b8160-1584-58dc-a12b-a66bd36419f7 |  | textbox | Instrument Earth:
checkpoint-status |  |  | checkpoint | Earth Resistivity Tests
text | fbe09a25-8390-54be-bcd9-8adea56ba62c |  | textbox | From (Main Earth Bar or Auxiliary Earth Point):
text | 7458c7b0-aa81-5a58-be0b-91e1eebd2905 |  | textbox | Result:
text | f5c1fdaf-8105-5559-ad91-f07139140c15 |  | textbox | From (Main Earth Bar or Auxiliary Earth Point):
text | 2ee2ffb0-6dc1-5c8e-a01f-82e854b45e9d |  | textbox | Result:
checkpoint-status |  |  | checkpoint | Earth Continuity Tests
text | 77c56fc4-7be2-51ff-9dcd-63e82a156d5a |  | textbox | From: (Main Earth Bar Location)
text | b460338d-3716-5409-8c94-b88d5ad2d8e5 |  | textbox | To: (Earth Electrode number/description)
text | 43f92af5-51c5-5c0f-a833-e69ad5e50088 |  | textbox | Record Resistance:
text | adae23b5-a29c-58a2-b6b9-fa1bc32a4017 |  | textbox | From: (Main Earth Bar Location)
text | dbfd7c4c-7103-56ea-b811-23d61dd39cea |  | textbox | To: (Earth Electrode number/description)
text | cd019c78-9340-5094-9935-64cb0f64e058 |  | textbox | Record Resistance:
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | c0e35cae-85fe-5844-9186-4d9b3667a5dc |  | textbox | Make:
text | 2995e151-9fcd-5d45-98c6-6805f8a39b89 |  | textbox | Model:
text | 9d6f0324-2630-5579-b52b-d5b896a4f6f7 |  | textbox | Serial No:
text | a9661c3c-6969-5e3f-b4d0-98fe2572eea8 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | f9437749-ca9f-5f25-9a49-5d0876fc7b48 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 6bb66774-fc89-5800-a015-62030eab6e3d |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | d40ec1f0-6cf0-5ad9-9323-3d183fe56c5d |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | 3556f3ae-8c3b-4cb0-81b6-30894d42ff1b
checkpoint-group |  |  | section | Toolbox meeting
checkpoint-status |  |  | checkpoint | Toolbox meeting
date | c04dbfd7-0e01-5307-bbf5-96c5d53282b5 |  | date | Date:
text | 2a83af6e-66d1-5bd4-a459-0e514b9538e5 |  | textbox | Meeting location:
text | de19c522-3c93-59c5-bea4-1025953c0952 |  | textbox | Meeting conducted by:
text | 5c05bb47-fed0-5e82-883c-b607e5cbd9e0 |  | textbox | Meeting attendees:
text | cea77388-c86a-5763-9884-2dd96bed1040 |  | textbox | Today's work scope/Hazards
text | be3d0a7d-113c-59fb-ae72-011ffce299ff |  | textbox | Hazard controls:
holdpoint |  |  | signoff | PICWS Signoff
checklist-flat |  |  | checklist | Certificate of compliance (COC) |  |  |  |  | Yes | Certificate of compliance (COC) | 369a27f3-e48d-4e2a-8c42-cefe75b8ec50
checkpoint-status |  |  | checkpoint | Please upload Certificate of Compliance here when complete (COC)
checklist-sectioned |  |  | checklist | ITR-I-11 Cone and Thread Pressure Testing |  |  |  |  | Yes | ITR-I-11 Cone and Thread Pressure Testing | 407f6045-8ab0-4aea-9b0e-41e96173d423
checkpoint-group |  |  | section | General Data
checkpoint-status |  |  | checkpoint | General Data
text | ae04152c-bebf-5f3a-b742-aa6e4863ff22 |  | textbox | Location:
text | b2129331-281c-5f68-814c-f470578c3e69 |  | textbox | Duty:
text | 7f8206b8-2412-5cad-a417-caef49ea4d0e |  | textbox | Reference Drawings:
text | e6f1082e-eed2-5480-aa85-277c6a6e698b |  | textbox | Hook-up drawing:
text | ddfdee62-9af8-5e9a-ae12-04a1de864dd5 |  | textbox | Related instrument tag no:
text | 4ffc6092-3f74-5f65-97ad-826d785d9028 |  | textbox | Tube diameter and wall thickness:
text | 8094b7a1-2b44-5048-82d4-360c25eb27cb |  | textbox | Instrument location drawing:
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Tubing orientation as per hook up drawing.
checkpoint-status |  |  | checkpoint | Checked with a Torque Wrench and marked and tagged
checkpoint-status |  |  | checkpoint | Ensure Area is barricaded off to restrict unauthorized entry to personnel
checkpoint-status |  |  | checkpoint | Tube as per specification and hook up drawings.
text | f1b3df66-799b-5da0-8e82-fce0ba1250dd |  | textbox | Max design pressure:
text | 5c593972-ecf9-5f2f-8509-35191e4ec6fa |  | textbox | Test medium used:
text | 7af2dd11-f4bb-5cee-b24a-96e8a3d19f10 |  | textbox | Record Testing pressure:
text | 02b82b79-2942-5661-af28-5315150ef033 |  | textbox | Test pressure duration: | Minutes
text | 784514c1-ae00-5548-9a5f-df8622830e43 |  | textbox | Test leak rate: | Litres/minute
checkpoint-status |  |  | checkpoint | Chart recorder used and attached (where applicable).
checkpoint-status |  |  | checkpoint | Confirm all Tubing lines have been pigged / cleaned.
checkpoint-status |  |  | checkpoint | Check all plugs are replaced (if removed), vents are closed, and isolation valves are in correct positions.
checkpoint-status |  |  | checkpoint | Ensure equipment is left clean and in a safe state for handover to operations to the standard of ITP-I-08 Cone and Thread cleaning procedure
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 99910def-c26b-53cd-a502-c12885d1aa8c |  | textbox | Make:
text | 6e73b47f-3c02-5f69-ba0e-d6a76bf75181 |  | textbox | Model:
text | 07c026b6-0bf2-5b4e-b2de-058ed7cbb785 |  | textbox | Serial No:
text | 2a2412e6-2999-58e5-b545-dc740c60f678 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 1e79fa87-498f-5770-80cd-adc936b057b1 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 690c6e0c-eaf4-5050-b0e7-d67a9a056e9f |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 887611c4-5eda-5404-a74b-96b5a33d2bf7 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-01 General Electrical Equipment |  |  |  |  | Yes | ITR-E-01 General Electrical Equipment | 451763ae-3a4c-4fe2-9c0d-62a1e192d0bf
checkpoint-group |  |  | section | General Electrical Equipment
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | No mechanical damage and paintwork in good condition.
checkpoint-status |  |  | checkpoint | Installation is clean and tidy
checkpoint-status |  |  | checkpoint | Mounting arrangement correct
checkpoint-status |  |  | checkpoint | All internal cabling and wiring correctly installed and labelled.
checkpoint-status |  |  | checkpoint | External cabling is correctly installed and labelled.
checkpoint-status |  |  | checkpoint | Check that Equipment is correctly earthed.
checkpoint-status |  |  | checkpoint | Check gland, plate, frame & door earth continuity
checkpoint-status |  |  | checkpoint | All spare entries blanked off with correct plugs.
checkpoint-status |  |  | checkpoint | Check item is suitably rated for area (E.g. IP rating, Ex rating)
checkpoint-status |  |  | checkpoint | Conforms to Specifications and Drawings.
checkpoint-status |  |  | checkpoint | As-builts complete.
checkpoint-group |  |  | section | Electrical Checks
checkpoint-status |  |  | checkpoint | IR and Earth tests
text | 51a648f3-c462-5180-a7be-98d372d799f6 |  | textbox | Insulation Resistance (P/N to E)
text | 01df5e99-c5e6-5fb5-ba17-bd1c7c5fd083 |  | textbox | Earth Continuity:
text | a52bf763-6800-5a00-bf60-e339d31ecad1 |  | textbox | Earth Bonding:
text | 44a05bf1-a7fb-5334-a0fc-83f1510fae93 |  | textbox | Other checks:
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 0afbdc35-c628-5a89-98b7-90b0da3ec7d2 |  | textbox | Make:
text | 0bb25653-2e67-563c-81f7-a3d4e2cf4750 |  | textbox | Model:
text | aeb3039c-a682-5dd1-856f-d8ea3156bb07 |  | textbox | Serial No:
text | 9c8af018-324f-5568-8c4f-591fd8189d3a |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 80b87bdb-e315-5b6f-ab01-cdccfb1adac9 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 50d1db77-86d3-53f0-a3bf-8eda4314196d |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | ca66157d-207b-5aa2-a718-519ac0795a9d |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-02 Conduit, Ducting, Unistrut, Cable Tray & Ladder Installation |  |  |  |  | Yes | ITR-E-02 Conduit, Ducting, Unistrut, Cable Tray & Ladder Installation | 524e55d9-c3b3-4b84-a2a7-7ab9aee6ca3f
checkpoint-group |  |  | section | Conduit/Ducting Installation Below Ground
checkpoint-status |  |  | checkpoint | Check equipment details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | Check conduit cable enclosure installation is as-per design, layout drawings and specifications.
checkpoint-status |  |  | checkpoint | Check conduit has been installed to the correct depth, "cable below" tape or Magslab installed.
checkpoint-status |  |  | checkpoint | Confirm that there are no obstructions, and that the installation will be accessible for maintenance.
checkpoint-status |  |  | checkpoint | Check all fixings are tight and secure.
checkpoint-status |  |  | checkpoint | Check bends do not exceed the maximum cable bend radius.
checkpoint-group |  |  | section | Cable Supports Above Ground
checkpoint-status |  |  | checkpoint | Verify cable support has been installed as per relevant drawings.
checkpoint-status |  |  | checkpoint | Check all machined parts cut or drilled have no rough edges, have been de-burred & protected by cold galvanising to restore the previous protection.
checkpoint-status |  |  | checkpoint | All covers fitted if applicable.
checkpoint-status |  |  | checkpoint | Check cable support structures are adequately fixed and present no hazard to personnel.
checkpoint-status |  |  | checkpoint | Correct cable support size and type used.
checkpoint-status |  |  | checkpoint | Welded support brackets have been wire-brushed and painted to completion.
checkpoint-status |  |  | checkpoint | Splice plates, barriers, earthing system secure.
checkpoint-status |  |  | checkpoint | Trays / ladders, supports, brackets not interfering with other disciplines.
checkpoint-status |  |  | checkpoint | Check bends do not exceed the maximum cable bending radius.
checkpoint-status |  |  | checkpoint | Cables have adequate mechanical protection as and where required.
checkpoint-status |  |  | checkpoint | Inspect for system rigidity, and check levels to correct plane.
checkpoint-status |  |  | checkpoint | Earth bonding straps have been fitted to any sections that are split, hinged or flexible.
checkpoint-status |  |  | checkpoint | Tray bonded to structure at correct locations.
text | 0dfab124-e776-5bc4-9edc-fda86bb4cbb8 |  | textbox | Earth bonding continuity tested – record result:
checkpoint-group |  |  | section | Cable Transits
checkpoint-status |  |  | checkpoint | Transit frame installed as per drawings.
checkpoint-status |  |  | checkpoint | Transit frame identification marked correctly and visible.
checkpoint-status |  |  | checkpoint | Frame correctly packed with correct sized blocks and infills.
checkpoint-status |  |  | checkpoint | Correct stay plates fitted (non-ferrous for single core power cables.)
checkpoint-status |  |  | checkpoint | Rated insulation installed to transit (where required.)
checkpoint-status |  |  | checkpoint | Cables entering and leaving transits adequately supported and protected.
checkpoint-status |  |  | checkpoint | Cables pass through frames without strain on blocks.
checkpoint-status |  |  | checkpoint | All cables identified on both sides of transit and visible.
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 4f7e71c9-da84-531b-a9b6-6a719c9d0c8e |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 0611a3b5-be08-5165-bfe2-51c96a49798f |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | fcd63e4f-f39b-5f6b-bd9a-b789e68680d9 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-08 Heat Tracing Circuit |  |  |  |  | Yes | ITR-E-08 Heat Tracing Circuit | 5b0c0d9b-ba73-4e9c-8a86-6ed616c9536a
checkpoint-group |  |  | section | Heat Tracing Circuit
checkpoint-status |  |  | checkpoint | Circuit installed, connected & identified according to design drawings.
checkpoint-status |  |  | checkpoint | End caps and connection kits correctly installed.
checkpoint-status |  |  | checkpoint | All junction boxes properly supported, and all cables protected against sharp edges.
checkpoint-status |  |  | checkpoint | Cable termination and glanding at all junction boxes correct.
checkpoint-status |  |  | checkpoint | All spare entries blanked off correctly.
checkpoint-status |  |  | checkpoint | Insulation resistance to earth after installation:
text | 63ebd850-8bdd-5804-8e2f-1098b2eb8aae |  | textbox | Insulation resistance:
checkpoint-status |  |  | checkpoint | Phase to Neutral resistance
text | fcdcf0a2-845d-5f2e-8900-76c6d3b9261d |  | textbox | Insulation resistance:
checkpoint-status |  |  | checkpoint | Equipment certification meets the area classification requirements.
checkpoint-status |  |  | checkpoint | Confirm warning labels are fixed on outside of pipe lagging
checkpoint-status |  |  | checkpoint | Check correct rating of protection device against design drawings.
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | d513ea42-dbdd-5322-8127-b078bceac7c7 |  | textbox | Make:
text | 002dc2be-6734-5b23-9ae0-140abf5d041b |  | textbox | Model:
text | d879f80a-f093-5976-b343-3cd22af13f5e |  | textbox | Serial No:
text | bfb0e28c-939e-55b0-85b2-fc3a2b3a5b2a |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 0ae2ed7f-78e9-5846-8957-10b6fe6a3cb2 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 5e6b625f-4f4b-572e-ae9d-628acf0b61a1 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | b2d2c007-03c8-538d-8f38-52a3a63176d3 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-11 Generator Package (LV) |  |  |  |  | Yes | ITR-E-11 Generator Package (LV) | 5db56764-e36a-43d3-bb37-688eb0006ab0
checkpoint-group |  |  | section | Generator Package (LV)
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | No mechanical damage and paintwork in good condition.
checkpoint-status |  |  | checkpoint | Check terminal boxes and glanding correct.
checkpoint-status |  |  | checkpoint | Check earthing is correct.
text | e987bf96-ff0c-53a6-a73a-97c4ab807a2f |  | textbox | Test and confirm the generator earth to local earth system is <1.0 Ohm
checkpoint-status |  |  | checkpoint | Instruments correctly installed.
checkpoint-status |  |  | checkpoint | Heaters correctly installed.
text | 97254d6b-1013-5c65-8788-95008cd67c21 |  | textbox | Heater circuit Insulation Resistance:
checkpoint-status |  |  | checkpoint | Check unit for cleanliness.
checkpoint-status |  |  | checkpoint | Check manual operation of selector switches, MCB, push buttons etc.
checkpoint-status |  |  | checkpoint | External cabling correctly installed.
checkpoint-status |  |  | checkpoint | Protection of live parts adequate.
checkpoint-status |  |  | checkpoint | Main terminal box complete and terminations correct torque.
checkpoint-status |  |  | checkpoint | Ensure direction of rotation is clearly marked.
checkpoint-status |  |  | checkpoint | Check gasket and seals are not damaged.
checkpoint-status |  |  | checkpoint | Unused cable entries are correctly sealed.
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | b789af65-828e-5354-807a-22d43f6955cc |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 8bc47e6b-fbaf-55ff-bfa6-199ba6ae0e0d |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 143f74fb-bcf4-5d1a-9ff9-d507769e8963 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | As-Built Drawings |  |  |  |  | Yes | As-Built Drawings | 605edd65-ee11-43f2-a114-b732daa276fb
checkpoint-group |  |  | section | As-Built Drawings - attach scanned documents
checkpoint-status |  |  | checkpoint | As-Built Drawings - attach scanned documents
text | 725b3daf-5cb8-5f3e-aaf4-0e3d51e15af4 |  | textbox | Drawing no.
checklist-sectioned |  |  | checklist | ITR-E-16 Lightning Protection |  |  |  |  | Yes | ITR-E-16 Lightning Protection | 658f6c86-756b-41ba-977a-a135cfb98a2b
checkpoint-group |  |  | section | Lightning protection checks
checkpoint-status |  |  | checkpoint | Lightning protection checks
label | 1b7f701b-eded-5ead-bd43-aed4df7c904d |  | note | These checks shall be conducted in accordance with the requirements of AS/NZS 1768:2007
checkpoint-status |  |  | checkpoint | Check lightning conductor is 2 metres or more above the entire protected area
checkpoint-status |  |  | checkpoint | Check the materials and equipment used for the down conductors are suitable
checkpoint-status |  |  | checkpoint | Check the down conductors are routed, located and electrically bonded as required
checkpoint-status |  |  | checkpoint | Check all installed components are firmly secured
checkpoint-status |  |  | checkpoint | Check the method of protection against electric shock, including the measurement of distances
checkpoint-status |  |  | checkpoint | Check the resistance of all connections at the location of the connection. The resistance of each connection shall not exceed 0.05 Ohm
checkpoint-status |  |  | checkpoint | Earth termination system resistance is correct
text | 26540aed-3a75-5d49-8a88-afdb0d36f739 |  | textbox | Resistance value:
checkpoint-status |  |  | checkpoint | Insulation resistance of the electrical installation
text | 341f4b01-a876-5523-b4fd-41cd4a0f8c67 |  | textbox | IR
checkpoint-status |  |  | checkpoint | Continuity of main and supplementary bonding
text | 54f48828-470e-5301-83f8-75fa0550eece |  | textbox | Main bonding:
text | 76419e1f-b3fb-5b54-bc20-04cd2b27415e |  | textbox | Supplementary bonding:
checkpoint-status |  |  | checkpoint | Check earth termination systems are interconnected
checkpoint-status |  |  | checkpoint | Check isolating and switching devices correctly located
checkpoint-status |  |  | checkpoint | Check warning signs and diagrams are installed
checkpoint-status |  |  | checkpoint | Check accessibility for operation and maintenance
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 25db8446-4fb3-5da2-8295-f5ba782c786e |  | textbox | Make:
text | e916194b-cd44-5c79-a629-bd9aa023d690 |  | textbox | Model:
text | 60aea0b6-72ed-5d98-8c5c-da63b3842d3d |  | textbox | Serial No:
text | 31732061-b9af-5dd1-8fe7-2718f3d3b084 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 883ccd78-3207-54a0-8799-f117b8cde59e |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 56448892-9a2f-54bc-addb-aa3b21835367 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 7b0123c1-9ca2-5c9d-967e-b130cdad10cb |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-10 Electrical Equipment Package |  |  |  |  | Yes | ITR-E-10 Electrical Equipment Package | 66a4f1db-dd27-4b91-9d60-caae0597069b
checkpoint-group |  |  | section | Electrical Equipment Package
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | Check equipment is correctly rated for the area.
checkpoint-status |  |  | checkpoint | Check if package is complete with all accessories.
checkpoint-status |  |  | checkpoint | No mechanical damage and paintwork in good condition.
checkpoint-status |  |  | checkpoint | All transportation supports, stops and fastenings removed.
checkpoint-status |  |  | checkpoint | Package fixing down bolts/shims/washers installed and tensioned.
checkpoint-status |  |  | checkpoint | Check package location.
checkpoint-status |  |  | checkpoint | Check package is installed on a level plane.
checkpoint-status |  |  | checkpoint | External cabling (if required) correctly installed.
checkpoint-status |  |  | checkpoint | Internal equipment installed and all tests complete and accepted.
checkpoint-status |  |  | checkpoint | Verify package using vendor and/or project P&IDs.
checkpoint-status |  |  | checkpoint | Check that equipment is correctly earthed.
text | 7954d488-0f27-5569-815b-f6506dea0abf |  | textbox | Test and confirm the earth resistance between equipment and local earth system is <1.0 Ohm
checkpoint-status |  |  | checkpoint | All spare entries blanked off with correct plugs.
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | b67278f6-39c3-535b-abd1-0fc46c266a9e |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 2534e8c1-4afa-529c-98c4-ef700329e688 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | dfcf5c77-02db-5d33-9d69-d8ce550fdeeb |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-03 Instrument Pressure/Leak Test |  |  |  |  | Yes | ITR-I-03 Instrument Pressure/Leak Test | 74a431b1-965e-48b0-bc1e-4f6cc0ee79cb
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Tube identification correct
checkpoint-status |  |  | checkpoint | Check mechanical damage
checkpoint-status |  |  | checkpoint | Flow direction and instrument orientation correct
checkpoint-status |  |  | checkpoint | Tubing installed correctly
checkpoint-status |  |  | checkpoint | Tubing size
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Testing
label | 9b9c69c2-d750-5455-a73b-2510dc72454d |  | note | Verify test pressure and medium is correct per project and manufacture specification prior to test
select | 3ff3242c-4c9c-5219-b661-b64962726753 |  | dropdown | Test fluid: | Air, N2, Water, Hydro-oil, Other
text | cd6c9fe5-b10d-5d4f-84f2-b9713dc03131 |  | textbox | Test pressure:
text | 101dc5ae-b92d-5f71-8b7c-76df0c9fec7f |  | textbox | Max design pressure:
select | 26cfa6ee-d263-5cff-a7f6-4750dfabdb2d |  | dropdown | Test pressure unit: | kgf/cm2, PSI, kPa, bar, Other
text | 37586776-08f7-5c23-aa13-8a63499c506c |  | textbox | Duration:
checkpoint-status |  |  | checkpoint | Confirm all impulse lines have been drained and cleaned
checkpoint-status |  |  | checkpoint | Confirm any temporary test connections, valve etc. are rated for the intended test.
checkpoint-status |  |  | checkpoint | Confirm pneumatic, test gas and aspirator lines have been blown clear.
checkpoint-status |  |  | checkpoint | Check hydraulic lines flushed to project specification.
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 38ac0f9d-0128-5141-aa39-2b52c5fad90c |  | textbox | Make:
text | 325f1168-03e2-5a78-9e92-33d04fcf8ee1 |  | textbox | Model:
text | 6c286d63-4397-5dff-b6d4-bccb57d63a82 |  | textbox | Serial No:
text | 7de1125f-0231-5c55-9ca1-a931c3c7ee0c |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | d6f32d9f-a040-5c99-9336-1c48c7be503d |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 1015f717-91fa-577f-acb3-5c6b35e93414 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 11e4c32a-6d21-5a10-8ca0-c438f44f9e6b |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-13 Temperature Instrument Installation |  |  |  |  | Yes | ITR-I-13 Temperature Instrument Installation | 766757ef-c944-4efc-be9d-957b507707d5
checkpoint-group |  |  | section | Temperature Instrument Installation
checkpoint-status |  |  | checkpoint | Check Instrument Nameplate details are correct in accordance with the instrument index.
checkpoint-status |  |  | checkpoint | Temperature instrument calibrated before installation (ITR-I-07 Instrument Calibration)
select | 898bad38-4611-5f95-9cb5-d5e459731e95 |  | dropdown | Type of thermowell installed | Flanged, Welded, Screwed, Other
checkpoint-status |  |  | checkpoint | Thermowell details including flange size are correct in accordance with the specifications
checkpoint-status |  |  | checkpoint | Internal depth of thermowell checked and recorded
text | 86ae3bd4-0388-5317-86ad-15297584ae4d |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Bar material and tag number stamped on thermowell flange/exposed surface
button | 2e221b34-f9b9-5b3d-9337-ede461950125 |  | button | Thermowell CE marked | YES,NO
checkpoint-status |  |  | checkpoint | EOL resistor fitted and correctly rated where applicable
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 8ecccd7c-3111-5a4d-814e-57329098ae9c |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | a8235353-b555-5e15-9286-28e51f0ba8a7 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | adf33472-24c1-5b68-8734-96fb20adab0e |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-15 UPS Installation |  |  |  |  | Yes | ITR-E-15 UPS Installation | 7bf47f42-664e-49d4-8c7b-e40390097fb5
checkpoint-group |  |  | section | UPS Installation
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | Check for mechanical damage.
checkpoint-status |  |  | checkpoint | Panel IP rating is correct:
text | de1931bc-9a97-5433-82ac-7b468729ce1f |  | textbox | IP Rating:
checkpoint-status |  |  | checkpoint | Holding down arrangement and seat alignment correct.
checkpoint-status |  |  | checkpoint | Panels aligned correctly.
checkpoint-status |  |  | checkpoint | Earth alignment to vendor specification & connecting link bolts torqued to the manufacturers recommendations & marked.
checkpoint-status |  |  | checkpoint | External bonding correct
checkpoint-status |  |  | checkpoint | Bus bar alignment to vendor specifications & connecting link bolts torqued to the manufacturers recommendations & marked.
text | 92e5cd4c-9087-5f9c-9d4c-6641d6c9af1b |  | textbox | Nm.
checkpoint-status |  |  | checkpoint | Phase identification correct.
checkpoint-status |  |  | checkpoint | Instrument, indication lamps & interlocks correct.
checkpoint-status |  |  | checkpoint | Main switches, contactors, fuses etc. sized & identified correctly as per Single-
checkpoint-status |  |  | checkpoint | Line Drawings.
checkpoint-status |  |  | checkpoint | Check main isolator switch operation.
checkpoint-status |  |  | checkpoint | Check bypass isolator switch operation.
checkpoint-status |  |  | checkpoint | Check DC UPS battery isolator switch operation.
checkpoint-status |  |  | checkpoint | COM Interface & Mod Link.
checkpoint-status |  |  | checkpoint | Padlocking facilities correct.
checkpoint-status |  |  | checkpoint | Check internals for cleanliness.
checkpoint-status |  |  | checkpoint | Check manual operation of selector switch, MCB, push button, etc.
checkpoint-status |  |  | checkpoint | Incoming cable correctly installed, terminated & supported.
checkpoint-status |  |  | checkpoint | Unused cable entries sealed.
checkpoint-status |  |  | checkpoint | All internal cabling & wiring neat, correct & tight.
checkpoint-status |  |  | checkpoint | Heaters correctly installed.
checkpoint-status |  |  | checkpoint | Fans correctly installed.
checkpoint-status |  |  | checkpoint | Verify continuity of earth bar to frame
text | 6b2acb8b-2f0d-5ad0-9c0d-16ca364b7ca1 |  | textbox | Earth continuity:
checkpoint-status |  |  | checkpoint | Check Busbar Insulation resistance between Phases & Phases & Earth (690V-2500VDC, 400V -1000VDC)
text | 7a4b9d36-6cef-5a55-928c-8b854eee128c |  | textbox | L3-L2
text | fe0e1739-ae04-55ff-b357-51511ebc7b4f |  | textbox | L3-L1
text | b162c793-b712-5f8a-a53a-bd8acc367032 |  | textbox | L3-N
text | 344a9fe1-7f23-542a-8ca6-f6094f87ef7e |  | textbox | L2-L1
text | 0485f808-d02e-591a-bcf6-fa8416422bf8 |  | textbox | L2-N
text | bd70fed8-4f72-51b9-8493-c75e1101c6a2 |  | textbox | L2-E
text | a0d3c503-2a39-56bc-bcec-f88e040c041e |  | textbox | L1-N
text | f32c7518-f52e-5d08-b257-6a4a126d3330 |  | textbox | L1-E
text | 0246b5ee-a450-55ee-9d57-44b3f61f0a18 |  | textbox | N-E
checkpoint-status |  |  | checkpoint | Drawings marked up with relevant changes
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 9b339d0e-da12-58fb-af5e-3eb65228fae2 |  | textbox | Make:
text | 7d46317a-b65b-5875-a45f-eec38f3b3559 |  | textbox | Model:
text | cd976e82-aaad-5109-a177-dbb3174dcdba |  | textbox | Serial No:
text | e292347f-745c-54ee-9953-0195b7d4bb54 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | ef401e43-ba70-5138-843f-6973e614d370 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 3a5f6dc2-eb52-52ae-babb-ad464a7d218e |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 46f2778f-9407-5fe9-9437-41a490ff526b |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-flat |  |  | checklist | Record of Inspection (ROI) |  |  |  |  | Yes | Record of Inspection (ROI) | 7ce99b76-0c1a-46ae-aad2-20e458cbd6b0
checkpoint-status |  |  | checkpoint | Please upload Record of Inspection here when complete (ROI)
checklist-sectioned |  |  | checklist | ITR-E-13 Motors |  |  |  |  | Yes | ITR-E-13 Motors | 7e6f528a-8f08-4086-b232-263eebd9a817
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Tag number correct
checkpoint-status |  |  | checkpoint | Area Classification correct
text | ee2b83a5-2a8a-5385-ab7b-ea55f06f4343 |  | textbox | IP Rating:
text | 67fce126-768f-5d9e-ae14-f183f81e622d |  | textbox | Hazardous area cert:
checkpoint-status |  |  | checkpoint | Electrical Connections correct
button | 0b896658-16e3-5732-af02-01e020bd45a8 |  | button | Space heater | YES,NO
text | 58647fe5-c9da-5a22-bdd2-44aa566a77fb |  | textbox | Space heater Volts:
text | a99c2961-4cf5-5aa9-84d0-edea5ce51b58 |  | textbox | Space heater Power (Watts)
checkpoint-status |  |  | checkpoint | General condition
checkpoint-group |  |  | section | Nameplate Details
checkpoint-status |  |  | checkpoint | Nameplate Details
text | 50d71ce8-5013-5e12-866c-23d27bf68c11 |  | textbox | Tag No:
text | 61331e2c-7156-55fa-844b-0eafc39f98dd |  | textbox | Manufacturer:
text | ad381b70-d541-5fac-82c3-f404878bbc41 |  | textbox | Motor Serial Number:
select | 1fc6df7c-4167-5c50-b88a-bd73c7e342d4 |  | dropdown | Phases: | Single-Phase, Three-Phase
text | bd70ef54-5a6a-5de0-8751-5812b097d7b3 |  | textbox | Frame:
text | e47e7570-d510-5b30-b8f2-2329b828ac00 |  | textbox | Enclosure:
text | 6eb9bc87-d67d-5031-a17b-a8aa4c83b887 |  | textbox | Voltage:
text | 0c75b0d0-5572-5814-a0fb-48d3a4728e5b |  | textbox | Current:
text | d1cc8a22-1b4e-5396-a07b-df52e82ccb75 |  | textbox | kW:
text | ab4a1cf0-dc0b-539b-a23a-2100bc6e02cb |  | textbox | Speed:
text | c42f2336-7b26-5d50-ac7b-a2ed049ff01f |  | textbox | PF:
text | c9d84e00-2644-55e0-b78b-25d8d908a642 |  | textbox | No. of Poles:
text | 075df284-a6d2-58ca-921d-ff463d26585e |  | textbox | Insulation Class:
select | 49e8ee86-c8a4-583a-932b-eb675ff4edee |  | dropdown | Rotation direction (looking down shaft) | Clockwise, Counter-Clockwise
checkpoint-status |  |  | checkpoint | Bearing Specs
text | 034471ae-7e3d-5db3-9184-c016f7cbc5e5 |  | textbox | Drive end
text | f903bd79-ea66-5ee2-96bd-de69fddd1dbf |  | textbox | Non Drive end
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Equipment has been received in good condition and is the correct type as per the site drawings, specifications & data sheets
checkpoint-status |  |  | checkpoint | Check Equipment and Nameplate details are correct in accordance with the data sheet.
checkpoint-status |  |  | checkpoint | Identification Tag and Rotation Plate correctly fitted
checkpoint-status |  |  | checkpoint | Motor electrical coupling (Delta /Star) as per voltage is correct.
checkpoint-status |  |  | checkpoint | Check for mechanical condition, air ducts and fan free of debris
checkpoint-status |  |  | checkpoint | Correct glanding for area classification.
checkpoint-status |  |  | checkpoint | Holding down bolts fitted correctly.
checkpoint-status |  |  | checkpoint | Check bearing lubrication.
checkpoint-status |  |  | checkpoint | Check free rotation with driven equipment uncoupled
checkpoint-status |  |  | checkpoint | Cable(s) correctly terminated, labelled and colour identification
checkpoint-status |  |  | checkpoint | Terminations/ connections torqued correctly to data sheets.
checkpoint-group |  |  | section | Motor Installation Testing
checkpoint-status |  |  | checkpoint | LV Motor winding insulation resistance with cables disconnected
checkpoint-status |  |  | checkpoint | 1 Minute
text | 75e8400d-ea63-5461-8702-8c5368dabf1b |  | textbox | Winding "U"
text | 5d0a739f-e962-5781-b10d-496e50bebc83 |  | textbox | Winding "V"
text | 16e2b17b-fc82-5d72-998b-fb47edd5a98c |  | textbox | Winding "W"
checkpoint-status |  |  | checkpoint | 10 Minutes
text | 3aae298b-3e49-5e91-b243-a1f06115af90 |  | textbox | Winding "U"
text | 90ca66cc-fff5-57ec-99d2-523442c6ff58 |  | textbox | Winding "V"
text | e2c13e62-8502-5dc3-a7e7-817b49354296 |  | textbox | Winding "W"
checkpoint-status |  |  | checkpoint | Motor continuity between windings
text | bd422f12-c195-53b0-a2e3-6921103e6531 |  | textbox | U1 - U2
text | 658cc16a-1655-5e7a-97b0-3a90bec48fa7 |  | textbox | V1 - V2
text | 293b53bc-5533-5150-9b91-0cb277e0d680 |  | textbox | W1 - W2
checkpoint-status |  |  | checkpoint | Space heater continuity & resistance check
text | 4e5a1f69-007d-5801-b902-f818152c0134 |  | textbox | Continuity:
text | e8a32aed-5ccf-5beb-ab97-03a54cd8c3fc |  | textbox | Insulation Resistance:
checkpoint-status |  |  | checkpoint | Thermostat or RTD wiring resistance check
text | 7383d1fd-b9a1-5ae7-a70e-4d98f45c9ca1 |  | textbox | Resistance:
checkpoint-status |  |  | checkpoint | Check motor is earthed correctly and record motor earth bond:
text | b9aea3b9-37f3-5ba8-bae7-2e128ae22bc8 |  | textbox | External bond continuity:
checkpoint-group |  |  | section | Additional checks
checkpoint-status |  |  | checkpoint | Visual Inspections
checkpoint-status |  |  | checkpoint | Winding temperature detector
checkpoint-status |  |  | checkpoint | Air temp detectors
checkpoint-status |  |  | checkpoint | Bearing temp indicators
checkpoint-status |  |  | checkpoint | Vibration Monitors
checkpoint-status |  |  | checkpoint | Condensation detector
checkpoint-status |  |  | checkpoint | All spare entries in terminal boxes have been blanked off correctly (with certified plugs if applicable)
checkpoint-status |  |  | checkpoint | Inspect all Ex "d" terminal box flange surfaces and apply approved grease (if applicable)
checkpoint-status |  |  | checkpoint | Installation conforms to specification and drawings
checkpoint-status |  |  | checkpoint | As-Builts complete
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | d8359430-d20c-5074-8f60-03e6b97fbbf7 |  | textbox | Make:
text | c5206148-65e9-5803-9f47-1ab97ed847c4 |  | textbox | Model:
text | d02fb50a-3c0d-5929-9a88-fd3131db6bea |  | textbox | Serial No:
text | 40f0bd9f-b2fa-5707-a295-b45a5050de07 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | d2e20328-9cb3-5acf-8a56-639c6376b03e |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | fc0ec559-3d33-5001-936f-75eff0a2bd0b |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 23fa8248-21f4-5e12-afd2-7e9a1d88affe |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-10 Cone and Thread Tubing Installation |  |  |  |  | Yes | ITR-I-10 Cone and Thread Tubing Installation | 87eec5f9-4698-43ed-b566-3372cddaeef3
checkpoint-group |  |  | section | General Data
checkpoint-status |  |  | checkpoint | General Data
text | 44c2f0a3-e459-58ec-aaf4-750e2936127e |  | textbox | Location:
text | 758b2ea0-dffb-506e-93a3-5aa7431d9b67 |  | textbox | Duty:
text | c8181b4a-491e-5a15-87a5-66942a6e72bf |  | textbox | Reference Drawings:
text | 0d49a346-18d6-5185-ae5e-f6082e3562c2 |  | textbox | Hook-up drawing:
text | e27dc9d3-5e01-5711-8ae0-07b421a24d7d |  | textbox | Related instrument tag no:
text | 3c4b3894-fdee-59c8-8827-19bc58049f95 |  | textbox | Tube diameter and wall thickness:
text | fade9b6b-cd20-57bc-b6f9-ef9e14d792df |  | textbox | Instrument location drawing:
checkpoint-group |  |  | section | Cone and Thread installation - Stainless fittings
checkpoint-status |  |  | checkpoint | Correct thread compatibility and engagement
checkpoint-status |  |  | checkpoint | Correct thread lubricant used on fittings
checkpoint-status |  |  | checkpoint | Check fitting collar prior to connection - 1 to 2 threads visible at cone
checkpoint-status |  |  | checkpoint | Tube installation follows the client specification.
label | 40b55484-2be4-55af-bbb3-ac065d326930 |  | note | (Supports, Bracketry, Slope, Expansion, Vibration, Access, Cables)
checkpoint-status |  |  | checkpoint | Tube bent correctly, sufficient straight section into fitting
checkpoint-status |  |  | checkpoint | Tube cut clean and straight, de-burred, reamed, and blown through
checkpoint-status |  |  | checkpoint | Lubricate collar, cone and gland thread at assembly to prevent galling
checkpoint-status |  |  | checkpoint | Correct Tube nut used for the right sized tube
checkpoint-status |  |  | checkpoint | Ensure No thread tape or sealant are used on tube nuts
checkpoint-status |  |  | checkpoint | Tube fitting hex torqued to ensure correct tightness, marked with pen
checkpoint-status |  |  | checkpoint | Ensure Weep hole is unobstructed and clean
checkpoint-status |  |  | checkpoint | In service leak test performed and passed
checkpoint-status |  |  | checkpoint | Fitting completion tag completed and applied to each fitting
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 12ccedc8-4744-502d-ab08-1b25c6742c08 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | c4c73636-0223-5d19-ac0e-2689acbaec07 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | da85a7fd-8986-5114-ac42-8428296ecf6a |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-flat |  |  | checklist | Cable Test Record |  |  |  |  | Yes | Cable Test Record | 8ae249cb-6ce1-4568-a862-5e9a96980967
checkpoint-status |  |  | checkpoint | Upload completed ITR scans
checklist-sectioned |  |  | checklist | ITR-E-09 Electrical Switch Rooms |  |  |  |  | Yes | ITR-E-09 Electrical Switch Rooms | 9f8f5557-78a5-4e6f-99ba-0da80a7c86ab
checkpoint-group |  |  | section | Electrical Switch Rooms
checkpoint-status |  |  | checkpoint | Substation construction finished
checkpoint-status |  |  | checkpoint | All floor, wall & ceiling penetrations sealed.
checkpoint-status |  |  | checkpoint | Danger, warning & resuscitation signs installed
checkpoint-status |  |  | checkpoint | All equipment installed
checkpoint-status |  |  | checkpoint | Lighting & general power installation complete
checkpoint-status |  |  | checkpoint | All earth busbars installed satisfactorily & connections tight
checkpoint-status |  |  | checkpoint | All telecommunication equipment is installed & operational
checkpoint-status |  |  | checkpoint | Smoke / Heat detectors installed (Including Vesda / Alarm Panel)
checkpoint-status |  |  | checkpoint | Substation fire alarm panel installed
checkpoint-status |  |  | checkpoint | HVAC equipment installed & operational
checkpoint-status |  |  | checkpoint | Illuminated exit signs installed & operational
checkpoint-status |  |  | checkpoint | Hand-held fire extinguishers installed with correct type available
checkpoint-status |  |  | checkpoint | All doors and locks operational (including emergency)
checkpoint-status |  |  | checkpoint | All keys available and handed to Commissioning E&I Superintendent
checkpoint-status |  |  | checkpoint | All safety equipment supplied – rubber mats, voltage sticks etc
checkpoint-status |  |  | checkpoint | Single line diagram detailing main power is fitted to wall
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 7876b6b6-d7a3-5a7b-848b-5fd29d2dcd51 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | ae46deac-d156-538b-8bec-09a4d7bc7a2d |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | fdaa0e24-45b1-5447-9f22-138ae8c94879 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-05 Low Voltage Cables |  |  |  |  | Yes | ITR-E-05 Low Voltage Cables | a341a464-2870-462f-9c9f-4ef8eae06171
checkpoint-group |  |  | section | Low Voltage Cables
checkpoint-status |  |  | checkpoint | Verify cable type, size, colour code and tags are in accordance with the Cable Schedule.
checkpoint-status |  |  | checkpoint | Check dressing/cleating.
checkpoint-status |  |  | checkpoint | Check cable for damage.
checkpoint-status |  |  | checkpoint | Check cable cores correctly identified and labelled.
checkpoint-status |  |  | checkpoint | Cable terminated with correct lugs and crimped with the correct die.
checkpoint-status |  |  | checkpoint | Check that cable phasing is correct and point-to-point each core for continuity.
checkpoint-status |  |  | checkpoint | Check Armour/Screen correctly made off.
checkpoint-status |  |  | checkpoint | Check armour continuity /earthing is maintained by the correct use of serrated washers and/or earth tags.
checkpoint-status |  |  | checkpoint | Glanding/Locknuts correctly installed.
checkpoint-group |  |  | section | Gland type - from:
checkpoint-status |  |  | checkpoint | Gland type - from:
text | 26063694-eb7b-5996-b9af-71ade89f5631 |  | textbox | Haz. Area Rating:
text | f9c01903-b621-5a91-b46d-2b064f16096d |  | textbox | Haz. Area Cert Details:
checkpoint-group |  |  | section | Gland type - to:
checkpoint-status |  |  | checkpoint | Gland type - to:
text | d3483dce-208f-5dca-98dc-44c91567e6d6 |  | textbox | Haz. Area Rating:
text | c8a228cb-e989-501f-9f76-dd5dc8a57618 |  | textbox | Haz. Area Cert Details.
checkpoint-group |  |  | section | Electrical Testing
checkpoint-status |  |  | checkpoint | IR Testing - LV Cables
label | 893ecca9-e995-5f25-b3b8-11762a45fc30 |  | note | (Test voltage 1,000 VDC for LV cables and 5KVDC for HV cables)
text | 0cb21c0f-fc99-5dbd-9a9c-29d90c51adfa |  | textbox | L1 – Earth
text | d2c51934-2d68-5d65-a492-3079936bb4fb |  | textbox | L2 – Earth
text | 0a1bc0f9-2b89-5a74-b4dd-db5d14fc91da |  | textbox | L3 – Earth
text | 3358822e-8087-5940-b1d3-00a8c838c0d9 |  | textbox | L1 – L2
text | 2538d36b-6786-5a6d-b54d-20ba0681a11b |  | textbox | L1 – L3
text | 0c535fa0-cfad-506a-9dc4-54be6289b843 |  | textbox | L2 – L3
text | 47120931-28c3-5e6a-a28b-858479a1f118 |  | textbox | N – Earth
checkpoint-status |  |  | checkpoint | IR Testing - Multiple conductor cables (Record lowest readings)
text | 5e9f3fc9-01f9-5a72-857d-985597983ca6 |  | textbox | Between Conductors
text | 3048a593-93f7-588f-a545-ceba34c578cf |  | textbox | Conductors to GND
text | ca3528b8-8d5c-5937-83cb-119a46504fa8 |  | textbox | Measure gland body continuity to earth. (Max 0.1 Ohm)
checkpoint-status |  |  | checkpoint | Confirm cable routing and segregation is correct.
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | eaa7bc82-38d4-5a5e-8551-070093a4a4a6 |  | textbox | Make:
text | 8984f313-9fd1-5cd1-90af-f64cb26c3ad8 |  | textbox | Model:
text | 33bc45bc-6425-576a-807a-45520bb5afa7 |  | textbox | Serial No:
text | ad5fa812-febf-5ee6-8f3a-60a60cf7d2c7 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 6d6f451a-546b-549a-8baf-cc7fee94ece0 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 93b67842-6502-5e77-9ae2-bee56986003d |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 6fb3d8eb-0c1a-533e-941d-345c956426e5 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-03 Distribution Board Installation |  |  |  |  | Yes | ITR-E-03 Distribution Board Installation | a556ee7b-30dd-4e2b-ab23-ae5a2094e5c3
checkpoint-group |  |  | section | Distribution Board Installation
checkpoint-status |  |  | checkpoint | Inspect for mechanical damage from freight and handling
checkpoint-status |  |  | checkpoint | Check mounting arrangement is adequate.
checkpoint-status |  |  | checkpoint | Check tag number is in accordance with Electrical Equipment List, Document No. and nameplate details correct.
checkpoint-status |  |  | checkpoint | Check IP rating is correct for location.
text | e57f85ab-a478-585a-99b4-91b0cbbbbb32 |  | textbox | IP Rating:
checkpoint-status |  |  | checkpoint | Ensure there is no visible damage to the equipment and all meters, LED indicators, switches and fittings are in good order.
checkpoint-status |  |  | checkpoint | Confirm main isolator operates with associated switches and auxiliaries
checkpoint-status |  |  | checkpoint | Confirm main isolator operates all active conductors
checkpoint-status |  |  | checkpoint | Confirm main isolator and sub-circuit MCB’s can be padlocked open if required.
checkpoint-status |  |  | checkpoint | Check number and rating of sub-circuits as per design and specifications.
checkpoint-status |  |  | checkpoint | Ensure different Voltage segregation is correct.
checkpoint-status |  |  | checkpoint | Heaters installed and functioning.
text | 8a658010-a428-51f3-aedc-9b255ef02bee |  | textbox | Record IR of heater circuit
checkpoint-status |  |  | checkpoint | Check equipment panel external and internal earthing connections are securely fitted and properly terminated on the cabinet protective earth bar.
checkpoint-status |  |  | checkpoint | Check internal cables properly terminated and labelled
checkpoint-status |  |  | checkpoint | DB properly labelled, sub circuit MCB correct rating and application
checkpoint-status |  |  | checkpoint | Check cable penetration is correct. (E.g. sealed correctly, correct size/type of glands)
checkpoint-status |  |  | checkpoint | Active, Neutral and Earth bar properly identified and labelled
checkpoint-status |  |  | checkpoint | DB legend card correct and updated, As-built
checkpoint-status |  |  | checkpoint | Confirm panel is readily accessible for inspection and maintenance.
checkpoint-status |  |  | checkpoint | Confirm panel is clean and tidy
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | de78ed0c-43b6-51ec-a4b2-ace72164d7fd |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | cf9180aa-a3e7-5832-82f2-a6df29a47861 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | e916bed3-f4e2-58e3-9f47-343cdf07f13a |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-16 Level Instrument Installation |  |  |  |  | Yes | ITR-I-16 Level Instrument Installation | b2f13e10-f7f1-4ced-b61a-63662b8240d2
checkpoint-group |  |  | section | Level Instrument Installation
checkpoint-status |  |  | checkpoint | Check Instrument Nameplate details are correct in accordance with the instrument index.
checkpoint-status |  |  | checkpoint | Level Instrument calibrated before installation (ITR-I-07 Instrument Calibration)
checkpoint-status |  |  | checkpoint | Level instrument mounting equipment is adequately sturdy and correct materials used
checkpoint-status |  |  | checkpoint | Bolts and studs are to site specification
checkpoint-status |  |  | checkpoint | Ensure location and tapping point is verified per relevant drawings
checkpoint-status |  |  | checkpoint | Ensure gasket and studs are used as per specifications
checkpoint-status |  |  | checkpoint | Verify contact type sensor probes are installed without any resistance
checkpoint-status |  |  | checkpoint | Verify antenna/source are installed correctly
checkpoint-status |  |  | checkpoint | Ensure display is easily readable by operations and access is easy for technicians
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 556bef54-8365-5d23-bdfa-0063642d908a |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | e32fe667-a2be-56d2-b4d8-6d359aa76461 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 644ce9b2-4140-5a1c-b322-589b295c16c5 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-08 Instrument Pre-Commissioning |  |  |  |  | Yes | ITR-I-08 Instrument Pre-Commissioning | c6211d8a-e983-4bcc-b859-902af02c9975
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Verify transmitter loop connection - Remove wre on transmitter and confirm at Control System interface
checkpoint-status |  |  | checkpoint | Relevant individual control system/ESD loops have been checked and test sheets completed
checkpoint-group |  |  | section | Analogue Input:
checkpoint-status |  |  | checkpoint | Analogue Input:
text | bdcec23a-b385-5122-9cef-2ceeffe8ebdb |  | textbox | Input range & units:
text | 2b59f6cb-3417-5fcd-97ae-8502f22393f9 |  | textbox | Indication range & units:
checkpoint-status |  |  | checkpoint | 0% Rising
text | 3c71d7ca-f062-51cf-9cb0-0c055c446134 |  | textbox | Input Signal:
text | ea1086e8-bd32-5f2d-b943-c750c07dfd6d |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 25% Rising
text | b3b2f7b2-fda0-524d-a5f8-1192e128bc84 |  | textbox | Input Signal:
text | 324c4405-7195-549c-958e-4e7ed04f8554 |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 50% Rising
text | 9fbf9150-7e21-52a5-b0b3-ed07344f7732 |  | textbox | Input Signal:
text | e9672ea6-1e4d-555d-a037-3578792030d5 |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 75% Rising
text | d0508100-40df-5d4b-a76f-75959f07bae1 |  | textbox | Input Signal:
text | 900f05de-31fa-5e93-ba26-e2ac8edf50fb |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 100% Peak
text | c2d463e5-6342-574e-84f2-af74ef80b13d |  | textbox | Input Signal:
text | f64fa6b7-4988-539b-aa5e-c2e50df47a1e |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 75% Falling
text | 3bba6732-2541-5d35-8af9-687d29cf5575 |  | textbox | Input Signal:
text | 01aade3c-2d29-56f9-abeb-299c2dc0d864 |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 50% Falling
text | 1b56142c-dba2-529f-8077-4db1376ce8fc |  | textbox | Input Signal:
text | f5f068ac-d1b4-5409-94e1-97907e6e4991 |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 25% Falling
text | 787c979c-9986-510b-a0d1-c1cb781e3d75 |  | textbox | Input Signal:
text | 5ba884d1-d2c1-59b4-a281-40d89b37e201 |  | textbox | Control Interface Indication:
checkpoint-status |  |  | checkpoint | 0% Falling
text | 3ccb3332-dcf1-550f-ae85-519f46fa1a01 |  | textbox | Input Signal:
text | 2fd4460c-96ca-572e-abdd-dc317659dd24 |  | textbox | Control Interface Indication:
checkpoint-group |  |  | section | Digital Input/Analogue Alarm Trip Points
checkpoint-status |  |  | checkpoint | Alarm Lo:
text | 78eb4bd4-d125-59d9-8ba1-5b10d7b2ddc0 |  | textbox | Alarm setting
text | 95678259-89f7-552a-848c-8fa35d455a88 |  | textbox | Measured Alarm Point
text | bc0e27f3-1e61-5e7a-b2bc-6dc0a461b323 |  | textbox | Filter/Time Delay
text | 32c0d785-7ac3-5098-aff6-4baa1424af63 |  | textbox | Result
checkpoint-status |  |  | checkpoint | Alarm Lo-Lo:
text | d95018b2-8d7f-5689-9345-097d00b4ab82 |  | textbox | Alarm setting
text | 1a53d517-8732-54a0-80f3-9a2f207433fb |  | textbox | Measured Alarm Point
text | 4efa05f8-7513-5767-a0c0-73424a185111 |  | textbox | Filter/Time Delay
text | 8ad77f0f-41b9-5c5b-a571-3adfd63323f2 |  | textbox | Result
checkpoint-status |  |  | checkpoint | Alarm Hi:
text | 0e845567-6b7d-56b5-8dd9-fb84fea1d68a |  | textbox | Alarm setting
text | 16d16e7d-ea2d-557f-8997-550deff5b87f |  | textbox | Measured Alarm Point
text | 05d751d9-5b5b-5c3b-8384-a8f5fa17dd99 |  | textbox | Filter/Time Delay
text | 20a8b439-fb5a-564b-8dcf-52b6d81aa7fb |  | textbox | Result
checkpoint-status |  |  | checkpoint | Alarm Hi-Hi:
text | c50d0874-8e8e-5555-86d0-aa483de00a77 |  | textbox | Alarm setting
text | a8a5ff1d-89fa-5124-bcaf-ed62b3cf3d09 |  | textbox | Measured Alarm Point
text | 470fc1df-2542-5a3d-a1c4-8f8739c46876 |  | textbox | Filter/Time Delay
text | 77179e8b-300f-5cf8-861b-3fedd203e778 |  | textbox | Result
checkpoint-status |  |  | checkpoint | Control loop set points correct:
text | 6afbf178-5893-55d6-9265-86f7dd8897d6 |  | textbox | Set Point 1:
text | 47d05b2d-c2c0-5c9d-bb32-362d063ff443 |  | textbox | Set Point 2:
text | 650ff8be-92ef-55a4-9cd2-e8174d195fd7 |  | textbox | Set Point 3:
text | fd6412da-5dda-52ad-bd88-f371ececc131 |  | textbox | Set Point 4:
checkpoint-group |  |  | section | Startup, Shutdown and Override functions
checkpoint-status |  |  | checkpoint | Control system graphic display
checkpoint-status |  |  | checkpoint | Control system point display
checkpoint-status |  |  | checkpoint | ESD graphic display
checkpoint-status |  |  | checkpoint | Alarm Recording and Text
checkpoint-group |  |  | section | Additional checks
checkpoint-status |  |  | checkpoint | Control system display and alarms are correct as per control functions
checkpoint-status |  |  | checkpoint | Transmitter fail direction and burnout are to spec (Upscale/Downscale)
checkpoint-status |  |  | checkpoint | Switch action verified, including power loss
checkpoint-status |  |  | checkpoint | Drawings, documents and As-Builts scanned and attached
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | e0eae972-65a1-536e-b338-f196d9ff0f5c |  | textbox | Make:
text | b396c580-bb60-5d90-8532-20314b024611 |  | textbox | Model:
text | af340773-4861-5316-b763-ef6949f49b59 |  | textbox | Serial No:
text | 141c7148-8990-57df-9e06-21ba50113488 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 08467219-820d-5879-9ff2-80c7bd029a9e |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | ed65c19c-348f-5f0b-9b74-4c9b8304426b |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | d4db2cbd-748f-5121-9426-25d0f2833a75 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-E-07 Junction Box |  |  |  |  | Yes | ITR-E-07 Junction Box | c72b4deb-6522-44e7-8516-243355da7c3a
checkpoint-group |  |  | section | Junction Box
checkpoint-status |  |  | checkpoint | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule.
checkpoint-status |  |  | checkpoint | Check holding down/mounting arrangement and accessibility for maintenance.
checkpoint-status |  |  | checkpoint | Check for mechanical damage
checkpoint-status |  |  | checkpoint | Check that Junction box is correctly earthed.
text | 4d632221-ca71-5637-b327-4a2764d08d8c |  | textbox | Test and confirm the earth resistance between junction box and local earth system is <1.0 Ohm
checkpoint-status |  |  | checkpoint | Check all internal cabling and wiring is correct and tight, including segregation (e.g. IS to NON IS circuits).
checkpoint-status |  |  | checkpoint | Check cables for Voltage segregation. Ensure clearance, labelling, colour coding is to standard
checkpoint-status |  |  | checkpoint | Incoming/Outgoing cables are glanded and terminated correctly
checkpoint-status |  |  | checkpoint | Spare entries plugged correctly.
checkpoint-status |  |  | checkpoint | Check internals for cleanliness
checkpoint-status |  |  | checkpoint | All cover bolts and gasket undamaged
checkpoint-status |  |  | checkpoint | Verify ingress protection is suitable for area (IP rating)
text | b450d3d9-23fb-58dc-9793-5793b08806f5 |  | textbox | IP Rating:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | fe7f6604-030d-5c79-99d9-48850abe57f2 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | e84eb76f-c82d-58b0-bc86-f2e96ebfc391 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 97f2f780-7ab4-5423-b5f3-956e17fb1785 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-01 Fire and Gas Detection Alarms |  |  |  |  | Yes | ITR-I-01 Fire and Gas Detection Alarms | c856c2c7-e452-4580-afa5-21fef04081ae
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Checklist items
text | eb8986b7-ce71-5632-abe7-3846c4901287 |  | textbox | Manufacturer
text | cafb3cb0-c405-5e26-aeb6-428e9ef8f894 |  | textbox | Make and Model
text | e614dbe7-341d-57f3-a5c7-fc63aac351c0 |  | textbox | Type
checkpoint-status |  |  | checkpoint | Labelling/Number correct
checkpoint-status |  |  | checkpoint | Component & Type / Model correct
checkpoint-status |  |  | checkpoint | Cable connection & termination correct
checkpoint-status |  |  | checkpoint | Mechanical damage
checkpoint-status |  |  | checkpoint | Glanding condition
checkpoint-status |  |  | checkpoint | E.O.L Installation
checkpoint-status |  |  | checkpoint | Installation of Test tubing
checkpoint-status |  |  | checkpoint | Location correct
checkpoint-status |  |  | checkpoint | Detection Path Clear
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Tag No. Correct
text | fa1f7092-2b86-56bd-b488-75a56c9691da |  | textbox | Tag No:
text | c5e3797a-0b6f-538c-b140-911809bad642 |  | textbox | RX Tag No:
checkpoint-status |  |  | checkpoint | Area Classification correct
text | e352bc40-dfb4-5048-ad2c-52548bc9b4c2 |  | textbox | Hazardous Area Certificate:
text | d4cb020d-8553-5cc5-b846-fdd009aaef24 |  | textbox | Detector Type:
text | 60a2ebca-3eec-5b3e-bdc8-8203bfe83249 |  | textbox | Gas Type:
checkpoint-status |  |  | checkpoint | Body Material Correct:
checkpoint-status |  |  | checkpoint | General Condition Satisfactory
text | e7ef017e-139a-5b0d-a345-fe7f0aeb287d |  | textbox | Supply Voltage:
text | 7f1b7641-c40f-51f7-8fbd-259538c97903 |  | textbox | Output Signal:
checkpoint-group |  |  | section | Functional Check
checkpoint-status |  |  | checkpoint | Self Test
checkpoint-status |  |  | checkpoint | Alarm Operation
checkpoint-status |  |  | checkpoint | Fault Relay Operation
text | 34691dfe-9b40-57f9-a997-7630745ee75d |  | textbox | Measured output (clear path)
text | a77ad010-e992-50d0-a412-e673c6fb2d97 |  | textbox | Measured output (blocked path)
text | 7710dc52-34d2-55eb-97b1-2bf38c50d53d |  | textbox | Measured output (filter in place)
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 14d30ff8-063a-5cfa-9c41-b380314cfb2e |  | textbox | Make:
text | 8057e873-be3c-594b-b794-46130e75be55 |  | textbox | Model:
text | 5a2b310f-886d-5067-b043-89c25250896a |  | textbox | Serial No:
text | fb65ce49-a01f-5e20-b621-2cb48100412d |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 6445f52c-9f27-5c52-8acc-1148fedf4102 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 9033bf3c-4ee1-5e9f-954f-16cfa34f8846 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 9869af8c-a7f2-54c4-aa35-e9ebb3023f3f |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | JHA - Job Hazard Analysis |  |  |  |  | Yes | JHA - Job Hazard Analysis | cd1472ae-7b0c-443e-90dd-339b59b740fc
checkpoint-group |  |  | section | Job details
checkpoint-status |  |  | checkpoint | Job details
date | 34016a81-ce4b-5bc1-9e6a-8fb8a0beb8bc |  | date | Date:
text | 7285eb17-5ba1-538e-a15d-8e702cb4b486 |  | textbox | Permit No.
text | 66a9b5eb-f25a-5a69-8219-7617fc921c57 |  | textbox | Job No.
text | bf0438f0-6fd0-5904-9cbd-245f0bc0518b |  | textbox | Site
text | 0132f4fe-224c-5dc2-83e3-e6514f0e237e |  | textbox | Activity Location
text | 40c69886-9fc9-52ac-bd20-39c4c1413309 |  | textbox | Asset:
text | b46f7a32-34ee-5969-8dcf-1e87e687b700 |  | textbox | Work Details:
checkpoint-group |  |  | section | Prompts for Hazards - Mark all that apply.
checkpoint-status |  |  | checkpoint | Prompts for Hazards - Mark all that apply.
button | 8ea5ffe4-66db-5188-8532-34f1dfa6d1fd |  | button | Sparks/Open flame | YES,NO
button | a72b235e-b4d0-5cec-9c67-7a2bc09355fb |  | button | Disabled safety device(s) | YES,NO
button | 8378f986-971d-5927-a85b-32de12d48029 |  | button | Uneven surfaces | YES,NO
button | 49a7241e-d866-5a18-acef-d732f89cef62 |  | button | Fatigue, over-exertion | YES,NO
button | 573c8305-310f-5bad-8b0e-a78dec1db8f6 |  | button | Crane movements | YES,NO
button | b13fe4d9-3971-52e6-b0a1-9ac1ed0a9232 |  | button | Moving/Rotating parts | YES,NO
button | 3c760151-6b21-5866-83cd-bf56c1898f55 |  | button | Remote area, working alone | YES,NO
button | dbc9058c-e6f6-557a-84e4-188082fe9c23 |  | button | Conflicting work/SIMOPS | YES,NO
button | 6187c085-30f0-5fcd-b7d0-96237b5c6deb |  | button | Electrical arc flash | YES,NO
button | 6a6316df-4fb3-5ff5-9ee5-23167166e825 |  | button | Sharp objects/materials | YES,NO
button | b41bf584-1386-55c6-870d-87d4e0db7221 |  | button | Restricted/Difficult Entry/Exit | YES,NO
button | a817c35b-80cd-588f-843c-473736b8ef17 |  | button | Overhead obstacles | YES,NO
button | 41b4ead6-4253-5dd1-ba1b-1537986b3537 |  | button | Ignition sources (other) | YES,NO
button | d7019208-a612-5e07-b662-e9f7b5aadb60 |  | button | Access/Egress | YES,NO
button | 93c2a20d-8226-5cf3-9900-72be3ffeb8fd |  | button | Water body | YES,NO
button | 0719a1d0-31f4-5a98-9afc-e5827ed85a78 |  | button | Live equipment | YES,NO
button | b7607459-6c1e-56ab-8d10-c27f29168851 |  | button | Slippery surfaces | YES,NO
button | 5a649775-f44f-504c-935a-3a0d84eecc6c |  | button | Suspended loads | YES,NO
button | 8bdf7f60-5488-5c1a-8e12-3a4881de26b3 |  | button | Hazardous substances (chemicals) | YES,NO
button | b68ec512-06d2-5015-bdf0-d58ddfefff1d |  | button | Use of non-intrinsically safe equipment | YES,NO
button | d0416a2f-8eb4-5502-bb8c-908d88022601 |  | button | Weather extremes | YES,NO
button | 98d51133-56b9-5e01-bfeb-b27fda221b81 |  | button | Moving vehicles | YES,NO
button | be47a869-8282-5e6a-8796-6b2a4e7891b7 |  | button | Task related noise | YES,NO
button | 2aff7931-c11e-5a89-ac28-74865e4b5046 |  | button | Engulfment | YES,NO
button | b1c955bb-d670-5feb-a299-20d415be3058 |  | button | General waste | YES,NO
button | 99afbc2e-a227-59ac-a3b5-0925b4464220 |  | button | Hazardous waste | YES,NO
button | 1ca4c230-b02c-59ce-9a23-e2be1f750286 |  | button | Hazardous/toxic substance, fumes, gas | YES,NO
button | f3592d7b-b86f-5033-ba51-3d69fd98749e |  | button | Flammable materials - Gas, liquids, solids | YES,NO
button | 34e00b8e-83f7-5eb7-9dc3-aa6f1eba4cdf |  | button | Reduced visibility, lighting | YES,NO
button | bb4ddb86-f120-5b74-8d31-b58746070793 |  | button | Electricity | YES,NO
button | ae6220db-e03a-5730-82b9-c57f3f5f6dec |  | button | Static electricity | YES,NO
button | 7371f386-5134-5ea6-a667-d926d93bd122 |  | button | Work at height | YES,NO
button | 99fec4fe-5363-5268-bd48-8a7c200f81b2 |  | button | Underground services | YES,NO
button | ff3c7012-7ca2-5d4e-a54e-2d0f7031f866 |  | button | O2 Deficiency/Excess | YES,NO
button | 9c0053ce-6f9e-5a7e-bfe6-713a99645c22 |  | button | Temperature extremes | YES,NO
button | 7e884e46-9a82-57f9-8287-91a38eab0d24 |  | button | Heavy objects | YES,NO
button | 91c19ee6-0cba-5769-88b6-0582b4717477 |  | button | Radiation | YES,NO
button | af23505c-2a83-5bb8-b20e-84170f536a9b |  | button | Potential energy - Tension/Compression | YES,NO
button | 06bb6202-c234-5b89-94f5-b4b0ccd45c78 |  | button | Flying particles/Dust/Objects | YES,NO
button | fb5d0a7a-4b94-5793-8b1c-6b847956554b |  | button | Vehicle entry | YES,NO
button | d6871219-3685-59ea-b0bf-4c3df0270ea7 |  | button | Exposure to process temperatures. | YES,NO
checkpoint-group |  |  | section | Prompts for Initial Consequences - Mark all that apply
checkpoint-status |  |  | checkpoint | Prompts for Initial Consequences - Mark all that apply
button | 1dfc3c74-1dcb-5e12-9dc6-5cfbf38026a1 |  | button | Falling/Dropped objects | YES,NO
button | 1e8de455-c0c5-5697-92af-83a26ba50b5d |  | button | Fall from height | YES,NO
button | 47a273d9-f9b2-5f61-98ff-a01a6d6077ed |  | button | Trip/Slip/Fall | YES,NO
button | 6105e2fc-58d1-58c8-9066-d9713e03fac6 |  | button | Gas release | YES,NO
button | 7df5e50f-cf78-571b-a51d-98c49d2d172c |  | button | Pressure release | YES,NO
button | c4d3371a-7db5-5169-b3b6-13221d76a4c4 |  | button | Struck by object | YES,NO
button | 722d7801-a45d-5397-93aa-83420d2a9deb |  | button | Exceeding tool limits | YES,NO
button | a441d870-cdae-50fa-8d38-eafd2bd307a9 |  | button | Overloading people | YES,NO
button | 52a06ac1-358d-5dbc-9c73-7b2cbe382ccc |  | button | Unplanned shutdown | YES,NO
button | aab37dd2-1ca5-5f6c-8c93-bd245a5cd4d2 |  | button | Exposure to O2 deficiency/excess | YES,NO
button | ebcedc0d-5ae1-5162-8025-bc541a11fdf1 |  | button | Exposure to hazardous substance | YES,NO
button | 1be8b4a7-1e34-5707-bb1d-080817f5d16f |  | button | Entanglement | YES,NO
button | 0ec28a3b-d8d4-5a50-935c-3595c8494778 |  | button | Flying objects | YES,NO
button | bd81598d-950f-5ba9-bd39-0d884cdba59b |  | button | Loss of control | YES,NO
button | 7af2c4c5-e8ff-5ccc-8f3d-27ca6c300359 |  | button | Loss of containment | YES,NO
button | 64fa750c-0418-5978-acc3-c6f2241b5a58 |  | button | Excess exposure to Emissions, dust, fumes, noise, fibres, heat | YES,NO
button | 85d1ee2d-9aa6-5e83-a8f9-f326e9b8bf08 |  | button | Loss of structural integrity | YES,NO
button | 36fbfa87-d8c0-5174-bf00-ca771fb1ef2c |  | button | Equipment failure | YES,NO
button | 392ec03a-e78b-59a6-95e8-b03af8d8a470 |  | button | Uncontrolled ignition source | YES,NO
button | 3555cd9d-efac-5313-94d1-31b7cafa1c2c |  | button | Collision | YES,NO
button | 382b8a04-089e-5182-8d51-b19c3863d7f3 |  | button | Ignition/Fire | YES,NO
button | e4b7235f-0b28-5379-8681-75e256db3182 |  | button | Back strain/Injury | YES,NO
button | f027552a-04ea-5c78-993d-c96c368c5f1f |  | button | Burns | YES,NO
button | 783ef883-42c9-5830-bda2-68a7e56366ea |  | button | Heat exhaustion | YES,NO
checkpoint-group |  |  | section | Initial controls - Mark all that apply.
checkpoint-status |  |  | checkpoint | Initial controls - Mark all that apply.
label | fcb61cd0-b170-5a63-81fe-7e704c2dc1cc |  | note | People controls | YES,NO
button | 74965bac-4643-57ec-8e34-e0ec1be9d626 |  | button | Safety/Fire watch person | YES,NO
button | d661603f-4fa2-52b7-8fd3-0cdd37d911e4 |  | button | Barriers/Flagging | YES,NO
button | a2fdfd14-2fe2-5f7d-a6ac-aa681cdef672 |  | button | Warning signs | YES,NO
label | 51cd6324-6b84-545d-9e45-5756d773a0bd |  | note | Equipment controls | YES,NO
button | 3198edc5-4663-59fa-bd2c-ddbbd670d918 |  | button | Master tags and locks | YES,NO
button | ec099e05-47ba-525e-b6ab-bbf22eee1d6b |  | button | Scaffolding for access | YES,NO
button | d744ee3d-1ea8-5240-959c-1a6431c47c32 |  | button | Radio communication | YES,NO
label | bcf1fddb-f3d7-5a96-8d31-4894fdd89ed3 |  | note | Environmental controls | YES,NO
button | df548ec0-4955-564c-b987-0d55447efb43 |  | button | Ventilation | YES,NO
button | 860f361b-4999-5d37-9c68-64cce7aa508e |  | button | Lighting | YES,NO
button | 386d793e-13b5-54b3-97dd-774a04c7094e |  | button | Gas Testing | YES,NO
label | 602ed591-0f90-543d-b3d9-2f9056d39b82 |  | note | High risk controls | YES,NO
button | 46f43f95-b91b-5407-b68b-1cf2cbb13c64 |  | button | WSCS Work permit | YES,NO
button | 4bc61d7d-89e8-5799-967b-ce993eaad6c8 |  | button | WSCS Certificates | YES,NO
button | 937e638f-3c2d-561b-845e-8247765ccc79 |  | button | Critical lift/Fall protection plan | YES,NO
button | d4e48c7c-b92b-505c-9645-d224112e2129 |  | button | Specialised PPE | YES,NO
button | 24424a7f-2e53-594f-ad78-2ab6e8002fe2 |  | button | Spill kit | YES,NO
button | da560098-5983-50ba-b00c-a387edea8f6f |  | button | Fire extinguisher | YES,NO
checkpoint-group |  |  | section | Signatures
checkpoint-status |  |  | checkpoint | Signatures
text | 99f5593d-dc20-514b-9007-dcf732b02838 |  | textbox | Applicant name
holdpoint |  |  | signoff | Applicant signature
checklist-sectioned |  |  | checklist | ITR-I-04 Valve & Ancillaries (Pre-Installation) |  |  |  |  | Yes | ITR-I-04 Valve & Ancillaries (Pre-Installation) | d002b0c2-eba7-4772-8121-76f7824aa55d
checkpoint-group |  |  | section | Equipment
checkpoint-status |  |  | checkpoint | All equipment checked against correct revision of Instrument index for Manufacturer, Type and Model No.
checkpoint-status |  |  | checkpoint | Equipment checked for additional items as applicable
checkpoint-group |  |  | section | Valve
checkpoint-status |  |  | checkpoint | Valve
text | fb9bd626-f656-5ba5-8c56-bf344c4c74cd |  | textbox | Size:
text | 247c53e6-611f-5726-b919-64778935440f |  | textbox | Flange type:
checkpoint-status |  |  | checkpoint | Material certification correct
checkpoint-status |  |  | checkpoint | Trim material correct
text | e45ba072-bfdd-5e99-b5a0-bdfa173536a3 |  | textbox | Rating:
text | 52deb85b-3eb1-5405-b6fd-a88d79681185 |  | textbox | Service:
checkpoint-status |  |  | checkpoint | Body material correct
text | 4f3e4e9c-1aec-52c4-8a2b-ef284c2b107a |  | textbox | Leakage class:
checkpoint-group |  |  | section | Actuator
checkpoint-status |  |  | checkpoint | Actuator
text | 0aa17bc5-3123-53fc-be40-297b75032765 |  | textbox | Input range:
checkpoint-status |  |  | checkpoint | Failure action
checkpoint-status |  |  | checkpoint | Hand wheel operation correct
checkpoint-group |  |  | section | Positioner
checkpoint-status |  |  | checkpoint | Positioner
text | d47f7041-13e0-5c15-bdb0-42d86d74aef9 |  | textbox | Signal range
text | ca67a533-c76b-57a6-942b-ed13d0b2bb8e |  | textbox | Output range
checkpoint-group |  |  | section | I/P Converter
checkpoint-status |  |  | checkpoint | I/P Converter
text | d545d5dd-bdf2-565b-a40f-00ebf2266ff0 |  | textbox | Signal range
text | 92d25f6e-dbfe-5310-ad77-716b1fbfd43b |  | textbox | Output range
checkpoint-group |  |  | section | Filter/Regulator/On-Off Valve
checkpoint-status |  |  | checkpoint | Filter/Regulator/On-Off Valve
text | a3cb4600-9dcb-543b-906e-4a999c2dcc40 |  | textbox | Range
text | 116ed3e9-653e-514a-819e-3242fa8f3d91 |  | textbox | Pressure setting
checkpoint-status |  |  | checkpoint | Stroke Time
text | ead1f5a1-e0fe-59f5-bdf6-aa02d8c096c4 |  | textbox | Open
text | f054c6bc-f736-5f48-9584-03dc24d06d03 |  | textbox | Close
checkpoint-status |  |  | checkpoint | Open/Close times conform to commissioning specifications
checkpoint-group |  |  | section | Fail Action
checkpoint-status |  |  | checkpoint | Fail Action
select | 696df441-ed5e-5e9e-9884-3c546deff5ce |  | dropdown | Electrical Fail Action | FO, FC, FL
select | 1e473e04-dc97-571e-882e-1a41e1aaa141 |  | dropdown | Motive Force | FO, FC, FL
checkpoint-group |  |  | section | Valve Field Calibration and Hysteresis Check
checkpoint-status |  |  | checkpoint | Confirm test equipment is within calibration period prior to testing
label | 64f2ac1c-b0ef-5d6a-b141-dbdbe6dd964e |  | note | Valve to be calibrated according to manufacturer's data sheet and to be within quoted accuracy.
label | 03da5e96-694a-5184-9830-ebf7e3211f81 |  | note | Check at the following range percentages; both rising and falling 0%, 25%, 50%, 75% and 100%
checkpoint-group |  |  | section | Proximity Detectors
checkpoint-status |  |  | checkpoint | Open switch set
checkpoint-status |  |  | checkpoint | Open switch mode setting correct
checkpoint-status |  |  | checkpoint | Closed switch set
checkpoint-status |  |  | checkpoint | Closed switch mode setting correct
checkpoint-status |  |  | checkpoint | Electrical connections correct
checkpoint-status |  |  | checkpoint | Electrical certification correct
checkpoint-group |  |  | section | Solenoid Valve
checkpoint-status |  |  | checkpoint | Operation correct
checkpoint-status |  |  | checkpoint | Electrical connections correct
checkpoint-status |  |  | checkpoint | Electrical certification correct
text | f203c51c-5934-590b-85cb-d544c96b6f31 |  | textbox | Voltage:
checkpoint-status |  |  | checkpoint | Pneumatic connections correct
text | 9ddd3586-6005-5fd1-9f3e-83dce088d648 |  | textbox | Pneumatic pressure
checkpoint-group |  |  | section | Pilot Valve
checkpoint-status |  |  | checkpoint | Pneumatic connections correct
checkpoint-status |  |  | checkpoint | Operation correct
checkpoint-status |  |  | checkpoint | Action/Lockup
checkpoint-group |  |  | section | Hydraulic Actuator
checkpoint-status |  |  | checkpoint | Hydraulic Actuator
text | a89eba14-e8e2-5062-909f-58603d0ef522 |  | textbox | Working pressure
text | 8d327e59-6fe5-51e8-80d4-aa285c5ecdf8 |  | textbox | Manifold pressure
text | 49ea524d-f4f2-5219-b8f0-6070e25d6004 |  | textbox | Fluid type
checkpoint-status |  |  | checkpoint | Hydraulic connections correct
text | ce90d8ae-1698-5923-9056-67ad82606072 |  | textbox | Regulator pressure setting
checkpoint-status |  |  | checkpoint | Pilot operation correct
checkpoint-group |  |  | section | Accumulator
checkpoint-status |  |  | checkpoint | N2 Charge required
text | 0e5299d6-2d97-5722-a7e3-3ed098643b51 |  | textbox | N2 Pre-charge pressure
text | c11d673d-8544-539c-b5f5-f6f5bf5d8eb4 |  | textbox | Pressure switch setting
text | 02fbc76e-07be-554c-ba79-400236e351e2 |  | textbox | Working pressure
text | 7e26ee7a-146d-5004-a7d6-0001e93cfedb |  | textbox | Output range
checkpoint-status |  |  | checkpoint | Volume tank & check valve installed correctly
checkpoint-group |  |  | section | Electric Actuator
checkpoint-status |  |  | checkpoint | Electric Actuator
text | d1a0fed7-624d-51e4-b161-d8f1da02c8fd |  | textbox | Voltage:
text | 52526b12-8c32-566a-9dc8-11bc432e65e2 |  | textbox | Electrical certification correct
text | d5bd6de8-4872-51ad-a8e9-a28e77be9d4a |  | textbox | Electrical connections correct
text | 48606c32-9078-5936-91ce-9ccee773ed01 |  | textbox | Remote operation correct
text | ccd81a66-e563-58d1-98d0-ed1de9d574c0 |  | textbox | Local hand operation correct
text | e2975089-2f7d-51ff-a93e-6da3df2154ff |  | textbox | Torque switches and travel stops set
checkpoint-group |  |  | section | Miscellaneous Equipment
checkpoint-status |  |  | checkpoint | Miscellaneous Equipment
text | b0c23e3b-6aa0-575c-8250-6c13231bb5eb |  | textbox | Description
text | 3106e401-23c6-53a2-9772-69f201eeccd7 |  | textbox | Manufacturer
text | b68c7ffc-bbdb-55f3-858b-83e006b0c8a0 |  | textbox | Model No:
text | ed476632-c0d4-5bc4-8754-b3cc167eaaa7 |  | textbox | Serial No:
text | 068ae041-bb4d-5e46-b19f-b3d6683cfe30 |  | textbox | Range:
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | 6205f8eb-2dfe-5cba-9c74-010808efbe10 |  | textbox | Make:
text | c6def17d-4385-5851-be0b-db8d89247b67 |  | textbox | Model:
text | 02944971-0f18-538c-81fb-f62fc4b11d3c |  | textbox | Serial No:
text | 8f194aea-c6c6-511b-8931-23311ac1da62 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 0960c32f-c3af-5238-b24b-06746f71e397 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 07110c6e-ec51-530b-9d19-2343534ec954 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | b431aa02-5e79-5560-a366-116a19b87766 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-07 Instrument Calibration |  |  |  |  | Yes | ITR-I-07 Instrument Calibration | d3bef762-12d1-4843-b7d3-1c04d4740840
checkpoint-group |  |  | section | Required Data
checkpoint-status |  |  | checkpoint | Required Data
text | 6efb8abb-38ac-56d8-8ffb-3612b4a6b30b |  | textbox | Type and Size:
text | c108e056-2c25-5b47-bd79-b6db053a1042 |  | textbox | Make:
text | 9e9114a0-0bf3-5d75-9d95-504c51cb4144 |  | textbox | Serial No:
text | 577ece26-f0d9-59d5-a878-cc8c4691f210 |  | textbox | Instrument Type:
text | 2d4d116e-82d9-5807-aeb0-de575b9ad20d |  | textbox | Instrument designation/equipment no
text | 52898e62-c9ce-5493-9ed3-8350e8e46e1a |  | textbox | Calibration interval
text | f4ce403b-a451-57ba-9b8e-a6fe6ec6f5c4 |  | textbox | Calibration method
text | 084a88c2-d443-5f23-b08d-3ada69908325 |  | textbox | Calibrated at
checkpoint-group |  |  | section | Instrument Power Supply
checkpoint-status |  |  | checkpoint | Instrument Power Supply
select | c3cd2107-35bb-5d18-8d89-b80fe0cac6d5 |  | dropdown | Supply type | VAC, 2 Wire DC, Other, None
text | c9a81310-7cda-5b09-9345-a75da3870931 |  | textbox | Supply value:
checkpoint-status |  |  | checkpoint | Calibration sheet completed and attached below
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | b41831cf-72ca-5bac-9175-4dc08c123772 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 0ff0367a-a81c-5689-8307-5a017d290deb |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 78f9e8dd-087f-5afd-b5ec-c7206fd93daf |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-02 Instrument Tubing Installation |  |  |  |  | Yes | ITR-I-02 Instrument Tubing Installation | e7a04072-8a94-4d31-b2f9-34c793649b3e
checkpoint-group |  |  | section | Information
checkpoint-status |  |  | checkpoint | Information
text | 1093a7dd-d1c8-5f8b-a73d-cb1d013ccd49 |  | textbox | Equipment:
text | 359859db-ba33-5ad8-998f-efadfb305e57 |  | textbox | Location:
text | 29c018b3-43e1-5350-ab78-06419aac81b1 |  | textbox | Tag Numbers:
text | e9c157d8-6057-5131-af49-cffbf2ad28a9 |  | textbox | Process Fluid:
text | 6dddc96b-15bf-505c-befe-0309c29c6fbb |  | textbox | Reference Drawings:
text | 26e70412-dbae-52aa-9caa-d16786c0d71b |  | textbox | Max Process Pressure:
text | ab376e79-647d-516e-9ba7-b53875724128 |  | textbox | Max Supply Pressure:
text | 133e2515-7d10-590f-81ce-0c7f1f6ce185 |  | textbox | Max Signal Pressure:
text | 9cbdb052-1472-5e42-9339-6e14d5211dd4 |  | textbox | Process Temperature:
text | 13fbfd41-6c64-5b36-92c4-343e793a73bb |  | textbox | Other:
button | b5be2b61-5558-5e20-b82b-303ec1e37653 |  | button | Inspection | Yes, No
text | 3b95a0dd-2aee-53d1-b8ee-e14538c38b47 |  | textbox | Percentage of installed items to be checked:
checkpoint-group |  |  | section | Checks Pre-Installation
checkpoint-status |  |  | checkpoint | Tubing connection drawings and details available
checkpoint-status |  |  | checkpoint | Client site specific changes noted, agreed and sketched
checkpoint-status |  |  | checkpoint | Tube material type, size, gauge and standard confirmed and available
checkpoint-status |  |  | checkpoint | Tube fitting size and type confirmed and available
checkpoint-status |  |  | checkpoint | Torque wrench - Current calibration certificate
checkpoint-group |  |  | section | Checks During and Post-Installation
checkpoint-status |  |  | checkpoint | Correct thread compatibility and engagement
checkpoint-status |  |  | checkpoint | Correct thread tape and sealant used on fittings
checkpoint-status |  |  | checkpoint | Check fitting ferrule orientation and confirm prior to connection
checkpoint-status |  |  | checkpoint | Tube installation is in compliance with the client specification.
label | b805c1aa-79b2-5e57-bfe3-c00f0944e4f5 |  | note | (Supports, bracketry, slope, expansion, vibration, access, cables)
checkpoint-status |  |  | checkpoint | Tube bent correctly, sufficient straight section into fitting
checkpoint-status |  |  | checkpoint | Tube cut clean and straight, de-burred, reamed, and blown through
checkpoint-status |  |  | checkpoint | Depth insertion tool used; witness mark visible at all stages of process
checkpoint-status |  |  | checkpoint | Tube fitting hexes marked to ensure correct swage tightness
checkpoint-status |  |  | checkpoint | Random check with No-Go gap gauge
checkpoint-status |  |  | checkpoint | In service leak test performed and passed
checkpoint-status |  |  | checkpoint | Fitting completion tag completed and applied to each fitting
label | 33ea297b-7501-55d0-8aa2-b116397468c5 |  | note | Refer to Swagelok book for tube/thread size pressure ratings
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | bd99c82c-4eaa-5bc2-aaeb-4a3bbbbba5ed |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 7b5fd86b-d1a4-5f43-9590-46f82de35901 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 0a1d47ea-a6b5-5542-87aa-f14312bd5b39 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-06 Instrument Installation |  |  |  |  | Yes | ITR-I-06 Instrument Installation | f1e60cbc-ae8c-4699-ab91-63f911090425
checkpoint-group |  |  | section | Checklist items
checkpoint-status |  |  | checkpoint | Check instrument nameplate details are correct in accordance with instrument index
text | def52551-1e0b-5c38-9308-080635a972ea |  | textbox | Make:
text | b4640b2f-dc11-5171-b848-5416e59b8659 |  | textbox | Model:
text | 7060560a-99b7-5de8-be24-7a6128fe4025 |  | textbox | Serial No:
checkpoint-status |  |  | checkpoint | Ingress protection is suitable for area
text | 46f797ed-6e16-5209-8282-7964fd29e2e8 |  | textbox | IP rating:
checkpoint-status |  |  | checkpoint | Instrument rating is correct for hazardous area
text | 821bb289-f05e-5caa-9859-8963e91fc6bc |  | textbox | Haz Rating:
checkpoint-status |  |  | checkpoint | Instrument mounted correctly, elevation correct and free from vibration
checkpoint-status |  |  | checkpoint | Instrument is accessible for maintenance and clear of obstruction
checkpoint-status |  |  | checkpoint | Vent lines are directed into a safe area
checkpoint-status |  |  | checkpoint | Cable glands rated and installed correctly. Spare entries plugged with correctly rated plug
checkpoint-status |  |  | checkpoint | Impulse, hydraulic, pneumatics, lines and air headers correctly installed and supported
checkpoint-status |  |  | checkpoint | Instrument earthed according to client specification
checkpoint-status |  |  | checkpoint | Relevant ITRs for type of instrument completed in conjunction with this (if applicable)
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | e3646f19-811e-5b65-86dc-9986ff5979e7 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | eb92266f-f9bb-5a45-b356-b5b6125935b2 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | 6a53e8b9-0586-5052-b8fa-45a39631ca16 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-05 Analogue Valve & Ancillaries (Pre-Installation) |  |  |  |  | Yes | ITR-I-05 Analogue Valve & Ancillaries (Pre-Installation) | f719fe49-6da0-4848-9abb-ab2c8f8b228a
checkpoint-group |  |  | section | Equipment
checkpoint-status |  |  | checkpoint | All equipment checked against correct revision of Instrument index for Manufacturer, Type and Model No.
checkpoint-status |  |  | checkpoint | Equipment checked for additional items as applicable
checkpoint-status |  |  | checkpoint | Complete ITR-I-05A and attach
checkpoint-group |  |  | section | Valve
checkpoint-status |  |  | checkpoint | Valve
text | 4d73de96-5914-56e2-8e2e-cc2b7717421b |  | textbox | Size:
text | 39b7316e-5768-5424-9571-b3cbbfa818bb |  | textbox | Flange type:
checkpoint-status |  |  | checkpoint | Material certification correct
checkpoint-status |  |  | checkpoint | Trim material correct
text | ea18c670-d28a-5273-9872-9267ebcd21c3 |  | textbox | Rating:
text | efe0d44b-b6fc-5d96-8946-7c4237998c9f |  | textbox | Service:
checkpoint-status |  |  | checkpoint | Body material correct
text | 635405da-f695-554e-bdc3-be4aa3777aad |  | textbox | Leakage class:
checkpoint-group |  |  | section | Actuator
checkpoint-status |  |  | checkpoint | Actuator
text | feb122dc-e65a-5476-9fb7-0885e7c2c908 |  | textbox | Input range:
checkpoint-status |  |  | checkpoint | Failure action
checkpoint-status |  |  | checkpoint | Hand wheel operation correct
checkpoint-group |  |  | section | Positioner
checkpoint-status |  |  | checkpoint | Positioner
text | de6f61b5-6ae5-55b2-b02c-a90acefa8a76 |  | textbox | Signal range
text | 4a4d597e-1b21-5769-9ace-1c91f9f2d6ee |  | textbox | Output range
checkpoint-group |  |  | section | I/P Converter
checkpoint-status |  |  | checkpoint | I/P Converter
text | 68bf7fa9-67ad-5bb4-a41a-94e80fccca27 |  | textbox | Signal range
text | eee5303f-9206-5701-9dd7-0369d44ef7ce |  | textbox | Output range
checkpoint-group |  |  | section | Filter/Regulator
checkpoint-status |  |  | checkpoint | Filter/Regulator
text | 83d9ece0-cd74-559e-a856-18a97da542c8 |  | textbox | Range
text | afa1e199-5740-52ef-99f0-a12cf98d9b40 |  | textbox | Pressure setting
checkpoint-group |  |  | section | Fail Action
checkpoint-status |  |  | checkpoint | Fail Action
select | 9f113fd5-3c0e-58e8-a3d0-47efff08a2df |  | dropdown | Electrical Fail Action | FO, FC, FL
select | 8b15babb-f946-59d4-afb3-a6b1b20d4c41 |  | dropdown | Motive Force | FO, FC, FL
checkpoint-group |  |  | section | Proximity Detectors
checkpoint-status |  |  | checkpoint | Open switch set
checkpoint-status |  |  | checkpoint | Open switch mode setting correct
checkpoint-status |  |  | checkpoint | Closed switch set
checkpoint-status |  |  | checkpoint | Closed switch mode setting correct
checkpoint-status |  |  | checkpoint | Electrical connections correct
checkpoint-status |  |  | checkpoint | Electrical certification correct
checkpoint-group |  |  | section | Solenoid Valve
checkpoint-status |  |  | checkpoint | Operation correct
checkpoint-status |  |  | checkpoint | Electrical connections correct
checkpoint-status |  |  | checkpoint | Electrical certification correct
text | f3ca9d3a-1310-5d8f-95cd-d552ac41928c |  | textbox | Voltage:
checkpoint-status |  |  | checkpoint | Pneumatic connections correct
text | 1e6efe58-b23f-5c8f-8339-89528fd5e73e |  | textbox | Pneumatic pressure
checkpoint-group |  |  | section | Pilot Valve
checkpoint-status |  |  | checkpoint | Pneumatic connections correct
checkpoint-status |  |  | checkpoint | Operation correct
checkpoint-status |  |  | checkpoint | Action/Lockup
checkpoint-group |  |  | section | Hydraulic Actuator
checkpoint-status |  |  | checkpoint | Hydraulic Actuator
text | 3df9d727-8004-508a-9eed-8a3ede7ed104 |  | textbox | Working pressure
text | 13ad6e83-49ae-52ee-ae25-5fd8c60b0569 |  | textbox | Manifold pressure
text | dd241e83-1b0e-5a93-9980-33991fe83d2b |  | textbox | Fluid type
checkpoint-status |  |  | checkpoint | Hydraulic connections correct
text | 1a60e984-2ff5-54c9-8307-64867b87b242 |  | textbox | Regulator pressure setting
checkpoint-status |  |  | checkpoint | Pilot operation correct
checkpoint-group |  |  | section | Accumulator
checkpoint-status |  |  | checkpoint | N2 Charge required
text | 4a1369b4-9d56-530b-8ac6-5e4f5cca3757 |  | textbox | N2 Pre-charge pressure
text | deecc009-3b24-538d-a5c1-58898b373fba |  | textbox | Pressure switch setting
text | 59ff445a-2ca0-5b16-8afc-dfb23ea5757f |  | textbox | Working pressure
text | d09cc501-701e-54b7-baa2-dee6e23c95f8 |  | textbox | Output range
checkpoint-status |  |  | checkpoint | Volume tank & check valve installed correctly
checkpoint-group |  |  | section | Electric Actuator
checkpoint-status |  |  | checkpoint | Electric Actuator
text | 9b16c8b6-d8ed-5433-90d3-53765ab88491 |  | textbox | Voltage:
text | 1fdf5438-01fa-5b49-b8dc-d426cd41f2c6 |  | textbox | Electrical certification correct
text | a3d2f297-63cc-5d38-9fa9-a292f9acd60e |  | textbox | Electrical connections correct
text | 96bfb04e-c966-5ee2-bc1b-b51034ebcff9 |  | textbox | Remote operation correct
text | 2d92bfad-40ff-5860-a2fd-e2a881bd6233 |  | textbox | Local hand operation correct
text | 8457c310-4ad8-5350-bdc3-31b43b6794fa |  | textbox | Torque switches and travel stops set
checkpoint-group |  |  | section | Miscellaneous Equipment
checkpoint-status |  |  | checkpoint | Miscellaneous Equipment
text | e349a9e3-cbca-58d2-a43f-01f4db2eda4d |  | textbox | Description
text | 5cbe7a61-afe2-54c9-8169-c590802acd09 |  | textbox | Manufacturer
text | 5875e5a8-388e-5f36-bf9f-5f379562ff32 |  | textbox | Model No:
text | 2b99060f-ae2b-5029-96c8-80d6800f22f2 |  | textbox | Serial No:
text | 31ae7680-8058-53ff-9810-f4875ea35918 |  | textbox | Range:
checkpoint-group |  |  | section | Test Equipment
checkpoint-status |  |  | checkpoint | Test Equipment
text | c99a8340-ac9b-5631-bc38-e0b10d2c0b59 |  | textbox | Make:
text | 7a70f716-4c22-5a79-b503-2023ea6f8340 |  | textbox | Model:
text | 6d51b2d6-ac58-56f1-8cf7-852bed01c502 |  | textbox | Serial No:
text | 15d83e15-7b89-5d51-8bc7-fadbda2d12b5 |  | textbox | Calibration Expiry:
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 6d754e4e-3349-5923-9b83-09e9e1b0573b |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 9777a70b-90b9-533d-970f-551abfbae58b |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | badc6c7a-a162-54f1-9ab4-1762e7c3b101 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-12 Telecommunications Equipment Panel |  |  |  |  | Yes | ITR-I-12 Telecommunications Equipment Panel | f9576fda-23f5-42a5-ad40-5d1c19845e68
checkpoint-group |  |  | section | Telecommunications Equipment Panel
checkpoint-status |  |  | checkpoint | Ensure equipment panel is securely mounted within the Telecommunications Cabinet in the correct location as shown on general layout drawings:
checkpoint-status |  |  | checkpoint | Check tag number is in accordance with Telecommunications Equipment List.
checkpoint-status |  |  | checkpoint | Ensure there is no visible damage to the equipment and all meters, LED indicators, switches and fittings are in good order.
checkpoint-status |  |  | checkpoint | Confirm equipment panel has adequate air ventilation, as appropriate to its internal heat generation.
checkpoint-status |  |  | checkpoint | Confirm any slide-in cards are firmly fitted to the equipment panel and properly identified.
checkpoint-status |  |  | checkpoint | Check panel air vents are clean and free of dust and dirt.
checkpoint-status |  |  | checkpoint | Check equipment panel external earthing connections are securely fitted and properly terminated on the cabinet protective earth bar.
checkpoint-status |  |  | checkpoint | Where fitted, check instrument earth connections are securely fitted and properly terminated on the cabinet instrument earth bar.
checkpoint-status |  |  | checkpoint | Ensure any AC power connection(s) is securely fitted and cabled to the appropriate Power Distribution Panel circuit breaker(s).
checkpoint-status |  |  | checkpoint | Check sealing of all cable penetration (where applicable).
checkpoint-status |  |  | checkpoint | Ensure all signal cables, including any RF co-axial cables, are correctly identified and securely fitted to the equipment panel.
checkpoint-status |  |  | checkpoint | Where fitted ensure panel sliding rails are operating smoothly and without risk of damage to external cables and connectors. Check alignment of false floor after panel installation (where applicable).
checkpoint-status |  |  | checkpoint | Confirm panel is readily accessible for inspection and maintenance.
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | 3728aa77-0602-5760-bdba-c18b2ba5475a |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | 4887e746-2eca-5b5e-aa4a-bf650fc920ae |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | ee9e1b07-3eac-5f15-8928-dafaba4097d3 |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed
checklist-sectioned |  |  | checklist | ITR-I-14 Flow Meter Installation |  |  |  |  | Yes | ITR-I-14 Flow Meter Installation | fb070f86-3873-4a15-a61e-dd88ee5023d1
checkpoint-group |  |  | section | Flow Meter Installation
checkpoint-status |  |  | checkpoint | Check instrument nameplate details are correct in accordance with the instrument index
checkpoint-status |  |  | checkpoint | Flow meter calibrated before installation (ITR-I-07 Instrument Calibration)
checkpoint-status |  |  | checkpoint | Ensure location and tapping point is verified as per P&ID & location drawings
checkpoint-status |  |  | checkpoint | Ensure direction of flow is correct with respect to flow meter
checkpoint-status |  |  | checkpoint | Check mechanical clearance is adequate for installation of flow meter
checkpoint-status |  |  | checkpoint | Verify type and size of gasket is correct between process line and measuring unit flange
checkpoint-status |  |  | checkpoint | Ensure correct nut and bolt grade and material for connecting unit to process line
checkpoint-status |  |  | checkpoint | Verify display/cover is oriented for ease of use for operators and access for technicians
checkpoint-group |  |  | section | Acceptance Signatures
checkpoint-status |  |  | checkpoint | Test/Inspection carried out by:
text | da16faa3-bdc3-58ec-9bbf-c3c8737448f5 |  | textbox | Test/Inspection carried out by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Test/Inspection approved by:
text | bff134c7-c644-5574-b654-33d72ad71223 |  | textbox | Test/Inspection approved by:
holdpoint |  |  | signoff | Signed
checkpoint-status |  |  | checkpoint | Client Representative
text | c926783e-5b25-5c94-8940-dbeb830ed18b |  | textbox | Client Representative
holdpoint |  |  | signoff | Signed