## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
| Fauna Bridge 3 | To Contain Precast Beam Checklist | Ability to Add within Bridge Checklists
Fauna Bridge 2
Fauna Bridge 1
Alkimos Southern Bus Bridge
Alkimos Pedestrian (Service) Bridge
Eglington Ave Bridge
Romeo Road Bridge
Tuart Drive Bridge
Alkimos Capping Bridge
Brindabella Bridge

## Resources
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | HSE Management Plan
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Prestress
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Concrete Repair Methodology
checkpoint | Shop Drawings
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S50 Concrete Mix Design Approved by Client
label | Supplier : Holcim
label | Mix Code: WS502MP11 (S50/20/200)
label | Slump : 200 ± 40
checkpoint | S50 Concrete Mix Design Approved by Client
label | Supplier : WA Premix
label | Mix Code: BH1447 (S50/14/200)
label | Slump : 200 ± 40
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Prestressing Tendons
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Ensure that all Coil Numbers are recorded
checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint | Stressing Jack Calibration Certificates
section | Lifting Anchors
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Precast Beams
section | Pre-Pour Checklist
text | Cast Number | 1
text | Bridge Name | 3
text | Precast Beam 1 | 4
text | Precast Beam 2 | 5
text | Mould Beam 1
text | Mould Beam 2
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Cover maintained and within tolerance
checkpoint | All Cast-in Items are installed in accordance with Drawings
label | Cast-in Items
label | Fittings
label | Lifters Position and Type
checkpoint | Prestressing Strands
text | Enter Coil Number Used for this Cast
label | Sag Load all Strand
label | Mutli-Stress as per Pre-stressing Procedures
checkpoint | All Temperature Loggers are installed as per Approved WMS
label | Every 25m
label | 1 x End Block Mid-Diaphragm
label | 1 x Within Cover Zone
label | 1 x Within Tent/Tarp Enclosure (Outside concrete)
label | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
checkpoint | Ensure All temperature Loggers are Working (Check App)
checkpoint | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 2
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket 1 | 8
text | Concrete Delivery Docket 2 | 9
text | Concrete Delivery Docket 3 | 10
text | Concrete Delivery Docket 4 | 11
text | Concrete Delivery Docket 5 | 12
text | Concrete Delivery Docket 6 | 13
checkpoint | Total Concrete Volume
text | Volume (m3) | 7
checkpoint | Mix Design Verified (BH1447 - S50 or WS502MP11 - S50)
label | Concrete Mix Strength (Mpa) | 6
checkpoint | Ambient Temperature within Limits
label | 5 - 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance
text | Slump 1 | 14
text | Slump 2 | 15
label | 200 ± 40mm
checkpoint | Truck Tested for strength
text | Test Report Reference Number 1
text | Test Report Reference Number 2
checkpoint | Time Lag Between Trucks (< 20min)
checkpoint | Concrete Placed within 90min from Batching Plant
checkpoint | No Free Fall During Pour (< 2m)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR CLIENT TO SIGN OFF)
text | Stripping Strength | 16
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Product Clearly Labelled
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
label | Cast-in Items
label | Fittings
label | Lifters Position and Type
checkpoint | Lifted and Handled as per Drawings
checkpoint | Storage/Stacking as per Approved Plan
checkpoint | Curing as per Approved Methodology
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush
text | Strands Bulbs as per Drawing
text | Starter Bars are Bent as Required
text | All Drain Holes are Clean
text | All Miscellaneous Items are Completed
checkpoint | Survey Hog of Beams (Dumpy)
text | First Reading (Once Stripped)
text | Second Reading (if required)
text | Final Reading (Prior to Delivery)
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report Number 1
text | 7 Day Strength (1) | 17
text | 7 Day Strength (2) | 18
text | 28 Day Strength (3) | 19
text | 28 Day Strength (4) | 20
text | 28 Day Strength (5) | 21
text | 28 Day Strength (6) | 22
section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
checkpoint | Completed by
checkpoint | Reviewed by (INTERNAL HOLD POINT)
checkpoint | Client Representative (if applicable)