## ITP Cover Page
[BLANK] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 106 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 106
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement Drains |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA F/5 & TNZ/F7
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Review | 2023-03-31 |  | Callun Purchase |  | First revision for internal review |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2023-03-31 |  | Callun Purchase |  | First Revision for External Review and Approval |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
|  |  |  | Subsoil |  |  | [BLANK] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JESA to the Engineer before works | Downer | Construction Pack | Submit 10 days prior to commencement of works | H | PE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.04 | Topographic surveys for measurement | The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities. | PS 2.2.12 | As-built | Prior to works and Post Works | H | PE
3.01.05 | Permits | The contractor shall complete internal and external permits for construction requirements | ITP Register | ITP Sign Off | Prior to commencement of construction activity | R | SE
3.01.06 | Stakeholder Management | Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners | Project Stakeholder Management Plan | ITP Sign Off | Prior to Construction with continue updates throughout the works | R | SE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | SUB ACTIVITY
4.01.01 | Pavement Pipes | Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | GWS 3.2.1 | Datasheet | Prior to installation | C | SE
4.01.02 | Pavement Drainage Aggregate (20/40) | When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/5 including gradings | GWS 3.2.2 & 3.4 | PSD, CR | Prior to installation | C | SE
4.01.03 | Filter Cloth | Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent) | GWS 3.2.3 | Datasheet | Every 1,000m3. At least two weeks prior to works. | C | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | SUB ACTIVITY
5.01.01 | Filter Cloth Wrap Inspection | Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. | GWS 3.2.2 | Site Record | prior to backfilling | HP | ENG
5.01.02 | Trench Backfill | Backfilling of all trenches should be to the fill standard of the material previously trenched through | GWS 3.3 | Site Record | Each trench | I | SE
5.01.03 | Drainage Outlets and Inspection Points | At least one temporary flush point is required for each pavement drainage system to enable flushing of the system once the earthworks are complete. | GWS 3.6 | Site Records | Each Subsoil Line | I | SE
5.01.04 | Subsoil Flushing | On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer. | GWS 3.6 | Site Records | On completion of earthworks | HP | ENG
5.01.05 | Survey | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level | Downer | Records | Post construction | H | SV
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | PE
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
6.01.05 | Photos | Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill. | Downer | Photo Records | Post construction | H | SE